Implementation Plan

Of

Philadelphia Gas Works

To The

Stratified Management & Operations Audit

For the

Pennsylvania Public Utility Commission
Bureau of Audits

Docket No. D-06MGT042

January 2009

Introduction

PGW is pleased to submit this Implementation Plan for review by the Pennsylvania Public Utility Commission (PAPUC). The Implementation Plan is in response to the recommendations contained in the Stratified Management and Operations Audit Report (Docket No. D-06MGT042) prepared by Schumaker & Company under the direction of PAPUC Bureau of Audits – Management Audit Division and issued on December 24, 2008. The Implementation Plan provides PGW’s commitment to act on the recommendations by addressing opportunities for improvement in operational effectiveness while improving service to our customers.

Of the ninety-three (93) recommendations contained in the Audit Report, PGW has accepted eighty-eight (88) of them completely, accepted in-part three (3), and rejected two (2).

As requested, this Implementation Plan details the actions to be taken, the expected completion dates and the individuals responsible for implementing each recommendation. It should be noted that, in a great many of the proposed Action steps, management makes reference to the Business Transformation (BT) initiative. For a number of years there has been a recognized need for transformative steps to address fundamental change in Customer Affairs, Field Operations and the Supply Chain: Procurement, Materials Management and Fleet Operations. In effect, the need was to change the business model under which this utility has operated for decades. This audit is being completed on the cusp of implementation of Phase One of this effort that will address many of the consultants’ findings.  It is anticipated that the Phase Two BT design and implementation efforts, to start in late spring or early summer, will address much of the balance of the audit findings.  If for some reason the company does not get regulatory approval for the remaining BT program in the next several months or a particular item falls outside of the scope of that future BT design, management will return to the Commission with adjusted Action steps for the affected recommendations.

PGW management wishes to express its appreciation to the Audit staff and to Schumaker & Co. for their collective efforts in assisting PGW in furthering the company’s program for continuous improvement. From the perspective of management this report is a very positive outcome to an extensive process and we look forward demonstrating the successful implementation of the recommendations we have accepted.

# Chapter II – Executive Management and Human Resources

|  | Description | Page | PGW Response |
| --- | --- | --- | --- |
| II-1 | Develop an external relations strategic/business plan | 9 | Accepted |
| II-2 | Expand and document community relations and regulatory relations programs. | 10 | Accepted |
| II-3 | Implement management incentive compensation | 11 | Accepted |
| II-4 | Assess root causes of absenteeism and implement appropriate Human Resources and Organizational Development strategies to address these causes. | 12 | Accepted |
| II-5 | Develop a comprehensive return-to-work process, including metrics, for employees with medical restrictions | 13 | Accepted |
| II-6 | Appoint a return-to-work coordinator as part of the Absence control group in Human Resources. | 15 | Accepted |
| II-7 | Implement a comprehensive institutional knowledge loss risk assessment and workforce planning process. | 16 | Accepted |

# Chapter III – Support Services

|  | Description | Page | PGW Response |
| --- | --- | --- | --- |
| III-1 | Formalize a regularly conducted, long-range planning process. | 17 | Accepted |
| III-2 | Complete existing IS policies and procedures and expand focus to include internal IS guidelines. | 18 | Accepted |
| III-3 | Expand the purpose of the QA organization to become actively involved in all phases of major technology projects. | 19 | Accepted |
| III-4 | Use Microsoft Project Server to effectively track activities, milestones, and resources for all major technology projects. | 20 | Accepted |
| III-5 | Properly secure the PGW telecommunications and server room. | 21 | Accepted |
| III-6 | Expand emphasis on achievement of project management and technical certifications. | 22 | Accepted |
| III-7 | Establish Service Level Agreements (SLAs) with all major IS customers | 23 | Accepted |
|  | Description | Page | PGW Response |
| III-8 | Keep to the desired schedule for disaster-recovery tests, including frequent use of comprehensive tests that are fully documented. | 24 | Accepted |
| III-9 | Incorporate disaster recovery into business-continuity plan process and expand its focus. | 25 | Accepted |
| III-10 | Develop a specific human resources plan to ensure that the correct number of experienced replacements will be available to take over for the mechanics who will be retiring in the next few years. | 26 | Accepted |
| III-11 | Use information collected from outside contractors to make decisions on which FO activities can best be performed by outside contractors and what areas of FO need to be improved to be comparable with outside contractors. | 27 | Accepted |
| III-12 | Initiate a concerted effort to automate the production of the monthly PM schedule, thereby resulting in manpower time savings. | 28 | Accepted |
| III-13 | Evaluate the beneficial impact that having an auto–parts-knowledgeable person in the storeroom would have on improving the process of parts identification and ordering. | 29 | Accepted |
| III-14 | Develop specific programs that are intended to improve the levels of cooperation and communication between the FO Department and the various field operating groups. | 30 | Accepted |
| III-15 | Initiate an evaluation of the operations of the Facilities Department to identify procedures and processes that could be improved. | 31 | Accepted |
| III-16 | Initiate an internal audit of the Facilities Department. | 32 | Accepted |
| III-17 | Initiate a formal material-demand-requirements forecasting program in the Procurement Department. | 33 | Accepted |
| III-18 | Change the focus of the Procurement Department from being primarily an administrative group to being a proactive procurement organization that is actively involved in all aspects of the purchasing process. | 34 | Accepted |
| III-19 | Develop a program to perform regular surveys of the operating department clients of the PGW Procurement Department concerning the performance of the largest vendors and any other vendors with which problems have been experienced in the past. | 35 | Accepted |
| III-20 | Rotate the buyers across the vendors on a regularly scheduled basis, for both security and cross-training reasons. | 36 | Accepted in Part |
| III-21 | Develop a program to collect and use metrics that are related to individual buyer performance. | 37 | Accepted |
| III-22 | Develop a program to collect metrics related to the savings or contributions to PGW’s profitability that are achieved through the work of the Procurement Department. | 38 | Accepted |

|  | Description | Page | PGW Response |
| --- | --- | --- | --- |
| III-23 | Explore the available options for creating a purchasing consortium arrangement with the City of Philadelphia Procurement Department. | 39 | Accepted |
| III-24 | Evaluate the additional functionality that is not being used in the Oracle procurement application and develop a formal plan and schedule for taking advantage of those features, one that would have the most beneficial impact on the operations of the Procurement Department. | 40 | Accepted |
| III-25 | Identify operations and functions that could be better integrated between the Procurement Department and the Materials Management Department. | 41 | Accepted |
| III-26 | Evaluate the electronic commerce capabilities that are available through the Oracle e-procurement application and determine if these capabilities would be cost effective to implement. | 42 | Accepted |
| III-27 | Evaluate the purchasing authorization levels that are currently in place and identify potential areas that could be streamlined. | 43 | Accepted |
| III-28 | Explore the advantages that increased partnering with vendors and designation of strategic suppliers would bring to the procurement process at PGW. | 44 | Accepted |
| III-29 | Increase the amount at which a sealed bid is required from the current $10,000 threshold to a more realistic level of $25,000 or more. | 45 | Accepted in Part |
| III-30 | Initiate increased efforts to reduce the level of inventory in the MMD storerooms. | 46 | Accepted |
| III-31 | Initiate efforts to reduce the number of employees in the MMD. | 47 | Accepted |
| III-32 | Initiate a focused effort to increase the level of inventory turnover in the MMD storerooms and in aggregate. | 48 | Accepted |
| III-33 | Perform an analysis to determine the best way to utilize the spare parts classification and take the necessary steps to ensure that it is applied evenly across the storerooms. | 49 | Accepted |
| III-34 | Develop formal procedures to guide and govern the day-to-day operations of the MMD storerooms. | 50 | Accepted |
| III-35 | Conduct an evaluation to determine whether the Material Delivery function is cost effective when provided on an in-house basis or if the service could be provided as well and more cost effectively by an external contractor. | 51 | Accepted |

|  | Description | Page | PGW Response |
| --- | --- | --- | --- |
| III-36 | Conduct an evaluation to identify if there are potential advantages to be gained by transferring the gasoline and diesel fuel provision function to a private contractor. | 52 | Accepted |
| III-37 | Conduct an analysis to determine if it would be cost and operationally effective to outsource the vehicle parts procurement and inventory function. | 53 | Accepted |
| III-38 | Initiate efforts to increase the usage of vendor stocking arrangements. | 54 | Accepted |
| III-39 | Develop a high-level cross-training program that would provide MMD supervisors with increased training in the requirements and preferences of the field operations groups that are their clients. | 55 | Accepted |
| III-40 | Review the operational advantages to be gained from the implementation of a bar-coding program in the MMD storerooms. | 56 | Accepted |
| III-41 | Conduct an analysis to determine the economic and operational benefits that would be gained from the consolidation of the MMD storerooms. | 57 | Accepted |
| III-42 | Evaluate the unused functionality of the Oracle inventory management application and develop a formal plan and schedule for taking advantage of those features that would have the most beneficial impact on the MMD operations. | 58 | Accepted |
| III-43 | Formalize and enhance PGW’s Enterprise Risk Management (ERM) program. | 59 | Accepted |
| III-44 | Conduct a formal compensation study to evaluate marketplace salaries for attorneys and paralegals. | 60 | Accepted |

# Chapter IV – Corporate Governance

|  | Description | Page | PGW Response |
| --- | --- | --- | --- |
| IV-1 | Streamline the corporate governance processes of PGW. | 61 | Reject |
| IV-2 | Develop an ongoing Ethics training program. | 62 | Accepted |
| IV-3 | Strengthen the Board Audit Committee function. | 63 | Accepted |
| IV-4 | Modify the IA program structure by addressing all noted deficiencies. | 64 | Accepted |
| IV-5 | Expedite the pursuit of the Business Transformation project. | 66 | Accepted |

# Chapter V – Financial Management

|  | Description | Page | PGW Response |
| --- | --- | --- | --- |
| V-1 | Institute flexible work rules and hours in financial management functions | 67 | Accepted |
| V-2 | Update the payroll system cost analysis. | 68 | Accepted |
| V-3 | Improve the timing of the budget preparation and approval process | 69 | Accepted |
| V-4 | Strengthen PGW’s Internal Audit (IA) function and enhance internal controls. | 70 | Accepted |
| V-5 | Implement a process to ensure that the IA Director meets quarterly with the Board’s Audit Committee. | 71 | Accepted |

# Chapter VI – Diversity and DEEO

|  | Description | Page | PGW Response |
| --- | --- | --- | --- |
| VI-1 | Expand PGW’s diversity program beyond compliance-oriented activities. | 72 | Accepted |
| VI-2 | Begin filing comprehensive diversity reports to the PaPUC annually. | 73 | Accepted |
| VI-3 | Explore the use of spend targets in the Procurement Department’s performance objectives. | 74 | Accepted |

# Chapter VII – System Reliability Performance

|  | Description | Page | PGW Response |
| --- | --- | --- | --- |
| VII-1 | Provide at least two controllers on all shifts for the Gas Control Center. | 75 | Accepted |
| VII-2 | Take steps to plan for the retirements that could have a major impact on the ability to staff the Gas Control Center. | 76 | Accepted |

|  | Description | Page | PGW Response |
| --- | --- | --- | --- |
| VII-3 | Place the RFP that solicits gas commodity suppliers on the PGW electronic bulletin board. | 77 | Accepted |
| VII-4 | Institute a program to perform vendor credit checks in order to qualify for a NASEB purchasing agreement, and to perform credit evaluations on a regular basis for existing suppliers. | 78 | Accepted |
| VII-5 | Evaluate an all-inclusive or enterprise computer system to track the gathering of transactions so that supplier invoices, transportation invoices, and sales of excess suppliers are captured. | 79 | Accepted |
| VII-6 | Evaluate, year-to-year as well as on a real time basis, PGW’s gas supply assets to determine, based on the LNG levels, whether programs for storage capacity can be created to add value and savings as part of the 1307(f) review. | 80 | Accepted |
| VII-7 | Enhance the FSD and Distribution business processes through more computerization. | 81 | Accepted |
| VII-8 | Centralize all field force planning, scheduling, performance monitoring and analysis functions. | 82 | Accepted |
| VII-9 | PGW has implemented a new main replacement model that is an improvement over the previous model; however, further refinements are still possible. PGW should consider certain future enhancements to the Advantica program after gaining experience with the current implementation. | 83 | Accepted |
| VII-10 | Set more aggressive performance targets on gas leak response. | 84 | Accepted |
| VII-11 | Build a stronger gas theft of service program. | 85 | Accepted |
| VII-12 | Reassess PGW’s future field operation staffing levels based on its needs taking into consideration pending retirements. | 86 | Accepted |

# Chapter VIII – Customer Service

|  | Description | Page | PGW Response |
| --- | --- | --- | --- |
| VIII-1 | Investigate the possibility of streamlining some of the paper work in PGW’s Universal Services Programs through some type of computerization or electronic document management program. | 87 | Accepted in Part |
| VIII-2 | Hire part-time CSRs and implement variable staffing levels based on predicted call volume. | 88 | Accepted |
|  | Description | Page | PGW Response |
| VIII-3 | Investigate methods to improve CSR selection and retention. | 89 | Accepted |
| VIII-4 | Include CSR turnover as a key performance indicator (KPI) for the call center. | 90 | Accepted |
| VIII-5 | Redesign the call center supervisor jobs to focus more on coaching and development. | 91 | Accepted |
| VIII-6 | Develop a method for measuring actual call center turnover rates. | 92 | Accepted |
| VIII-7 | Assess the root causes of absenteeism and address the quality of work/life issues in the call center in conjunction with the enforcement of absence policies. | 93 | Accepted |
| VIII-8 | Implement an annual comprehensive customer satisfaction analysis and develop an improvement strategy based on the results. | 94 | Accepted |
| VIII-9 | Address customer dissatisfaction/satisfaction drivers. | 95 | Accepted |
| VIII-10 | Make changes to the configuration of the various customer service district offices. | 96 | Accepted |
| VIII-11 | Make modest renovations to customer service district offices. | 97 | Accepted |
| VIII-12 | Provide privacy for LIHEAP applicants. | 98 | Accepted |
| VIII-13 | Demonstrate, periodically, to the PaPUC that the Parts and Labor Program is self supporting | 99 | Accepted |
| VIII-14 | Work with PFMC and the PGC to develop a plan for addressing the major issues facing the City of Philadelphia regarding PGW. | 100 | Reject |
| VIII-15 | Report the number of credit balance customers and credit balances that were initiated in any given year, and then annually report the reduction in those numbers and balances on the next five years (prior to being turned over to the Pennsylvania Department of Treasury). | 101 | Accepted |
| VIII-16 | Reevaluate the use of the soft-off program at PGW. | 102 | Accepted |
| VIII-17 | Undertake a major study to improve the gas theft prevention Program. | 103 | Accepted |

## Recommendation –# II -1

Develop an external relations strategic/business plan

## Response

Accepted

## Action

PGW has begun the drafting of an external relations plan that addresses strategic business needs.  The work will be completed and implemented.

## Individual Responsible

Steven P. Hershey, Vice President Regulatory and External Affairs

## Expected Completion Date

2nd Quarter FY 2009

## Recommendation # II-2

Expand and document community relations and regulatory relations programs.

## Response

Accepted

## Action

PGW will create a community relations plan that will build on and expand current activities.  The plan will include measuring the opinions of the Community Advisory Council members and other key community opinion leaders to identify appropriate needs.  PGW will use the results of the survey and other tools to create action priority plans.  We will also begin to track hours dedicated to working with community organizations.

PGW will also begin implementation of a plan to provide more frequent informal meetings and briefings with regulatory staff for effective exchange of information.  Such efforts will be documented with appropriate reports.

## Individuals Responsible

Wade Colclough, Director of Corporate Communications

Steven P. Hershey, Vice President, Regulatory and External Affairs

## Expected Completion Date

3rd Quarter FY 2009

## Recommendation # II-3

Implement management incentive compensation (Refer to Finding II-11).

## Response

Accepted

## Action

As noted in the Audit, “While we would not expect a municipal utility to have the generous incentive compensation of private sector companies, it should have a program in place and be able to offer incentives based on company performance every year.”

At the outset, it should be clarified that for purposes of this discussion, incentive based compensation is synonymous with performance based compensation.  Employees must achieve specific goals or targets in order to be rewarded.  These goals are targets are defined early in the year and refined throughout the year.  The employee’s achievement of these goals is measured and reflected in their annual performance review.  The score received in their annual review then translates into increased levels of compensation depending upon the level of achievement of their goals.

PGW has implemented and continues to refine its goals, metrics and performance review process which would enable the company to put such a compensation program into effect.

PGW’s ability to fund and implement such programs is contingent upon approvals by multiple layers of governance.

## Individual Responsible

William C. Muntzer – VP – Human Resources

Lorraine Webb – VP - Organizational Development

## Expected Completion Date

4th Quarter FY 2009– Contingent upon approval by various levels of governance.

## Recommendation II-4

Assess root causes of absenteeism and implement appropriate Human Resources and Organizational Development strategies to address these causes. (Refer to Finding II-12).

## Response

Accepted

## Action

PGW will provide additional resources for the employee survey.  It will encourage employee involvement in providing survey responses.  The company will provide supervisory training for attendance related issues.  The company will continue to examine and, where appropriate, offer work/family benefits to support employees who are working to meet both company and family responsibilities.

Meeting both work and family responsibilities is very difficult for many people.  While the company should be both cognizant of, and sympathetic to those difficulties, it must also be cognizant of the needs of its customers to ensure that employees are providing a high quality of service at reasonable costs.  Therefore, the company will also explore the tools it already provides to its employees to see if these tools can effectuate lower absenteeism.

## Individual Responsible

William C. Muntzer – VP – Human Resources

Lorraine Webb – VP - Organizational Development

## Expected Completion Date

4th Quarter FY 2009

## Recommendation # II-5

Develop a comprehensive return-to-work process, including metrics, for employees with medical restrictions (Refer to Finding II-13).

## Response

Accepted

## Action

The main premise of the finding by Schumacher & Company is that both the employee and employer benefit from the employee’s return to some job function as opposed to staying at home.  They also note that PGW already has an effective absence management program, a key component of which is the Employee Utilization Committee (EUC).  The EUC attempts to place sick or injured workers in temporary jobs until they can return to their normal position.

Schumacher & Company feels that the “jobs-based approach” does not return enough workers to the work place.  They propose a “task based approach” whereby the company would be required to develop a bank of value added tasks to be performed and identify the physical demands of the tasks.  The task bank would include work that the company may be having trouble completing.

The auditor proposes that the company develop a detailed plan for each employee experiencing a long term illness or injury.  The plan would include those specific tasks which could be performed at the varying stages of recovery and would need to be revised accordingly.  The employees would be assigned multiple tasks that would be closely aligned with the physical demands of the tasks versus the medical restrictions placed upon the employee.  Further, the program would have to be assessed through the use of a scorecard that looks at costs, durations, accommodation rates, and other appropriate indicators of the effort’s success.

The findings fail to state that the assignment of employees to tasks is currently being performed at the departmental level.  Not until the departments have exhausted every opportunity to provide employees some alternate work are the employees sent home and become part of the EUC process.

The company will identify tasks that have reduced levels of physical exertion and identify levels for lifting, reaching, walking, etc.  The company will also review all job processes to identify tasks that are a component of a job function.

A scorecard approach will be put into place to monitor the program; however, resources would have to be dedicated to monitoring and reporting on the progress of these individuals.

## Individual Responsible

William C. Muntzer – VP – Human Resources

Lorraine Webb – VP - Organizational Development

## Expected Completion Date

1st Quarter FY 2010

## Recommendation # II-6

Appoint a return-to-work coordinator as part of the Absence control group in Human Resources. (Refer to Finding II-13).

## Response

Accepted

## Action

This would require hiring an additional resource in the Absence Control Group in the Human Resources Department.

## Individual Responsible

William C. Muntzer – VP – Human Resources

## Expected Completion Date

4th Quarter FY 2009

## Recommendation # II-7

Implement a comprehensive institutional knowledge loss risk assessment and workforce planning process.  (Refer to Finding II-14).

## Response

Accepted

## Action

Staffing/Attrition/Knowledge Management Recommendations

PGW considers this type of issue to have enterprise wide impact; as a result a comprehensive strategy is being developed to address the looming attrition issues facing PGW over the next several years.  The program is designed to address organization culture, retention, knowledge management (collection, organization, distribution, and preservation), succession planning as well as hiring. Various programs have already been put in place and include; succession planning for senior management, a Senior Team development program and part-time worker program while others such as Knowledge Management (Gas Supply) and telecommuting (Information Services) are being piloted. Still others such as flexible work schedules and the benefits mix are being evaluated.

## Individual Responsible

Lorraine Webb VP of Organizational Development

William Muntzer VP of Human Resources

## Expected Completion Date

2nd Quarter FY 2014

## Recommendation # III-1

Formalize a regularly conducted, long-range planning process.

## Response

Accepted

## Action

IS will finalize its new strategic plan document in 2Q FY2009 and will implement a formal annual review to take place in September of each year. Once finalized, the document will be posted on the intranet so that it is accessible to other interested parties within PGW.

## Individual Responsible

Eloise Young – VP & Chief Information Officer

## Expected Completion Date

4th Quarter FY 2009

## Recommendation # III-2

Complete existing IS policies and procedures and expand focus to include internal IS guidelines.

## Response

Accepted

## Action

IS policies will be finalized, signed off and stored in Policy Center as well as on the intranet as part of the strategy writing effort. These policies and procedures will be reviewed annually and updated as needed.

## Individual Responsible

Eloise Young – VP & Chief Information Officer

## Expected Completion Date

4th Quarter FY 2009

## Recommendation # III-3

## Expand the purpose of the QA organization to become actively involved in all phases of major technology projects.

## Response

Accepted

## Action

IS’ updated project initiation process requires the inclusion of QA from the inception of any project. The updated documentation will be posted on the intranet in the 2Q FY2009. QA Analysts’ will receive formal training on requirement gathering and project lifecycle by 4Q FY2009.  Ensuring that QA is an active part of projects from inception will be an ongoing effort.

## Individual Responsible

Joseph Szlanic – Dir. Tech Strategy Support

Michael Heron - Dir. Info Control & Compliance

## Expected Completion Date

4th Quarter FY 2009

## Recommendation # III-4

Use Microsoft Project Server to effectively track activities, milestones, and resources for all major technology projects.

## Response

Accepted

## Action

Project Server has been implemented and is being used to track all IS and Business Transformation projects. IS has contracted with an experienced Microsoft partner to resolve technical issues associated with the product. IS has developed a set of views that provide insight into project statuses and rankings. Refining the product to meet our needs will be an ongoing effort.

The Office of Business Transformation and IS Project Managers meet weekly to discuss projects and ensure that best practices and a common set of processes are being adhered to.

## Individual Responsible

Eloise Young –VP & Chief Information Officer

## Expected Completion Date

Completed - July 2008

## Recommendation # III-5

## Properly secure the PGW telecommunications and server room.

## Response

Accepted

## Action

IS will have a lock placed on the door between the server room and the Help Desk area.

## Individual Responsible

Eloise Young – VP & Chief Information Officer

Michael Heron – Dir. Info Control & Compliance

## Expected Completion Date

3rd Quarter FY 2009

## Recommendation # III-6

## Expand emphasis on achievement of project management and technical certifications.

## Response

Accepted

## Action

IS has updated its documentation on each employee to include certifications attained. The IS Administration section is responsible for maintaining this information using the On Track software. Individual development plans will be developed for each IS employee by April 2009. These plans will include technical and project management certifications. IS will continue to encourage its employees to seek certifications.

## Individual Responsible

Driscilla Wanser-Bynum – IS Dir. Admin & Communications

## Expected Completion Date

3rd Quarter FY 2009– individual development plans

Ongoing – updated documentation in On Track

## Recommendation # III-7

Establish Service Level Agreements (SLAs) with all major IS customers

## Response

Accepted

## Action

IS will identify its major client groups in its strategy document which will be completed by the end of January 2009. The department will negotiate written, formalized service level agreements with each of these groups by 1Q FY 2010. IS will develop a formalized feedback mechanism as part of its strategy documentation and will have completed the first round by 3Q FY2009.

## Individual Responsible

Joseph Szlanic– Dir. Tech Strategy Support

## Expected Completion Date

## 1st Quarter FY 2010

## Recommendation # III-8

## Keep to the desired schedule for disaster-recovery tests, including frequent use of comprehensive tests that are fully documented.

## Response

Accepted

## Action

IS has implemented a test lab so that server build documentation can be developed and tested in between DR tests. IS and Internal Audits will continue to work together to ensure that all 2007 recommendations are addressed.

## Individual Responsible

Michael Heron – Dir. Info Control & Compliance

## Expected Completion Date

2nd Quarter FY 2009

## Recommendation # III-9

## Incorporate disaster recovery into business-continuity plan process and expand its focus.

## Response

Accepted

## Action

Business Continuity has included IS in its most recent pandemic planning sessions. IS will work with Corporate Preparedness and Internal Auditing to expand the scope of our DR tests to include business continuity scenarios.

## Individual Responsible

Michael Heron –Dir. Info Control & Compliance

## Expected Completion Date

4th Quarter FY 2009

## Recommendation # III-10

## Develop a specific human resources plan to ensure that the correct number of experienced replacements will be available to take over for the mechanics who will be retiring in the next few years.  (Refer to Finding III-14.)

Audit Noted: This review and plan development should be done in conjunction with the PGW Human Resources Department to draw on their specialized expertise in developing such plans.  Due to a lack of new hiring for many years, numerous utilities across the country are facing or have faced similar issues with their experienced craft employees.  Some have discovered that identifying this potential situation and responding too late can create problems.  Experienced craft employees have gained their technical expertise over the course of many years of training and work experience.  This tenured knowledge cannot be replaced by a new employee in a short amount of time; rather sufficient time must be provided for new employees to obtain the proper training and experience so they may adequately step into their new role.

## Response

Accepted

## Action

PGW considers this type of issue to have enterprise wide impact; as a result, a comprehensive strategy is being developed to address the looming attrition issues facing PGW over the next several years.  The program is designed to address organization culture, retention, knowledge management (collection, organization, distribution, and preservation), succession planning as well as hiring.  Various programs have already been put in place and include:  succession planning for senior management, a Senior Team development program and part-time worker program, while others such as Knowledge Management (Gas Supply) and telecommuting (Information Services) are being piloted.  Still others such as flexible work schedules and the benefits mix are being evaluated.

## Individual Responsible

Jean A. Paul, Manager, Fleet Operations

## Expected Completion Date

3rd Quarter FY 2010

Recommendation # III-11

Use information collected from outside contractors to make decisions on which FO activities can best be performed by outside contractors and what areas of FO need to be improved to be comparable with outside contractors. (Refer to Finding III-15)

Audit Noted: In Schumaker & Company’s experience, over the last several years, utilities have begun to seriously consider alternatives to a totally in-sourced fleet operations.  Some utilities have totally outsourced fleet maintenance, others have outsourced various types of repairs – such as passenger car repairs while still doing major repairs in-house, and others have out-source parts supply and inventory.  In each case, the decision made on what activities can be outsourced more effectively was based on the particular circumstances of the particular utility.  The plan to issue a request for proposal (RFP) for a contractor to perform a portion of the vehicle maintenance and repair work would begin to provide FO personnel with the information necessary to determine the best way to perform various types of FO activities.  Furthermore, in that FO is facing a natural attrition due to retirements, it would be a good time to make some decisions on potential outsourcing of various activities.

## Response

Accepted

## Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

Jean A. Paul, Manager, Fleet Operations

## Expected Completion Date

2nd Quarter FY 2010

Recommendation # III-12

Initiate a concerted effort to automate the production of the monthly PM schedule, thereby resulting in manpower time savings.  (Refer to Finding III-16).

Audit Noted: The fleet management application is in place and the relevant data is being collected.  The problem appears to be that there needs to be some additional programming done to bring the two together.  PGW management should place an emphasis on getting these programming changes made due to the large monthly payback that would result.  This programming could be done on either an internal or an external basis, depending on the availability of resources.

## Response

Accepted

## Action

Fleet Operations agrees with the intent of this finding and will investigate means of automating the production of the monthly Preventive Maintenance schedule, while remaining aware that so many factors and data sources contribute to the PM schedule that PGW has in the past relied on human attention and intervention to produce a reliable, working schedule that takes into account all the variables.  Variables may include other departments’ special operating needs, seasonality, emergencies, special requests, etc.

## Individual Responsible

Jean A. Paul, Manager, Fleet Operations.

## Expected Completion Date

1st Quarter FY 2010

Recommendation # III-13

Evaluate the beneficial impact that having an auto–parts-knowledgeable person in the storeroom would have on improving the process of parts identification and ordering.  (Refer to Finding III-17.)

Audit Noted: An improvement in parts identification and ordering should improve the efficiency and timeliness of the FO operations.  That is because it would reduce the amount of time that is spent waiting for parts and dealing with parts that were ordered in error.  This efficiency would, in turn, result in a better overall FO operation, better customer service, and a commensurate improvement in some of the metrics that are monitored.

## Response

Accepted

## Action

Evaluation will be performed in cooperation with the Materials Management Department by 8/31/09.

## Individual Responsible

Jean A. Paul, Manager, Fleet Operations

## Expected Completion Date

4th Quarter FY 2009

Recommendation # III-14

Develop specific programs that are intended to improve the levels of cooperation and communication between the FO Department and the various field operating groups.  (Refer to Finding III-18.)

Audit Noted: Interviews with FO staff revealed that there are varying levels of cooperation among the various operating groups.  Some are very cooperative while others less so.  PGW management needs to put a strong emphasis on this cooperation to make it clear to all the various groups and employees that it is required of them in order to foster a more efficient overall operation.  Additionally, a review should be done of the communications methods and tools that are in place for interdepartmental communication to determine if any of the current processes could be improved.

## Response

Accepted

## Action

Fleet meets with Field Operations bi-weekly to discuss issues and processes that affect both Operations.  Fleet will initiate similar meetings with Gas Processing, Customer Affairs, Marketing and Materials Management in order to develop better communication flow between the departments.

## Individual Responsible

Jean A. Paul, Manager, Fleet Operations

## Expected Completion Date

2nd Quarter FY 2010

## Recommendation # III-15

Initiate an evaluation of the operations of the Facilities Department to identify procedures and processes that could be improved.

## Response

Accepted

## Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program which is expected to commence in late spring or early summer 2009.   The specific elements of the program are currently be developed and will be made available in March of 2009, should this recommendation not be part of that program PGW will provide an alternative strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

R.S.Rajan Director, Engineering and Facilities

## Expected Completion Date

4th Quarter FY 2009 (subject to BT input)

## Recommendation # III-16

Initiate an internal audit of the Facilities Department.

## Response

Accepted

## Action

Internal Audit Department will be contacted to schedule an Audit of the Facilities Department

## Individual Responsible

R.S.Rajan Director, Engineering and Facilities

## Expected Completion Date

4th Quarter FY 2009

## Recommendation # III-17

Initiate a formal material-demand-requirements forecasting program in the Procurement Department.  (Refer to Finding III-21.)

Audit Noted: The PGW Procurement Department should begin to improve its forecasting by working in conjunction with the operating departments and their planned work for the future. In this way, forecasts could be made that would reflect the actual work that is to be done rather than the work that has been done in the past.  Such enhanced forecasting would result in an improved ability to provide the required procurement services in an effective, efficient, and timely manner.

## Response

Accepted

## Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

Kenneth Williams, Director Procurement & MBE

## Expected Completion Date

4th Quarter FY 2010

## Recommendation # III-18

Change the focus of the Procurement Department from being primarily an administrative group to being a proactive procurement organization that is actively involved in all aspects of the purchasing process.  (Refer to Finding III-22.)

Audit Noted: The first step in this effort is to eliminate much of the paper that is now being generated and handled as part of the procurement process.  This paper-based procurement process requires large amounts of time that would be better spent on other more important procurement tasks, such as vendor partnering, identifying new potential vendors, price negotiations, etc.  It is through activities such as these that the PGW Procurement Department can institute improvement in the overall procurement process and provide better service to its clients.

## Response

Accepted

## Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

Kenneth Williams, Director Procurement & MBE

## Expected Completion Date

2nd Quarter FY 2011

## Recommendation # III-19

Develop a program to perform regular surveys of the operating department clients of the PGW Procurement Department concerning the performance of the largest vendors and any other vendors with which problems have been experienced in the past.  (Refer to Finding III-23.)

Audit Noted: A simple form of vendor performance surveying should be done in accordance with an established schedule.   This regularity would permit the collection of the required information in an efficient and timely manner.  This information could then be reviewed to identify potential problems with vendors or other areas where the Procurement Department could work with the vendors to improve their performance in the eyes of the PGW clients.  This review process would also allow for the development of vendor performance ratings, which should be of great use to the Procurement Department buyers.

## Response

Accepted

## Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

Kenneth Williams, Director Procurement & MBE

## Expected Completion Date

4th Quarter FY 2010

## Recommendation # III-20

Rotate the buyers across the vendors on a regularly scheduled basis, for both security and cross-training reasons.  (Refer to Finding III-24.)

Audit Noted: As stated previously, such a regularly scheduled rotation of buyers prevents situations of excessive familiarity with vendors on the part of the buyers.  It also identifies any situations where this familiarity may have been a problem in the past.  Additionally, a regular rotation provides necessary cross-training for the buyers so that situations of vacation, illness, or personnel changes can be responded to in a proactive manner thanks to the increased flexibility of the buyer staff.

## Response

Accepted in Part

## Action

Procurement agrees with this concept, while remaining aware that implementation will depend on a large extent on whether Phase 2 of the Business Transformation initiatives includes augmentation of Procurement’s staffing level.  At present, we have only 5 buyers and depend on their expertise in purchasing within specific product categories to function efficiently.  Increasing staff size was a feature of the original BT plan for transformation of the procurement organization and once that takes place, Procurement will implement this recommendation.

## Individual Responsible

Kenneth Williams, Director Procurement and MBE

## Expected Completion Date

4th Quarter FY 2010

Recommendation # III-21

Develop a program to collect and use metrics that are related to individual buyer performance.  (Refer to Finding III-25.)

Audit Noted: Such buyer performance metrics would provide Procurement Department management with a viable tool to assist them in the job performance evaluation process.  These metrics would also provide feedback to the individual buyers as to how they are doing in terms of job performance.  Additionally, they would serve as a tool in the training of new buyers as they would provide an indicator of those new buyers’ progress as well as equip them with a set of standardized performance metrics against which they know that their performance would be measured.

## Response

Accepted

## Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

Kenneth Williams, Director Procurement & MBE

## Expected Completion Date

2nd Quarter FY 2010

Recommendation # III-22

Develop a program to collect metrics related to the savings or contributions to PGW’s profitability that are achieved through the work of the Procurement Department.  (Refer to Finding III-26.)

Audit Noted: Such metrics would provide a clear demonstration to PGW management of the Procurement Department’s contribution to the performance of the overall company.  This insight would serve to bring greater credibility to the Procurement Department in that PGW could quantify the staff’s contribution, which can be sometimes overlooked.  Such purchasing group achievement metrics could also be used by the department’s management and the Supply Chain organization to judge, in a quantitative manner, the current performance of the Procurement Department relative to past periods.  They could also be leveraged to establish empirical goals and objectives for the group to strive toward.

## Response

Accepted

## Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

Kenneth Williams, Director Procurement & MBE

## Expected Completion Date

3rd Quarter FY 2010

Recommendation # III-23

Explore the available options for creating a purchasing consortium arrangement with the City of Philadelphia Procurement Department.  (Refer to Finding III-27.)

Audit Noted: Because volume purchasing is one of the keys to controlling purchased material costs, it would seem logical to investigate the opportunities that are available for developing joint purchasing agreements with the City on those items and on materials that are purchased by both groups.  Because both entities are part of the overall City of Philadelphia organization, such arrangements may be very feasible from an organizational perspective.

## Response

Accepted

## Action

## We have made preliminary contact with the City of Philadelphia Procurement Commissioner’s Office and are currently attempting to schedule a meeting to begin discussion of this concept, as well as working toward identifying areas where such an arrangement could have the greatest impact for PGW.  We will continue to explore this in cooperation with the City’s procurement office.

## Individual Responsible

Kenneth Williams, Director Procurement and MBE

## Expected Completion Date

4th Quarter FY 2010

Recommendation # III-24

Evaluate the additional functionality that is not being used in the Oracle procurement application and develop a formal plan and schedule for taking advantage of those features, one that would have the most beneficial impact on the operations of the Procurement Department.  (Refer to Finding III-28.)

Audit Noted: There are a number of capabilities in the existing Oracle procurement module that are not being used and which have been replaced with paper-based processes.  This underutilization is inefficient from both an operational and an economic perspective.  The basis of this study would be a determination of which of Oracle’s features would be expected to bring the largest and most immediate benefit to the operations of the Procurement Department.  There would certainly be costs associated with the implementation effort and the required training, but the long-term benefits that would be derived would almost certainly be greater.

## Response

Accepted

## Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

Kenneth Williams, Director Procurement & MBE

## Expected Completion Date

3rd Quarter FY 2010

Recommendation # III-25

Identify operations and functions that could be better integrated between the Procurement Department and the Materials Management Department.  (Refer to Finding III-29.)

Audit Noted: The Procurement Department and the Materials Management Department are partners in the work that is focused on providing the PGW operating groups with the materials they need, when they need them, and where they need them.  Therefore, a seamless integration between these two key groups can only lead to improved operational efficiency and, as a result, better service provision to their client groups.

## Response

Accepted

## Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

Although BT will provide the centralized umbrella for Supply Chain transformation, there are basic processes such as consolidation of procuring certain materials, i.e., valves and general materials that can be implemented before the larger BT project gets underway.  We plan to move ahead with those.

## Individual Responsible

Kenneth Williams, Director Procurement & MBE

## Expected Completion Date

3rd Quarter FY 2010

Recommendation # III-26

Evaluate the electronic commerce capabilities that are available through the Oracle e-procurement application and determine if these capabilities would be cost effective to implement.  (Refer to Finding III-30.)

Audit Noted: Moving to a full e-procurement mode of operation will require the purchase and implementation of an additional Oracle module.  While there are certainly significant costs associated with this implementation, most firms have found that the ongoing operational and economic benefits outweigh the initial costs.  Procurement Department management and staff need to review the associated costs and benefits that would accrue from such an implementation and determine if such an effort would be operationally and economically beneficial to both the department and its clients.

## Response

Accepted

## Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

Kenneth Williams, Director Procurement & MBE

## Expected Completion Date

2nd Quarter FY 2010

Recommendation # III-27

Evaluate the purchasing authorization levels that are currently in place and identify potential areas that could be streamlined.  (Refer to Finding III-31.)

Audit Noted: Such a reduction in the levels of authorization would serve to expedite and simplify the overall procurement process for both the Procurement Department staff and its clients throughout PGW while still retaining control over dollars expenditures.

## Response

Accepted

## Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

Kenneth Williams, Director Procurement & MBE

## Expected Completion Date

3rd Quarter FY 2010

Recommendation # III-28

Explore the advantages that increased partnering with vendors and designation of strategic suppliers would bring to the procurement process at PGW.  (Refer to Finding III-32.)

Audit Noted: If the evaluation does show that such a new strategic sourcing strategy would be beneficial, the next step would be to identify specific vendors with which to begin the program.  Using these vendors as a pilot program would provide an empirical means of testing the potential benefits of this new strategy.

## Response

Accepted

## Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

Kenneth Williams, Director Procurement & MBE

## Expected Completion Date

3rd Quarter FY 2010

## Recommendation # III-29

Increase the amount at which a sealed bid is required from the current $10,000 threshold to a more realistic level of $25,000 or more. (Refer to Finding III-33.)

Audit Noted: As discussed previously in this report, the $10,000 limitation has been in place at PGW for some time.  Raising the limitation to a number that is more reasonable in terms of the current economy and pricing structures would save a significant amount of unnecessary paperwork and effort on the part of the Procurement Department.  This decrease in required effort, in turn, should raise the level of performance and produce financial savings.

## Response

Accepted in Part

## Action

While we agree with this Finding and with the intent of the recommendation, we remain aware that the $10,000 sealed bid limitation is written into PGW’s Management Agreement with the City of Philadelphia, which dates back to 1972.  To amend it is beyond the scope of the Procurement Department and would require an effort by other PGW divisions, including the executive and legal organizations.  We will make the request to increase the sealed bid limitation although the outcome will be out of our hands due to the governance agencies involved in any such decision.

## Individual Responsible

## Kenneth Williams, Director Procurement & MBE

## Expected Completion Date

2nd Quarter FY 2010 – Initiation Time Frame

Recommendation # III-30

Initiate increased efforts to reduce the level of inventory in the MMD storerooms.  (Refer to Finding III-14.)

Audit Noted: Inventory targets have been established for each of the MMD storerooms for 2008, which is a very good first step.  But concrete strategies now have to be established to ensure the achievement of these goals in the designated timeframe.  Numerous means to achieve inventory reductions have been discussed in this report and they should provide a good basis for action.  However, other methods of inventory reduction should be solicited from the MMD staff and managers as they have the highest level of knowledge of the daily operations.  Additionally, an inventory reduction results-monitoring program should be put into place (if one does not exist already) to ensure that the ongoing progress of the initiative is known to all involved with it.

As discussed Finding III-14. PGW would be able to reduce its inventory valuation by approximately $2 million, a one-time savings.  Assuming 25% inventory carrying charges (which is the general industry standard), PGW would also be able to reduce its annual costs by approximately $500,000 (25% x $2,000,000).

## Response:

## Accepted

## Action

MMD has improved the process of identifying obsolete materials.  Inventory meetings are conducted with the operating departments to identify non-moving items.  When items are identified as obsolete, the approval is agreed upon and the items are removed from inventory each month.   This process will continue as follows:

| Warehouse | Department | Material Composition | Inventory Reduction |
| --- | --- | --- | --- |
| Tioga | Distribution | Pipes, Valves, Fittings | $ 75,000 |
| Montgomery | General Materials | General Materials | $ 50,000 |
| Richmond | Gas Processing | LNG Facility | $ 50,000 |
| Passyunk | Gas Processing | LNG Facility | $150,000 |
| Fleet | Fleet Operations | Auto Equipment | $ 50,000 |
| Total |  |  | $ 375,000 |

## Individual Responsible

Gearasir Jackson, Manager, Materials Management Department

## Expected Completion Date

4th Quarter FY 2010

Recommendation # III-31

Initiate efforts to reduce the number of employees in the MMD.  (Refer to Finding III-35.)

Audit Noted: Employee reductions should be the natural result of some of the other initiatives discussed in this report, such as inventory reduction, warehouse consolidation, and increased use of available Oracle capabilities.  However, as in any such employee-reduction program, it is critical that the work goes away before the number of employees is reduced.  Additionally, employee reductions should be well thought-out in advance to avoid deleterious effects on the operations or the included employees.

As discussed in Finding III-35, a reduction of eight in MMD staff is a feasible target.  Based on a conservative estimate of a total annual cost of $50,000 per employee, if this eight employee reduction were achieved it can be estimated that it would result in an annual savings to PGW of approximately $400,000 (8 x $50,000).

## Response

Accepted

## Action

Upon consolidation of the warehouses and continued reduction of inventory, MMD will be able to reduce the headcount of employees.  The consolidation will not be effective until 2010.

PGW considers this type of issue to have enterprise wide impact; as a result a comprehensive strategy is being developed to address the looming attrition issues facing PGW over the next several years.  The program is designed to address organization culture, retention, knowledge management (collection, organization, distribution, and preservation), succession planning as well as hiring. Various programs have already been put in place and include; succession planning for senior management, a Senior Team development program and part-time worker program while others such as Knowledge Management (Gas Supply) and telecommuting (Information Services) are being piloted. Still others such as flexible work schedules and the benefits mix are being evaluated.

## Individual Responsible

Gearasir Jackson, Manager Materials Management Department

## Expected Completion Date

4th Quarter FY 2012

Recommendation # III-32

Initiate a focused effort to increase the level of inventory turnover in the MMD storerooms and in aggregate.  (Refer to Finding III-36.)

Audit Noted: Again, this effort would go hand in hand with the other initiatives discussed in this report, such as reduced levels of inventory, consolidation of storerooms, and improved utilization and application of the spare parts designation.  Making operational gains in any of those areas should have a positive effect on the level of inventory turns that are produced.

## Response

## Accepted

## Action

MMD has reduced order quantities and will continue to remove obsolete items as well as investigate additional vendors for inventory stocking programs.  Upon consolidation of warehouses the identical items will be categorized under one material code number instead of multiple material code numbers.  In order to reduce inventory and increase turns, Materials Management will take the following actions:

- Identify fast from slow moving inventory.  On slow moving inventory, identify obsolete items, long-lead items, and emergency repairs items.

- Remove obsolete items from inventory and sell for scrap

- Review quantities levels and usage of slow moving items.  Right size based on usage, lead-time, and seasonal periods.

- Investigate further vendor stocking options

- Increase turn to 3.0.

Once consolidation occurs as part of the BT initiative, remove redundant items from stock. This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

Gearasir Jackson, Manager, Materials Management Department

## Expected Completion Date

2nd Quarter FY 2011

Recommendation # III-33

Perform an analysis to determine the best way to utilize the spare parts classification and take the necessary steps to ensure that it is applied evenly across the storerooms.  (Refer to Finding III-37.)

Audit Noted: As stated previously in this report, most utilities have a standardized empirical definition of spare parts and apply this definition equally to all parts of their inventory.  These spare parts are then excluded from the turn’s calculations because their critical nature renders them uncontrollable by the inventory managers.  Only the general inventory should be used for the turn’s calculation.  That is because the spare parts are generally expensive parts that do not move frequently but must be kept in stock in the event that equipment repairs are needed.

## Response

Accepted

## Action

The department is reviewing the items that are turning in the spare parts category and will establish a method to classify them as general inventory as well as the items that are in the general inventory that are required for an emergency will be re-classified as spare parts.  A spare parts, general inventory, and emergency stock policy will be established, across warehouses, depending on movement, usage, and lead-time. Current spare items are identified as well as general inventory and emergency stock in Oracle.  Historical data will be reviewed in each warehouse and re-classified in the appropriate categories.

## Individual Responsible

Gearasir Jackson, Manager, Materials Management Department

## Expected Completion Date

2nd Quarter FY 2010

Recommendation # III-34

Develop formal procedures to guide and govern the day-to-day operations of the MMD storerooms.  (Refer to Finding III-38.)

Audit Noted: Oracle-related inventory procedures already exist at PGW.  These processes could easily serve as the basis for the development of a fully functional set of day-to-day operational procedures for the MMD operations.

## Response

Accepted

## Action

Oracle procedures exist; procedure manuals are being developed for each area and will be distributed.

## Individual Responsible

Gearasir Jackson, Manager, Materials Management Department

## Expected Completion Date

3rd Quarter FY 2010

Recommendation # III-35

Conduct an evaluation to determine whether the Material Delivery function is cost effective when provided on an in-house basis or if the service could be provided as well and more cost effectively by an external contractor.  (Refer to Finding III-39.)

Audit Noted: Such a study would be a standard cost/benefit analysis to determine which course of action would serve the MMD and PGW in general the best.  It is important to make sure that all of the various advantages and disadvantages of each of the modes of operation are included and thoroughly considered.

## Response

Accepted

## Action

An assessment will be performed to determine if the Material Delivery function is cost effective.  An economic analysis will be performed to determine if a third party performing these functions would be more cost effective.

## Individual Responsible

Gearasir Jackson, Manager, Materials Management Department

## Expected Completion Date

2nd Quarter FY 2010

Recommendation # III-36

Conduct an evaluation to identify if there are potential advantages to be gained by transferring the gasoline and diesel fuel provision function to a private contractor.  (Refer to Finding III-40).

Audit Noted: This assessment entails another straightforward cost/benefit analysis, but weight should be given to the operational advantages of having someone else deal with the day-to-day fuel provision function.

## Response

Accepted

## Action

An assessment will be performed to determine cost/benefit, and any advantages to PGW operational efficiencies.

## Individual Responsible

Gearasir Jackson, Manager, Materials Management Department

## Expected Completion Date

2nd Quarter FY 2010

Recommendation # III-37

Conduct an analysis to determine if it would be cost and operationally effective to outsource the vehicle parts procurement and inventory function.  (Refer to Finding III-41.)

Audit Noted: As stated previously in this report, outsourcing of this function could potentially serve two purposes: saving money and putting personnel who are more knowledgeable of vehicle parts into the Fleet Operations storeroom. Again, firms that specialize in the provision of vehicle parts procurement and inventory bring specialized expertise and economies of scale.  That is because such operations are within their core competencies.  A local example of where such an outsourcing effort has been successful is at Philadelphia Energy Company (PECO).

## Response

Accepted

## Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

Gearasir Jackson, Manager, Materials Management Department

## Expected Completion Date

3rd Quarter FY 2010

Recommendation # III-38

Initiate efforts to increase the usage of vendor stocking arrangements.  (Refer to Finding III-42.)

Audit Noted: This effort should not be focused solely on initiating vendor stocking agreements.  Rather, it should also attempt, in conjunction with the Procurement Department, to identify the opportunities that exist for the creation of a more wide-ranging strategic sourcing program.  However, it is likely that the vendor stocking aspect is the one that would pay the largest returns to PGW in a relatively short timeframe.

## Response

Accepted

## Action

MMD is currently working with Procurement on bundling items and will converse to determine what other opportunities are available.

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

Gearasir Jackson, Manager, Materials Management Department

## Expected Completion Date

3rd Quarter FY 2010

Recommendation # III-39

Develop a high-level cross-training program that would provide MMD supervisors with increased training in the requirements and preferences of the field operations groups that are their clients.  (Refer to Finding III-43.)

Audit Noted: This cross-training program does not need to be intensive or extremely time-consuming to produce the desired effect.  Rather, it should provide more in the way of exposure to the daily workings of the operational groups so that their requirements can be better understood.  A frequent result of such a program is an improvement in communication between the materials management groups and the operating groups, which can serve to significantly improve coordination.

## Response

Accepted

## Action

A training program will be developed and scheduled with the Field Operations, Gas Processing, and Fleet Departments.

## Individual Responsible

Gearasir Jackson, Manager, Materials Management Department

## Expected Completion Date

4th Quarter FY 2010

Recommendation # III-40

Review the operational advantages to be gained from the implementation of a bar-coding program in the MMD storerooms.  (Refer to Finding III-44.)

Audit Noted: This assessment entails a fairly standardized analysis that would look at the costs and the benefits and then determine if bar-coding would be worthwhile from both operational and economical standpoints.  Most of the materials management organizations that have performed similar studies have found that bar-coding did bring substantial benefits to their operations.

## Response

Accepted

## Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

Gearasir Jackson, Manager, Materials Management Department

## Expected Completion Date

3rd Quarter FY 2010

Recommendation # III-41

Conduct an analysis to determine the economic and operational benefits that would be gained from the consolidation of the MMD storerooms.  (Refer to Finding III-45.)

Audit Noted: Under the current mode of operation with six storeroom facilities, a considerable amount of double-handling and wasted effort results.  Shipments are received in one storeroom and are put into storage.  Subsequently, they are required by another storeroom and have to be picked, packed, and transported again.  Then at the second warehouse, the receiving process must be undertaken again.  This assessment should include a lease versus buy analysis for the storeroom facility.  At a minimum, this evaluation should include consideration of a consolidation into one storeroom for the Montgomery and Tioga storerooms.  Such unification was done at one time in another larger facility but that facility was sold (PGW had leased it).  Subsequent to this event, PGW no longer had a facility large enough to house the combined inventory so multiple storerooms were established.

## Response

Accepted

## Action

This recommendation may be implemented as part of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  A professional evaluation of all PGW facilities is currently underway which may result in a plan for warehouse consolidation earlier than the original BT timeline.

## Individual Responsible

Gearasir Jackson, Manager, Materials Management Department

## Expected Completion Date

2nd Quarter FY 2010

Recommendation # III-42

Evaluate the unused functionality of the Oracle inventory management application and develop a formal plan and schedule for taking advantage of those features that would have the most beneficial impact on the MMD operations.  (Refer to Finding III-46.)

Audit Noted: There are a number of capabilities in the existing Oracle inventory management module that are not being used and which have been replaced with paper-based processes.  This underutilization is inefficient from both an operational and an economic perspective.  The basis of this study would be a determination of which Oracle features would be expected to bring the largest and most immediate benefit to the operations of the MMD.  There would certainly be costs associated with the implementation effort and the required training, but the long-term benefits that would be derived would almost certainly outweigh them.

## Response

Accepted

## Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program, which is expected to commence in late spring or early summer 2009.  The specific elements of the program are currently being developed and will be made available in March of 2009.  Should this recommendation not be part of that program, PGW will provide an alternate strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

## Individual Responsible

Gearasir Jackson, Manager, Materials Management Department

## Expected Completion Date

3rd Quarter FY 2010

## Recommendation # III-43

Formalize and enhance PGW’s Enterprise Risk Management (ERM) program.

## Response

Accepted

## Action

PGW has continued to follow through on its plan to improve, formalize, and finalize its Enterprise Risk Management Program.  PGW has engaged the services of experts from Marsh, PGW’s insurance broker.  Following a preliminary review of the current program, Marsh will be meeting with top management to explore the next steps.  In addition, PGW’s internal audit contractor, Grant Thornton, will be performing a basic risk assessment for audit identification purposes which will be considered as part of the Marsh evaluation.  Grant Thornton has also proposed ERM software which will also be considered, in addition to other tracking methods.  With these measures, PGW will have a high level, professional ERM program to address its myriad risks, devise proper responses, and allocate resources appropriately.

## Individual Responsible

Jane Lamb Director, Risk Management

## Expected Completion Date

4th Quarter FY 2009

## Recommendation # III-44

Conduct a formal compensation study to evaluate marketplace salaries for attorneys and paralegals.

## Response

Accepted

## Action

Legal, working with Human Resources and Organizational Development, will utilize an outside consultant to perform a formal compensation study to evaluate marketplace salaries for attorneys and paralegals.

## Individual Responsible

Abby Pozefsky, Senior Vice President and General Counsel

Raquel Guzmán, Vice President and Associate General Counsel

## Expected Completion Date

4th Quarter FY 2009

## Recommendation # IV -1

Streamline the corporate governance processes of PGW.

## Response

Reject

## Action

This recommendation is beyond the capacity of PGW Management to address and is therefore rejected.

## Individual Responsible

Thomas E. Knudsen, President and Chief Executive Officer

## Expected Completion Date

Not Applicable

## Recommendation # IV-2

Develop an ongoing Ethics training program.

## Response

Accepted

## Action

Legal will continue to offer periodic, mandatory ethics training to all exempt employees on a bi-annual basis, and will pursue offering training to represented employees.

## Individual Responsible

Howard Lebofsky, Assistant General Counsel and Ethics Officer.

## Expected Completion Date

4th Quarter FY 2009

## Recommendation # IV -3

Strengthen the Board Audit Committee function.

## Response

Accepted

## Action

PGW is currently working with the PFMC Audit committee in acting on the recommendations made by Schumaker and Company in the audit report. These items should be instituted by the February 2009 Board of Directors meeting.

## Individual Responsible

Thomas E. Knudsen, President and Chief Executive Officer

## Expected Completion Date

3rd Quarter FY 2009

## Recommendations # IV–4

Modify the IA program structure by addressing all noted deficiencies.

## Response

Accepted

## Action

PGW Internal audit has initiated a number of activities to aggressively move the Internal Audit function forward. These include:

Performing a number of internal and outsourced audits to provide the basis for assessing risk mitigation, audit planning and establishing appropriate management policies, plans, procedures, practices, and systems;

- A draft strategic plan, based on increasing in-house capability while utilizing elements of outsourcing and co-sourcing, has been prepared and is being presented to the Audit Committee for approval in February 2009;

- A new audit plan was approved and Grant Thornton selected to perform selected audits during a transition period. Their four Audit Projects will be completed in late January or no later than early February 2009;

- A new IIA Audit Manual was purchased, edited, and published in 2008 with management policies, plans, procedures, practices, and systems suggested by the IIA in compliance with the International Standards for the Professional Practice of Internal Auditing;

- IA will contract with the Grant Thornton to assist staff in the evaluation and selection of a Commercially-off-the-shelf (COTS) integrated Governance, Risk, and Controls software and complete a Risk Assessment by February 2009, to evaluate, utilizing the COSO framework:

- a common business risk language;

- the effectiveness of the PGW organizational control structure;

- Business Process controls; and

- To identify, map, and evaluate major financial, and non-financial, processes and key control points, promoting the early identification, assessment, and management of key risks;

- The Risk Assessment will be used with a three year  Audit Plan pursuant to IA’s charter and in compliance with IIA standards;

- IA will contract with Grant Thornton to help it self assess its procedures as a step in performing a Quality Assessment.  The output of the Assessment will be recommendations, aligned with the Management Audit Recommendations and IIA standards, to help IA move to best practices in management policies, plans, procedures, practices, and systems;

- IA will use the Risk Assessment and this report to support the budget, which is designed to increase staff over the five-year period, and reduce the heavy percentage of out/co-sourcing in parallel, to support its new strategic plan.

## Individual Responsible

Thurman Bullock, Director Internal Auditing

## Expected Completion Date

## 3rd Quarter FY 2009

## Recommendation # IV-5

## Expedite the pursuit of the Business Transformation project.  (Refer to Finding IV-7.)

Only a portion of the BT project has been approved to date. This management audit report identifies other findings and recommendations that could be addressed by certain aspects of the BT project. Pending the successful outcome of the already approved portion of the BT project, the remaining portion of BT should be revisited for implementation. It should also be included in the implementation plan submitted by PGW to the PaPUC in response to our management audit report.

## Response

Accepted

## Action

PGW has begun planning for the next phase of Business Transformation (BT) as ordered by the PaPUC as part of the recently approved Emergency Rate relief. PGW expects to have a proposal for the remainder of the BT Program completed in early March outlining the specifics of the program and the associated Cost/Benefit analysis. 

The current BT “Lite” Completion schedule is below:

Customer Affairs				Anticipated Production Date

Write-Off Reactivation			March 2009

Risk Based Collections			March 2009

Landlord Cooperation Program		July 2009
Lien System					January 2009

Soft-Off					April 2009

Field Operations

Resource Management			May/June 2009

Field Management				May/June 2009

Other

Real Estate Rationalization		April 2009 assessment compete

Time & Labor Management		March 2009

## Individual Responsible

Thomas L. Kuczynski, SVP Business Transformation & Information Services

## Expected Completion Date

4th Quarter FY 2010

## Recommendation # V-1

Institute flexible work rules and hours in financial management functions

## Response

Accepted

## Action

PGW on September 13, 2008 entered into a memorandum of agreement with GWEU Local 686 for the purpose of implementing formal educational requirements, performance standards, and cross-functionality of all Accounting and Reporting and Treasury union employees (See attached Agreement).  The intent of this agreement is to accomplish three main goals. First, PGW has established formal educational requirements for all new union employees hired after this agreement is executed.  It is the belief of PGW that to truly enhance the performance of the department, it is essential that all new union employees be formally trained in the principles of accounting. Secondly, from this agreement, PGW implemented performance standards.  With the implementation of these performance standards, PGW believes in conjunction with the new formal educational requirements that the work quality of the department will be improved.  Finally, PGW has implemented cross-functionality for all union-represented employees to develop and enhance their skill set by cross-training these employees in every job function within the hierarchy. The combination of the formal educational requirements, performance standards, and the implementation of cross-functionality will allow each union employee to have the skill sets to be interchangeable within their respective grade levels.  With this training and versatility, management will have the additional tools essential to increase productivity during critical time sensitive periods.

## Individual Responsible

Robert C. Haeberle, Manager Financial Reporting

## Expected Completion Date

Completed September, 2008

## Recommendation # V-2

Update the payroll system cost analysis.  (Refer to Finding V-6).

## Response

Accepted

## Action

PGW initially implemented Automatic Data Processing, Inc. (ADP) Human Resources Management System (HRMS) in April 2003 and continued automatic contract extensions through October 2008.

PGW has since contracted with ADP for another four (4) years extending through November 2012.  Provisions in the contract included no price increases for the durations of the contract.

PGW completed a Request for Proposal (RFP) process in September 2008.  Two (2) HRMS/Payroll Providers bid which included ADP and Ceridian, Inc.  Ceridian was the lower bid; however, Ceridian could not fulfill all of PGW’s requirements.  PGW has been utilizing ADP for Human Resources Management Applications and Payroll Processing since April 2003.  It was deemed more economical in the long run to stay with ADP than to incur the additional costs associated with a full software conversion.

Additionally, ADP had created Custom Programs including PGW’s Pension Calculation, which Ceridian could not satisfy and PGW would have to use a third-party vendor for the calculation (no estimate was supplied by Ceridian).  This program is already in place in the current ADP HRMS/Payroll System.

## Individual Responsible

Joseph F. Golden, Jr. - Controller

## Expected Completion Date

Completed December, 2008

Recommendation # V-3

Improve the timing of the budget preparation and approval process

Response

Accepted

Action

- Review timing of the FY 2010  budget review processes;

- Determine factors that contributed to any delay in approving the budget;

- Identify modifications to process to insure timely approval;

- Develop recommendations to insure timely approval; and

- Seek any necessary approvals to implement recommendations for FY 2011 budget process.

Individual Responsibility

Joseph R. Bogdonavage, Senior Vice President of Finance

Expected Completion Date

1st Quarter FY 2010

## Recommendations # V-4

Strengthen PGW’s Internal Audit (IA) function and enhance internal controls.

## Response

Accepted

## Action

The Action Plan and corresponding schedules detailed in Recommendation IV-4 will be applied.

## Individual Responsible

Thurman Bullock, Director Internal Auditing

## Expected Completion Date

3rd Quarter FY 2009

## Recommendation # V-5

Implement a process to ensure that the IA Director meets quarterly with the Board’s Audit Committee.

## Response

Accepted

## Action

A calendar of meetings has been prepared and given to the Audit Committee Chair incorporating quarterly meetings.  The CEO and Director will work with the Chair to ensure holding quarterly meetings

## Individual Responsible

Thurman Bullock, Director Internal Auditing

## Expected Completion Date

Complete

## Recommendation # VI-1

## Expand PGW’s diversity program beyond compliance-oriented activities.

## Response

Accepted

## Action

Look at developing overarching diversity programs to include online learning, speakers’ bureau, etc. (featured guest)

PGW continues to be a viable partner within our community.  We participate in numerous neighborhood diversity initiatives as well as hosting events for our neighbors.

An online diversity learning module has just been completed and will be launched to all employees in 2009.  We have also recognized the business need for diversity by hiring bi-lingual customer representatives.

We will continue to recognize our diverse workforce through the employee recognition initiative.

We envision a speaker bureau that will address various diversity issues and present them to our management team.

## Individual Responsible

Lorraine Webb, Vice President of Organizational Development

## Expected Completion Date

3rd Quarter FY 2010

## Recommendation # VI-2

## Begin filing comprehensive diversity reports to the PaPUC annually.

## Response

Accepted

## Action

Preparing to submit report and send report by April 1st of each year.

These reports will be filed at the appropriate times.

## Individual Responsible

Lorraine Webb, Vice President of Organizational Development

## Expected Completion Date

1st Quarter FY 2010

Recommendation # VI-3

Explore the use of spend targets in the Procurement Department’s performance objectives.  (Refer to Finding 0-8.)

## Response

Accepted

## Action

The Procurement Department currently sets an MBE participation goal in the form of an overall percentage of purchasing business handled directly by Procurement.  We will conduct an analysis to determine how specific dollar-amount spend targets would impact our ability to meet MBE goals.

## Individual Responsible

## Kenneth Williams, Director Procurement & MBE

## Expected Completion Date

2nd Quarter FY 2010

Recommendation # VII -1

Provide at least two controllers on all shifts for the Gas Control Center.

Response

Accepted

Action

PGW considers this type of issue to have enterprise wide impact; as a result, a comprehensive strategy is being developed to address the looming attrition issues facing PGW over the next several years.  The program is designed to address organization culture, retention, knowledge management (collection, organization, distribution, and preservation), succession planning as well as hiring. Various programs have already been put in place and include; succession planning for senior management, a Senior Team development program and part-time worker program while others such as Knowledge Management (Gas Supply) and telecommuting (Information Services) are being piloted. Still others such as flexible work schedules and the benefits mix are being evaluated.

In addition PGW requires two gas controller staffing on a 24/7 basis from November 15th through April 15th, and will bring in two controllers to staff the area during any non routine situations outside of this time period, i.e. high terrorist threat levels and hurricanes which threaten PGW supply.

Individual Responsible

Nicholas LaPergola Director of Gas Supply and Transportation

Expected Completion Date

2nd Quarter FY 2010

Recommendation # VII -2

Take steps to plan for the retirements that could have a major impact on the ability to staff the Gas Control Center.

Response

Accepted

Action

PGW considers this type of issue to have enterprise wide impact; as a result a comprehensive strategy is being developed to address the looming attrition issues facing PGW over the next several years.  The program is designed to address organization culture, retention, knowledge management (collection, organization, distribution, and preservation), succession planning as well as hiring. Various programs have already been put in place and include; succession planning for senior management, a Senior Team development program and part-time worker program while others such as Knowledge Management (Gas Supply) and telecommuting (Information Services) are being piloted. Still others such as flexible work schedules and the benefits mix are being evaluated.

Individual Responsible

Nicholas LaPergola Director of Gas Supply and Transportation

Expected Completion Date

2nd Quarter FY 2010

Recommendation # VII -3

Place the RFP that solicits gas commodity suppliers on the PGW electronic bulletin board.

Response

Accepted

Action

In consultation with the Legal department PGW will do an analysis of its procedure.

Individual Responsible

Nicholas LaPergola Director of Gas Supply and Transportation

Expected Completion Date

1st Quarter FY 2010

Recommendation # VII -4

Institute a program to perform vendor credit checks in order to qualify for a NASEB purchasing agreement, and to perform credit evaluations on a regular basis for existing suppliers.

Response

Accepted

Action

PGW will develop a process and procedure to implement a credit evaluation of its suppliers.

Individual Responsible

Nicholas LaPergola Director of Gas Supply and Transportation

Expected Completion Date

1st Quarter FY 2010

Recommendation # VII -5

Evaluate an all-inclusive or enterprise computer system to track the gathering of transactions so that supplier invoices, transportation invoices, and sales of excess suppliers are captured.

Response

Accepted

Action

This recommendation is being evaluated and may be part of the next phase of the Business Transformation Program which is expected to commence in late spring or early summer 2009.   The specific elements of the program are currently be developed and will be made available in March of 2009, should this recommendation not be part of that program PGW will provide an alternative strategy to address this recommendation at that time.  Specific implementation dates to address the recommendation will also be available once the details of the program have been finalized.

Individual Responsible

Nicholas LaPergola Director of Gas Supply and Transportation

Expected Completion Date

2nd Quarter FY 2010

Recommendation # VII -6

Evaluate, year-to-year as well as on a real time basis, PGW’s gas supply assets to determine, based on the LNG levels, whether programs for storage capacity can be created to add value and savings as part of the 1307(f) review.

Response

Accepted

Action

Based on PGW’s 1307F settlement for Fiscal Year 08-09, it will continue to evaluate these types of arrangements on an ongoing basis.

Individual Responsible

Nicholas LaPergola Director of Gas Supply and Transportation

Expected Completion Date

4rd Quarter FY 2009 and on going thereafter

## Recommendation # VII-7

Enhance the FSD and Distribution business processes through more computerization.

## Response

Accepted

## Action

This recommendation is addressed by the Business Transformation “Lite” Program which is currently underway.

As part of its Business Transformation Program, PGW will implement a Resource Management function within the Field Operations department that will be responsible for the development of a rolling long-term integrated plan for completing all scheduled and response-related work, while meeting the corporate-driven objectives and regulatory requirements associated with PGW field work.

In order to better enable Operations to be successful in executing the work plans, PGW intends to define, design, and implement a number of system enhancements focused on improving productivity by automating various associated processes.

Specific functions that will be evaluated will included and may not be limited to work order generation, estimating, scheduling, work order racking and assignment, and dispatching.  Once this initial requirement definition process is completed, the actual technical design, development, test, and implementation effort / cost will be estimated and a cost / benefit analysis will be completed prior to obtaining approval to move forward.

In addition to these system enhancements, PGW intends to investigate the use of global positioning software (GPS) in order to provide automated best available work assignments to dispatchers in real-time.

## Individual Responsible

Paul Mondimore, Vice President of Operations

## Expected Completion Date

The initial requirement definition process is expected to be complete by the end of the

4th Quarter FY 2009

## Recommendation # VII-8

Centralize all field force planning, scheduling, performance monitoring and analysis functions.

## Response

Accepted

## Action

This recommendation is addressed by the Business Transformation “Lite” Program which is currently underway.

As part of its Business Transformation Program, PGW will implement a Resource Management function within the Field Operations department that will be responsible for the development of a rolling long-term integrated plan for completing all scheduled and response-related work, while meeting the corporate-driven objectives and regulatory requirements associated with PGW field work.

Resource Management will define work bundling guidelines, identify work bundling opportunities, and schedule the associated jobs based on planned work volume targets and work priority for all of Field Operations.

In addition, Resource Management will provide monthly work completion reports and will be responsible for capturing all completed work volumes and associated costs in order to track relative performance against the work plan and approved budgets.

## Individual Responsible

Paul Mondimore, Vice President of Operations

## Expected Completion Date

Resource Management is expected to be functional by the beginning of the

4th Quarter FY 2009

## Recommendation # VII-9

PGW has implemented a new main replacement model that is an improvement over the previous model; however, further refinements are still possible. PGW should consider certain future enhancements to the Advantica program after gaining experience with the current implementation.

## Response

Accepted

## Action

As part of its Main Replacement Prioritization Program, PGW agrees that as we become more familiar with the implemented software and its functionality, we will consider potential enhancements to our risk and condition model.

## Individual Responsible

Paul Mondimore, Vice President of Operations

## Expected Completion Date

PGW will have sufficient knowledge of the new application to be able to consider future enhancements to the Advantica program by the beginning of the 4th Quarter FY 2010

## Recommendation # VII-10

Set more aggressive performance targets on gas leak response.  (Refer to Finding VII-22.)

## Response

Accepted

## Action

PGW places the highest urgency on leak response.  PGW will review its’ current leak response goal and set a more aggressive target.

## Individual Responsible

Paul A. Mondimore, Vice President of Field Operations

## Expected Completion Date

4th Quarter FY 2009

## Recommendation # VII – 11

## Build a stronger gas theft of service program.

## Response

Accepted

## Action

As stated in Recommendation VIII-17, PGW will review its current theft prevention program and undertake an industry study to determine Best Practices.  The analysis will include but will not be limited to internal systems, external vendors/systems and other gas utilities.  Enhancements to existing policies and procedures will be implemented as necessary.

## Individual Responsible

## Cristina Coltro, VP of Customer Service

## Expected Completion Date

1st Quarter FY 2010

## Recommendation # VII-12

Reassess PGW’s future field operation staffing levels based on its needs taking into consideration pending retirements.

## Response

Accepted

## Action

Operations monitors on a monthly timeframe, current staffing levels and departmental future requirements.  In conjunction with the Organizational Department within Human Resources, Operations coordinates departmental and organizational employee requirements.

PGW considers this type of issue to have enterprise wide impact; as a result a comprehensive strategy is being developed to address the looming attrition issues facing PGW over the next several years.  The program is designed to address organization culture, retention, knowledge management (collection, organization, distribution, and preservation), succession planning as well as hiring. Various programs have already been put in place and include; succession planning for senior management, a Senior Team development program and part-time worker program while others such as Knowledge Management (Gas Supply) and telecommuting (Information Services) are being piloted. Still others such as flexible work schedules and the benefits mix are being evaluated.

## Individual Responsible

Paul A. Mondimore, Vice President of Field Operations

## Expected Completion Date

Ongoing

Recommendation # VIII-1

Investigate the possibility of streamlining some of the paper work in PGW’s Universal Services Programs through some type of computerization or electronic document management program.

If you look at the number of different programs PGW deals with in assisting its customer base, a significant amount of “paper” is dealt with.  Many of these programs have been developed by different agencies and have their own paper forms and procedures that are unique to the specific program.

CAP

Senior Citizen Discount

Special Grants Program

Pennsylvania Governor’s Office Grant Program

LIHEAP

Fuel Fund

## Response

Accepted in Part

Accepted with regard to the CAP and Senior Citizen discount programs. Reject to the extent that it relates to the four last items stated on the list above, as these refer to programs developed by an agency other than PGW.  Paper forms associated with these programs are required by those agencies responsible for administering those programs.

## Action

PGW will look into ways of reducing paperwork associated with the CAP and Senior Citizen Discount Programs to the extent that we find cost-effective ways to mitigate the excess while conforming to legal requirements.

## Individual Responsible

Elsa Leung, Director of Regulatory Compliance

## Expected Completion Date

1st Quarter FY 2010

## Recommendation # VIII-2

Hire part-time CSRs and implement variable staffing levels based on predicted call volume.

## Response

Accepted

## Action

PGW has retained a consulting firm to conduct an assessment of the Call Center operations. This assessment is expected to be finalized in the spring of 2009. PGW will review recommendation for short and long term solutions.

## Individual Responsible

Cristina Coltro, Vice President, Customer Affairs

## Expected Completion Date

3rd Quarter FY 2009

Recommendation # VIII-3:

Investigate methods to improve CSR selection and retention.

## Response

Accepted

## Action

PGW will develop strategies for improving selection and retention of Customer Service Representatives by:

- Defining desired employee profile. (experience, education)

- Determining market and venues for job recruitment.

- Evaluating training for new hires.

## Individual Responsible

Cristina Coltro, Vice President, Customer Affairs

## Expected Completion Date

1st Quarter FY 2010

## Recommendation # VIII-4

## Include CSR turnover as a key performance indicator (KPI) for the call center.

## Response

Accepted

## Action

PGW will develop and maintain reports on turn over rates in order to better manage workforce and operations.

## Individual Responsible

Cristina Coltro, Vice President, Customer Affairs

## Expected Completion Date

## 3rd Quarter FY 2009

## Recommendation # VIII-5

## Redesign the call center supervisor jobs to focus more on coaching and development.

## Response

Accepted

## Action

PGW will develop strategies for revamping supervisors’ jobs to focus on coaching and development by:

- Redefining supervisor role to provide coaching and development 70 – 75 % of their time.

- Identifying key metrics to provide specific targets for coaching

- Establishing supervisor skill development training

## Individual Responsible

Cristina Coltro, Vice President, Customer Affairs

## Expected Completion Date

1st Quarter FY 2010

## Recommendation # VIII-6

## Develop a method for measuring actual call center turnover rates.

## Response

Accepted

## Action

PGW will develop and maintain reports on turn over rates in order to better manage workforce and operations.

- Create a metric to evaluate attrition rates at various stages.

- Begin tracking attrition by reason, i.e. retirement, promotion, attendance, etc.

## Individual Responsible

Cristina Coltro, Vice President, Customer Affairs

## Expected Completion Date

3rd Quarter FY 2009

## Recommendation Number # VIII-7

## Assess the root causes of absenteeism and address the quality of work/life issues in the call center in conjunction with the enforcement of absence policies.

## Response

Accepted

## Action

PGW’s Customer Affairs department will work with Human Resources and Organizational Development to develop a root cause analysis of absenteeism. The plan includes:

- Analysis on the impact of FMLA and EUC.

- Adherence to the new Lateness Policy.

- Assessment of the hiring criteria of HRD/OD, and its impact or contribution to the overall attendance, as referenced in Recommendation Number - 3.

- Encourage HRD/OD to develop a customized survey to assess the Call Center employees’ attitudes and concerns that may have a negative effect on overall attendance.

## Individual Responsible

Cristina Coltro, Vice President, Customer Affairs

## Expected Completion Date

1st Quarter FY 2010

## Recommendation # VIII -8

## Implement an annual comprehensive customer satisfaction analysis and develop an improvement strategy based on the results.  (Refer to Finding VIII-3, Finding VIII-4, and Finding VIII-7.)

## Response

Accepted

## Action

PGW has contracted with an independent agency to develop and conduct customer surveys, and provide an analysis of results. PGW will evaluate results and derive strategies for improvements.  The surveys are conducted year-round while the analysis is completed once each year.

## Individual Responsible

Cristina Coltro; V.P. Customer Affairs

## Expected Completion Date

1st Quarter FY 2010

## Recommendation # VIII-9

## Address customer dissatisfaction/satisfaction drivers.  (Refer to Finding VIII-4).

## Response

Accepted

## Action

PGW has contracted with an independent agency to develop and conduct customer surveys, and provide an analysis of results. PGW will evaluate results and derive strategies for improvements.  The surveys are conducted year-round while the analysis is completed once each year.

## Individual Responsible

Cristina Coltro; V.P. Customer Affairs

## Expected Completion Date

1st Quarter FY 2010

## Recommendation # VIII-10

Make changes to the configuration of the various customer service district offices. (Refer to Finding VIII-9.)

## Response

Accepted

## Action

PGW has embarked on a Real Estate Rationalization Utilization Plan Project (RUP) which began December 2008 and will be completed by March 31, 2009.  The goal of the project is to develop a comprehensive Real Estate Rationalization strategy to effectively utilize PGW’s Real Estate assets and to consolidate operations, with the goal of reducing operating costs and improving the company’s financial position. The recommendations suggested in the RUP project will form the basis for PGW’s strategy for configuration of district offices.

## Individual Responsible

Steve Jordon, Director Labor, Administration, and Accounts Management

## Expected Completion Date

Project recommendations will be completed by 2nd Quarter FY2009.  Actual implementation will depend on the scope of the recommendations and approvals by the Philadelphia Gas Commission.

## Recommendation # VIII - 11

## Make modest renovations to customer service district offices.  (Refer to Finding VIII-10)

## Response

Accepted

## Action

PGW has embarked on a Real Estate Rationalization Utilization Plan Project (RUP) which began December 2008 and will be completed by March 31, 2009.  The goal of the project is to develop a comprehensive Real Estate Rationalization strategy to effectively utilize PGW’s Real Estate assets and to consolidate operations, with the goal of reducing operating costs and improving the company’s financial position. Once this is complete renovations will be made accordingly.

## Individual Responsible

Steve Jordon, Director Labor, Administration, and Accounts Management

## Expected Completion Date

Project recommendations will be completed by 2nd Quarter FY 2009.  Modifications will be based on the scope of the recommendations and PGW’s financial position.

## Recommendation # VIII - 12

## Provide privacy for LIHEAP applicants.  (Refer to Finding VIII-11)

## Response

Accepted

## Action

PGW took steps to establish a separate waiting area for customers awaiting service for LIHEAP application.  While waiting, customer will be asked to complete LIHEAP applications as much as possible on their own. This minimizes loud presentment of information. Once seen by the customer service representative, the representative ensures the application is completed properly and makes copies of the information.  The designated LIHEAP customer service representatives work area has been moved further away from the LIHEAP customer waiting area.

## Individual Responsible

Steve Jordon, Director Labor, Administration, and Accounts Management

## Expected Completion Date

Implemented this current LIHEAP Season December 2008

# Recommendation # VIII-13

# Demonstrate, periodically, to the PaPUC that the Parts and Labor Program is self supporting.

Noted in Audit - As previously mentioned, many state regulatory commissions consider such programs a competitive service that should be funded totally by the customers that use the program.  Another way of stating that sentence is that the ratepayers who are not using that program should not be providing any funding to that program – what many refer to as cross subsidization.  A study needs to be performed periodically to ensure that this is the case.

## Response

Accepted

## Action

PGW has and will continue to determine the profitability of the Parts and Labor Program. A cost benefit analysis is performed after each fiscal year using Generally Accepted Accounting Principles – (GAAP) guidelines.

## Individual Responsible

Joseph Smith, Vice President of Marketing

Cristina Coltro, Vice President of Customer Affairs

Paul Mondimore, Vice President of Field Operations

Joseph Bogdonavage, Senior Vice President of Finance

## Expected Completion Date

4th Quarter FY 2009

Recommendation # VIII-14

Work with PFMC and the PGC to develop a plan for addressing the major issues facing the City of Philadelphia regarding PGW.  (Refer to Finding VIII-15.)

## Response

Rejected to the extent the recommendation affects governance over which PGW has no control. Accepted with regard to Finding VIII-15.

## Action

PGW will continue its investigation and analysis of universal services programs around the country including funding mechanisms. The plan is to develop scenarios for program design and mechanisms for sharing the burden in a fair and equitable manner. PGW will also look at potential funding mechanisms through the use of its own assets. PGW will work with parties that have jurisdiction and/or the ability to assist in creating a solution to the problem.

## Individual Responsible

Steven Hershey, V.P. Regulatory and External Affairs

## Expected Completion Date

2nd Quarter FY 2010

## Recommendation # VIII-15

Report the number of credit balance customers and credit balances that were initiated in any given year, and then annually report the reduction in those numbers and balances on the next five years (prior to being turned over to the Pennsylvania Department of Treasury).  This type of information could be used to measure the performance in providing customer refunds on a timely basis.

## Response

Accepted

## Action

PGW will develop a report that lists all accounts that will contain the date when the credit balance occurred with the amount as well as the refund date and refund amount. This information will be maintained on a historical basis.

## Individual Responsible

Steve Jordon, Director Labor, Administration, and Accounts Management

## Expected Completion Date

3rd Quarter FY 2009

Recommendation # VIII-16

Reevaluate the use of the soft-off program at PGW.

## Response

Accepted

## Action

As part of its Business Transformation Program, PGW will implement an automated soft off selection and monitoring process as well as a landlord cooperation program.  The automated soft off process will systematically dictate whether a customer requested shut-off should result in scheduling a physical shut-off order or placement of the gas service account into PGW’s name and then monitoring the account for excess usage.  The landlord cooperation program is an incentive based program that will increase PGW’s access to premises containing multiple meters connected to a single service.  These custom solutions will be integrated with existing PGW systems and business processes in order to manage customer and property information accurately and to manage all field work including physical notification, shut-off, and turn-on activities.  The system solutions will be user configurable, allowing PGW to define specific monitoring and notification time periods, usage thresholds, and daily work volume.  As a result of these initiatives and the system automation that they will provide, PGW will be able to minimize the extra costs that exceed the expected soft off consumption / cost by physically notifying and shutting off properties where the accumulated usage has exceeded a PGW defined threshold in a timely manner.

## Individual Responsible

Cristina Coltro, Vice President of Customer Affairs

## Expected Completion Date

1st Quarter FY 2010

## Recommendation VIII – 17

## Undertake a major study to improve the gas theft prevention program.  (Finding VIII – 18.)

## Response

Accepted

## Action

PGW will review its current theft prevention program and undertake an industry study to determine Best Practices.  The analysis will include but will not be limited to internal systems, external vendors/systems and other gas utilities.  Enhancements to existing policies and procedures will be implemented as necessary.

## Individual Responsible

G. Hornbuckle, Director Credit and Collections

## Expected Completion Date

3rd Quarter FY 2010

# Appendix A: Glossary

## A.

| Item | Acronym | Description |
| --- | --- | --- |
| accounts payable | A/P |  |
| affirmative action | AA |  |
| affirmative action plan | AAP |  |
| American Gas Association | AGA |  |
| automated call director | ACD |  |
| automated clearinghouse | ACH |  |
| Automated Computer Aided Drafting | AutoCAD |  |
| Automated Data Processing | ADP |  |
| Automated Information Management System | AIMS/AIMS2 |  |
| automated meter reading | AMR |  |
| automated time management system | ATMS |  |
| automatic external defibrillator | AED |  |

## B.

| Item | Acronym | Description |
| --- | --- | --- |
| Bank of America | BOA |  |
| Billing Collection & Customer Service | BCCS |  |
| billion cubic feet | Bcf |  |
| Board of Directors | BOD |  |
| British thermal unit | BTU |  |
| Bureau of Consumer Service | BCS |  |
| Business Technology Consultant | BTC |  |
| Business Transformation | BT |  |
| business transformation | BT |  |
| Business Transformation Initiative | BTI |  |
| Item | Acronym | Description |
| Business Transformation Steering Committee | BTSC |  |
| business unit | BU |  |

## C.

| Item | Acronym | Description |
| --- | --- | --- |
| calendar year | CY |  |
| Cannot Get In | CGI |  |
| Chief Executive Officer | CEO |  |
| Chief Financial Officer | CFO |  |
| Chief Information Officer | CIO |  |
| Chief Operating Officer | COO |  |
| Cincinnati Gas & Electric Company | CG&E |  |
| code division multiple access | CDMA |  |
| commercially-off-the-shelf | COTS |  |
| compressed natural gas | CNG |  |
| continuing property records | CPR |  |
| contract management system | CMS |  |
| corrective maintenance | CM |  |
| Credit & Collections | C/C |  |
| customer assistance program | CAP |  |
| Customer Contact Center | C3 |  |
| Customer Responsibility Program | CRP |  |
| Customer Review Unit | CRU |  |
| customer service center | CSC |  |
| customer service representative | CSR |  |

## D.

| Item | Acronym | Description |
| --- | --- | --- |
| database administrator | DBA |  |
| decatherms | DTH |  |
| Delaware Department of Transportation | DelDot |  |
| Department of Transportation | DOT |  |
| disabled-owned business enterprise | DBE |  |
| Dispute Resolution Unit | DRU |  |
| Distribution Integrity Management Program | DIMP |  |

## E.

| Item | Acronym | Description |
| --- | --- | --- |
| electronic data interchange | EDI |  |
| electronic funds transfer | EFT |  |
| end of year | EOY |  |
| Energy Insurance Mutual | EIM |  |
| enterprise resource planning | ERP |  |
| enterprise risk management | ERM |  |
| Enterprise Steering Committee | ESC |  |
| equal employment opportunity | EEO |  |
| Equal Employment Opportunity Commission | EEOC |  |
| Expert Agent Selection | EAS |  |

## F.

| Item | Acronym | Description |
| --- | --- | --- |
| Federal Energy Regulatory Commission | FERC |  |
| Field Services Department | FSD |  |
| file/print | F/P |  |
| financial size category | FSC |  |
| Item | Acronym | Description |
| fiscal year | FY |  |
| Fixed Utility Services | FUS |  |
| Fleet Operations | FO |  |
| Flexible Spending Account | FSA |  |
| free-is-good | FIG |  |
| full-time equivalent | FTE |  |

## G.

| Item | Acronym | Description |
| --- | --- | --- |
| gas cost recovery | GCR |  |
| Gas Industry Standards Board | GISB |  |
| Gas Processing Department | GPD |  |
| General Counsel | GC |  |
| general ledger | G/L |  |
| geographic information system | GIS |  |

## H.

| Item | Acronym | Description |
| --- | --- | --- |
| heating, ventilation, and air conditioning | HVAC |  |
| Human Resource Information System | HRIS |  |
| Human Resources | HR |  |

## I.

| Item | Acronym | Description |
| --- | --- | --- |
| Information Services | IS |  |
| Information Systems Audit and Control Association | ISACA |  |
| Item | Acronym | Description |
| information technology | IT |  |
| instruction set architecture | ISA |  |
| integrated voice response | IVR |  |
| Internal Audit | IA |  |
| International Customer Management Institute | ICMI |  |
| International Swaps & Derivative Association | ISDA |  |

## J.

| Item | Acronym | Description |
| --- | --- | --- |

## K.

| Item | Acronym | Description |
| --- | --- | --- |
| key performance indicator | KPI |  |

## L.

| Item | Acronym | Description |
| --- | --- | --- |
| Landlord Cooperation Program | LCP |  |
| liquid natural gas | LNG |  |
| Living Disaster Recovery Planning System | LDRPS |  |
| local area network | LAN |  |
| local distribution company | LDC |  |
| long-term disability | LTD |  |
| Low Income Home Energy Assistance Program | LIHEAP |  |

## M.

| Item | Acronym | Description |
| --- | --- | --- |
| Main Replacement Prioritization | MRP |  |
| Materials Management Department | MMD |  |
| Medical Review Officer | MRO |  |
| Meter Investigation Unit | MIU |  |
| minority business enterprise | MBE |  |
| Minority Business Enterprise Council | MBEC |  |
| Minority Supplier Development Council | MSDC |  |
| minority/women business enterprise | M/WBE |  |
| thousand cubic feet | Mcf |  |

## N.

| Item | Acronym | Description |
| --- | --- | --- |
| National Association of Securities Dealers | NASD |  |
| National Association of Women Business Owners | NAWBO |  |
| Natural Gas Approved Standardized Buy/Sell Agreement | NASBY |  |
| New Jersey Department of Transportation | NJDot |  |
| New York Stock Exchange | NYSE |  |
| non-payment shutoff program | NPSO |  |
| not-to-exceed | NTE |  |

## O.

| Item | Acronym | Description |
| --- | --- | --- |
| Office of Federal Contract Compliance Program | OFCCP |  |
| operations and maintenance | O&M |  |
| Item | Acronym | Description |
| Operations Systems Support | OSS |  |
| Organizational Development | OD |  |
| overtime | OT |  |

## P.

| Item | Acronym | Description |
| --- | --- | --- |
| Parts and Labor Plan | PLP |  |
| payback period | PBP |  |
| payment arrangement | PAR |  |
| Pennsylvania Department of Transportation | PennDOT |  |
| Pennsylvania Human Relations Commission | PaHRC |  |
| Pennsylvania Public Utility Commission | PaPUC |  |
| performance improvement plan | PIP |  |
| personal computer | PC |  |
| Philadelphia Commission on Human Relations | PCHR |  |
| Philadelphia Facilities Management Corporation | PFMC |  |
| Philadelphia Gas Commission | PGC | Same acronym as purchased gas costs |
| Philadelphia Gas Works | PGW |  |
| Philadelphia Housing Authority | PHA |  |
| Philadelphia Human Rights Commission | PHRC |  |
| preventive maintenance | PM |  |
| Pricewaterhouse Coopers, LLC | PwC |  |
| project management office | PMO |  |
| Project Management Professional | PMP |  |
| Public Utility Commission | PUC |  |
| purchase order | PO |  |
| purchased gas costs | PGC | Same acronym as Philadelphia Gas Commission |
| Purchasing Management Association of Philadelphia | PMAP |  |

## Q.

| Item | Acronym | Description |
| --- | --- | --- |
| quality assurance | QA |  |
| quality-of-service isolation | QoS isolation |  |

## R.

| Item | Acronym | Description |
| --- | --- | --- |
| request for proposal | RFP |  |
| request for quote | RFQ |  |
| Return Material Authorization | RMA |  |
| Revenue Protection Unit | RPU |  |

## S.

| Item | Acronym | Description |
| --- | --- | --- |
| Sarbanes-Oxley Act | SOX |  |
| Securities and Exchange Commission | SEC |  |
| Senior Vice President | SVP |  |
| separate trading of interest and principal securities | STRIPS |  |
| service level agreement | SLA |  |
| Small Business Administration | SBA |  |
| Source of Authority | SOA |  |
| Southeastern Pennsylvania Transportation Authority | SEPTA |  |
| storage area network | SAN |  |
| Strategic Alignment Score | SAS |  |
| Strategic Focused Organization | SFO |  |
| Supervisory Control and Data Acquisition | SCADA |  |
| Item | Acronym | Description |
| Supply Chain | SC |  |

## T.

| Item | Acronym | Description |
| --- | --- | --- |
| tax-exempt commercial paper | TXCP |  |
| third-party administrator | TPA |  |
| Transcontinental Pipeline | Transco |  |

## U.

| Item | Acronym | Description |
| --- | --- | --- |
| unaccounted-for gas | UAG |  |
| Underground Facilities Database | UFD |  |
| uninterruptible power supply | UPS |  |
| United States Department of Transportation | USDOT |  |
| Utility Emergency Service Fund | UESF |  |
| Utility Workers Union of America | UWUA |  |

## V.

| Item | Acronym | Description |
| --- | --- | --- |
| Vice President | VP |  |
| virtual machine | VM |  |

## W.

| Item | Acronym | Description |
| --- | --- | --- |
| wide area network | WAN |  |
| women business enterprise | WBE |  |
| workers’ compensation | WC |  |

## Y.

| Item | Acronym | Description |
| --- | --- | --- |

## Z.

| Item | Acronym | Description |
| --- | --- | --- |
| zero balance account | ZBA |  |

# Text boxes

# Appendix A- Glossary of Terms and their Acronyms