PENNSYLVANIA PUBLIC UTILITY COMMISSION

HARRISBURG, PENNSYLVANIA  17105-3265

	Pennsylvania Public Utility Commission Prosecutory Staff
     v.

Redevelopment Authority of Luzerne County
	
	Public Meeting held March 27, 2008

	
	
	JAN-2008-OSA-0085

	
	
	

	
	
	Docket No.  C-20054555

	
	
	


MOTION OF CHAIRMAN WENDELL F. HOLLAND


Before the Commission for consideration and disposition are the Exceptions filed by the Pennsylvania Department of Transportation (PennDOT) and the Commission’s Bureau of Transportation and Safety, Prosecutory Staff (Prosecutory Staff) to the Recommended Decision (RD) of Administrative Law Judge Ember S. Jandebeur (ALJ), issued on June 4, 2007.  The Redevelopment Authority of Luzerne County (Authority) filed Reply Exceptions.

The central issue is whether the Authority has fully complied with prior Commission Orders.  The Commission ordered the removal of the rail-highway crossing (AAR 361 585 X) where State Route 2001 at Cemetery Street crosses below the grade of the tracks owned by the Redevelopment Authority of Luzerne County and operated by the Luzerne County Rail Corporation in Ashley Borough, Luzerne County. 
Our Opinion and Order entered in this proceeding on July 17, 1997 outlined the nature of the initial repairs to the bridge.  On July 31, 2002, the Authority filed a Petition for Modification specifically detailing the nature of the repairs including demolition.  Specifically, the Petition states:

9. I.
After improvements are made to the Ashley Street Bridge, the Petitioner will demolish the Cemetery Street Bridge including removal of the abutment and pier bents along the roadway and grade behind any abutment to a two to one slope.  The Petitioner agrees to maintain the Cemetery Street Bridge until demolition of same and for all bridge work agrees to be responsible for road closures, detours or traffic protection incidental to the work. (Emphasis Added).
(July 31, 2002 Petition for Modification at 4-5).

By Opinion and Order dated October 31, 2002, the Commission granted the Petition for Modification filed by the Authority.  Paragraph 9.I. from the Authority’s Petition is restated verbatim at page 6 of our Opinion and Order.  As apparent in the above quote, this language includes the Authority’s agreement to remove the abutments.

In addition, Ordering Paragraph 2 of the Opinion and Order states:

2.  That the Redevelopment Authority of Luzerne County, at its initial cost and expense, provide all material and perform all work, to complete the repairs and alterations described on Exhibits A and B to the Response to of [sic] the Pennsylvania Department of Transportation, to the railroad bridges carrying its tracks above the grade of State Highway Route 2001 at Ashley Street and St. Mary’s Street (Cemetery Street), including, but not limited to, the demolition of the railroad bridge over St. Mary’s Street (Cemetery Street).
(October 31, 2002 Opinion and Order at 9).


Exhibits A and B are letters from The Cultural, Environmental and Engineering Group, Inc. dated March 15, 2002 and April 17, 2002.  The letters define the nature of the necessary repairs to eliminate the safety issues surrounding the bridge until the demolition occurs.

Ordering paragraph 3 refers back to the language of the Opinion and Order and instructs the Authority to “complete all work required by this Opinion and Order…”

On April 21, 2005, the Prosecutory Staff filed a Complaint alleging that the authority had not complied with our orders and requested the assessment of a civil penalty.  Subsequently, on July 14, 2005, the Authority filed a Petition for Modification asking that removal of the abutments be removed from the project since they pose no safety hazard.  This Petition was consolidated with the Complaint proceeding which resulted in the Recommended Decision before us.  However, the ALJ did not consider the Petition because she determined that our prior orders did not require removal of the abutments.  I disagree with that determination. As mentioned above, the October 31, 2002 Opinion and Order directed the Authority to make necessary repairs to the bridge while it remained operational and still standing and then detailed what must be done during demolition, including tearing down or removal of the abutments. Accordingly, I would reverse the ALJ and grant the Exceptions of Prosecutory staff and PennDOT.  Since the Petition for Modification remains outstanding, I recommend remanding the proceeding to the Office of Administrative Law Judge (OALJ) to be handled as detailed in the following paragraph.

The proceeding has been ongoing for more than a decade and the costs of further litigation will be borne by the ratepayers and taxpayers of the Commonwealth.  In light of these considerations, further litigation is not in the public interest as it would result in additional costs.  In the interest of bringing a final resolution to this proceeding, the parties should be given an opportunity to further examine the matters raised in the July 14, 2005 Petition for Modification and alternatives to removal of the abutments presented by the various parties.  Mediation of this issue presents a cost effective viable alternative to further litigation.  The parties are encouraged to utilize the mediation process and participate in good faith to come to a resolution on this issue that addresses the parties concerns and promotes the public interest.  If mediation is not successful the matter will be referred to OALJ for hearing on the July 14, 2005 Petition for Modification. 

Moreover, since the Authority filed a Petition for Modification requesting that the abutment removal requirement be eliminated from the project requirements, I am not inclined to impose a civil penalty at this time.  Imposing a civil penalty at this point serves no useful purpose other than to impose an undue burden on the taxpayers of Luzerne County.

THEREFORE, I MOVE:


1.
That the Recommended Decision dated June 4, 2007 be reversed.


2.
That the Exceptions filed by the Pennsylvania Department of Transportation and the Commission’s Bureau of Transportation and Safety, Prosecutory Staff be granted to the extent they are consistent with this Motion.


3.
That the Petition for Modification be remanded to the Office of Administrative Law Judge for mediation.

4.
If mediation is not successful the matter will be referred to OALJ for hearing on the July 14, 2005 Petition for Modification. 
5.
That the Office of Special Assistants prepare the Opinion and Order.

__________________________

___________________________________





DATE




WENDELL F. HOLLAND, CHAIRMAN


