PENNSYLVANIA

PUBLIC UTILITY COMMISSION

Harrisburg, PA 17105-3265

Public Meeting held June 24, 2004

Commissioners Present:

Terrance J. Fitzpatrick, Chairman

Robert K. Bloom, Vice Chairman

Glen R. Thomas

Kim Pizzingrilli

Wendell F. Holland

| Borough of Penn v. Consolidated Rail Corporation, Pennsylvania Department of Transportation, Penn Township, the City of Jeanette and County of Westmoreland Alleging Conrail’s Refusal to Construct a Replacement Bridge Near the Site of the Former Borough Bridge, Westmoreland County | C-00892372 |
| --- | --- |

OPINION AND ORDER

BY THE COMMISSION:

Before the Commission for consideration and disposition is a Petition for Extension of Time (Petition) filed on May 27, 2003, by the Pennsylvania Department of Transportation (PennDOT).  The Petition refers to our Order of March 29, 1996, which adopted as the action of the Commission the Recommended Decision of Administrative Law Judge (ALJ) James D. Porterfield, issued on February 12, 1996.  On June 6, 2003, the Commission’s Bureau of Transportation and Safety (BTS) filed an Answer and New Matter to the Petition.

History of the Proceedings

On May 18, 1989, the Borough of Penn (Borough) filed a Complaint against Conrail.  The Complaint alleged, inter alia, that a Borough bridge originally constructed by the Pennsylvania Railroad Company (PRR) was then collapsing and, therefore, should be either replaced or substantially reconstructed.  The construction of the Borough bridge by PPR emanated from a Public Service Commission Order dated April 2, 1934.

An Initial Hearing was held on May 23, 1991, and a Recommended Decision was issued on June 18, 1992, allocating costs and assigning various responsibilities between the Borough and Conrail.  By Opinion and Order entered on January 5, 1993, the Commission granted a Joint Petition to Reopen the Record filed by the Borough and the Township of Penn on August 31, 1992.  The Opinion and Order directed Conrail to perform an engineering study to determine whether the bridge should be rehabilitated or replaced, and also directed Conrail to report its recommendation to the Commission within one year.

Subsequently, the case was remanded to the Office of Administrative Law Judge (OALJ) for further hearing to determine the exact location of the bridge and which municipalities actually have property along its boundaries.  ALJ Porterfield issued a Recommended Decision on Remand on February 2, 1996.  Conrail filed Exceptions to the Recommended Decision on February 27, 1996.  	By Order entered on March 29, 1996, the Commission directed PennDOT to complete the construction of the subject bridge by September 30, 1999.

PennDOT sought and was granted two prior extensions of time.  On January 2, 2001, Conrail filed a Response to PennDOT’s Petition.  By Order entered on March 12, 2001, the Commission directed, inter alia, that PennDOT should prepare and submit detailed right-of-way and construction plans for the construction of a new bridge and any necessary highway approaches by May 31, 2003.  (Opinion and Order of March 12, 2001, at 6).

PennDOT filed the instant Petition on May 27, 2003 seeking another extension of time.  BTS filed an Answer as above noted.

### Discussion

We note that Section 1.15 of our Regulations, 52 Pa. Code §1.15, confers upon us the authority and discretion to grant an extension of time.  Section 1.15 provides, in pertinent part, as follows:

§ 1.15.  Extensions of time and continuances

(a)	Extensions of time shall be governed by the following:

Except as otherwise provided by statute, whenever under this title or by order of the Commission,...an act is required or allowed to be done at or within a specified time, the time fixed or the period of time prescribed may, by the Commission, the presiding officer or other authorized person, for good cause be extended upon motion made before the expiration of the period originally prescribed or as previously extended.  Upon motion made after the expiration of the specified period, the act may be permitted to be done where reasonable grounds are shown for the failure to act.

We note initially that the Commission has the exclusive authority to order the construction, alteration, relocation, suspension or abolition of railroad crossings such as the one involved here.  Additionally, the Commission has the exclusive authority to determine and order which concerned parties should perform such work at the crossing and which concerned parties shall maintain the crossing in the future, all to effectuate the prevention of accidents and the promotion of the safety of the public.  66 Pa. C.S. § 2702(b).

In its Petition, PennDOT alleges that it is encountering difficulty in formulating final design plans for the replacement of the structure due to unforeseen engineering design issues.  It avers that its consultants and engineers require additional time to convene further meetings of the design team, in order to formulate a suitable bridge replacement design.  That design should improve the existing alignment, retain or improve the existing grade, and minimize the impact to the surrounding community.  (Petition, ¶¶ 14-16).

In response, BTS points out that PennDOT has already been granted two previous time extensions in order to comply with the Commission’s Order.  As such, BTS rejoins that the engineering design issues presented by the subject bridge could not have been completely unforeseen.  The design and configuration of the existing structure has been known by PennDOT and all Parties since the first hearing herein, and those conditions have existed since the Pennsylvania Public Service Commission ordered the bridge constructed in 1934.  (Answer, ¶¶ 14-16).

In its New Matter, BTS asserts that the existing bridge is currently posted for a weight limit of thirty-three tons for single vehicles and forty tons for combination vehicles.  BTS points out that in the Commission’s Order of March 29, 1996, at Paragraph 6 thereof, Conrail was ordered to maintain the existing structure for the thirty-three ton/forty ton weight limit until the replacement structure was constructed.  (New Matter, ¶¶ 18, 19).  BTS further points out that, since the entry of the Commission’s Order of March 29, 1996, Norfolk Southern Railway Company (Norfolk Southern) has replaced Conrail as the operating railroad at the subject crossing.

We note that to date, PennDOT has not provided BTS, Norfolk Southern, or the Commission with current information on the condition of the existing structure and whether or not it will be able to continue carrying vehicular traffic of the relevant weight until the time when the bridge will be replaced.  (New Matter, ¶¶ 20-21).  BTS requests that, if the Commission grants the instant Petition, PennDOT be ordered to provide a written report by a professional engineer setting forth the current condition of the bridge and certifying that the bridge is capable of carrying vehicular traffic of the weight set forth in the Commission’s Order.

On review of the instant Petition, we conclude that PennDOT has demonstrated good cause for a grant of the Petition, pursuant to Section 1.15, supra.  Specifically, we note the difficulty PennDOT has encountered in the formulation of final design plans for the replacement of the bridge.  (Petition, ¶ 15).  However, we are also mindful that PennDOT has previously received two prior time extensions.  Therefore, we will grant PennDOT its requested extension of time until May 31, 2005, in order for it to formulate the relevant plans.  However, we will also require that PennDOT submit a written report, prepared by a professional engineer, on the weight-carrying capacity of the existing bridge as well as a verification of the structural adequacy and the general condition of the bridge.  We caution PennDOT to move expeditiously to ensure timely completion of the work contemplated by this Opinion and Order.

## Conclusion

We have carefully reviewed the record as developed in this proceeding.  Premised upon our review, we find that PennDOT’s Petition, requesting a time extension for the formulation of a bridge replacement design, as directed in our Order entered on March 29, 1996, as subsequently modified, is meritorious.  Accordingly, we will grant PennDOT’s Petition to the extent that it is consistent with this Opinion and Order; THEREFORE,

IT IS ORDERED:

1.	That the Petition for Extension of Time filed by Pennsylvania Department of Transportation is granted to the extent consistent with this Opinion and Order.

2.	That Ordering Paragraph No. 7 of our Order entered herein on March 29, 1996, as modified most recently by our Order of March 12, 2001, is further modified to read as follows:

- That the Pennsylvania Department of Transportation, having agreed to do so, at its initial cost and expense, by May 31, 2005, shall prepare and submit to all parties for review and to this Commission for review and approval detailed right-of-way and construction plans for the construction of a new bridge, to replace the existing bridge and for the construction of any necessary highway approaches to the new bridge.  The new bridge is to be constructed to provide for, but not be limited to, the following:

- The new bridge is to be constructed to present day design standards for loads and width for the class and volume of traffic likely to use the Burrell Hill Road Bridge;

- The minimum vertical clearance under the bridge shall conform to the requirements set forth at 52 Pa. Code §33.121 (Overhead clearance);

- The minimum side clearance between the tracks and the bridge shall conform to the requirements at 52 Pa. Code §33.122 (Side clearances).

3.	That Ordering Paragraph No. 8 of our Order entered herein on March 29, 1996, as modified most recently by our Order of March 12, 2001, is further modified to read as follows:

- That the Pennsylvania Department of Transportation, by May 31, 2005, at its initial cost and expense, shall prepare and submit a metes and bounds description of any railroad property required to be appropriated by the Commission for the project, subsequent to which the described property shall be appropriated according and pursuant to the provisions of Section 2702(b) of the Public Utility Code, 66 Pa. C.S. §2702(a).

4.	That, in all other respects not inconsistent herewith, the Order of March 29, 1996, as amended, shall remain in full force and effect.

5.	That Pennsylvania Department of Transportation provide to the Commission, within ninety days of the date of entry of this Opinion and Order, a written report prepared signed and sealed by a professional engineer setting forth the current condition of the existing bridge and certifying that the bridge is capable of carrying vehicular traffic of the weight set forth in the Commission’s Order entered March 29, 1996, as well as a verification as to the structural adequacy and the general condition of the bridge.

6.	That the Commission’s Order entered March 29, 1996, as subsequently modified, is further modified to reflect that Norfolk Southern Railway Company has replaced Consolidated Rail Corporation as the operating railroad at the crossing that is the subject of this proceeding.

BY THE COMMISSION,

James J. McNulty

Secretary

(SEAL)

ORDER ADOPTED:  June 24, 2004

ORDER ENTERED:  June 28, 2004

# Footnotes

PPR was the predecessor railroad to Conrail at this crossing.

The Public Service Commission was the predecessor to the Public Utility Commission.