PENNSYLVANIA

PUBLIC UTILITY COMMISSION

Harrisburg, PA 17105-3265

Public Meeting held August 6, 2009
Commissioners Present:

James H. Cawley, Chairman


Tyrone J. Christy, Vice Chairman


Kim Pizzingrilli


Wayne E. Gardner

Robert F. Powelson
	Application of Consolidated Rail Corporation for the Abolition of Thirty‑One Crossings of the Enola Branch, LC201323, MP 3.5 to MP 27.0, Sub No. 1095X, Harrisburg Division, Lancaster County

Board of Supervisors of Bart Township

                               v.

Consolidated Rail Corporation and the Pennsylvania Department of Transportation and Commissioners of the County of Lancaster, et al.  


	A‑00111016
C-00913256


OPINION AND ORDER

BY THE COMMISSION:  



Before the Commission for consideration and disposition is a Petition to Request a Partial Further Extension of Time (Petition) filed by Norfolk Southern Railway Company (Norfolk Southern) on June 26, 2009.  No Response to the Petition has been filed. 



The Opinion and Order to which the Petition refers was initially entered on October 9, 1997, and subsequently was modified by Opinion and Orders entered on November 22, 1999, January 26, 2001, April 15, 2002, and October 31, 2007.
History of the Proceedings


This proceeding involves two consolidated proceedings at Docket Nos. C‑00913256 and A-00111016.  The Complaint at the C-docket was initiated on February 25, 1991.  The proceeding at the A-docket was initiated when Conrail filed an Application with the Commission on September 29, 1993, requesting approval for the abolition of thirty-one rail-highway crossings along its Enola Branch located in Lancaster County.



After preliminary proceedings, the Commission, per Opinion and Order entered on October 9, 1997, adopted the Recommended Decision of Administrative Law Judge (ALJ) Louis G. Cocheres, as modified.  A Stipulation of Settlement among the Parties subsequently was approved, consistent with the October 9, 1997 Opinion and Order.  As above noted, the October 9, 1997 Opinion and Order was modified by Opinion and Orders entered on November 22, 1999, January 26, 2001, April 15, 2002, and October 31, 2007.


The instant Petition was filed as outlined above.  In its Petition, Norfolk Southern is requesting an extension of time until December 31, 2010, for certain work to be performed on Crossing No. 28 herein.
Discussion



We note that Section 1.15 of our Regulations, 52 Pa. Code § 1.15, confers upon us the authority and discretion to grant an extension of time.  Section 1.15 provides, in pertinent part, as follows:



§ 1.15.  Extensions of time and continuances


(a)
Extensions of time shall be governed by the following:




Except as otherwise provided by statute, whenever under this title or by order of the Commission, . . . an act is required or allowed to be done at or within a specified time, the time fixed or the period of time prescribed may, by the Commission, the presiding officer or other authorized person, for good cause be extended upon motion made before the expiration of the period originally prescribed or as previously extended.  Upon motion made after the expiration of the specified period, the act may be permitted to be done where reasonable grounds are shown for the failure to act. 



In our Order entered herein on October 31, 2007, Norfolk Southern was granted an extension of time to perform certain work originally outlined in our Order entered on October 9, 1997, as subsequently modified.  Specifically, Norfolk Southern was granted an extension of time until June 30, 2009, to remove the electric transmission line towers of the National Railroad Passenger Corporation (Amtrak) from the Martic Forge Bridge (Crossing No. 28) and to re-suspend the line in a manner satisfactory to Amtrak pursuant to Ordering Paragraph No. 149 of the Commission’s Opinion and Order entered on October 9, 1997, as subsequently modified.



In its Petition, Norfolk Southern avers that Amtrak has informed it that it has received Federal stimulus funding to modernize its transmission line along the entire length of the former Enola Branch rail line.  The work will involve replacing an antiquated dual pole system with a mono pole, as has been proposed for the Martic Forge transmission line re-suspension in connection with this proceeding.  Petition at ¶ 3.


Norfolk Southern further avers that Amtrak has informed it that Amtrak would like to take advantage of design and construction cost savings by incorporating the Martic Forge bridge line re-suspension project into its larger transmission line modernization project.  Petition at ¶ 4.  Amtrak’s transmission line modernization project is on a “fast track,” according to Amtrak representatives, and is expected to be completed next year.  Petition at ¶ 5. 
On review of Norfolk Southern’s Petition, we find it to be meritorious.  We note that Federal stimulus money for this modernization project has been received.  Accordingly, it makes sense for Amtrak, at this point, to incorporate the Martic Forge bridge line re-suspension project into its larger transmission line modernization project.   Accordingly, the instant Petition will be granted, and the appropriate modification will be made to the appropriate Ordering Paragraph of our 1997 Order, pertaining to Crossing No. 28.  We note that Amtrak’s receipt of the stimulus money will not alter Norfolk Southern’s (or Conrail’s) financial responsibility for the Martic Forge line relocation.
Conclusion



We have carefully reviewed the record as developed in this proceeding.  Premised upon our review, we find that Norfolk Southern’s Petition, requesting a time extension, is meritorious.  Accordingly, it will be granted.



As we have noted previously, due to the lengthy litigation which has characterized this proceeding, this project has been pending for far too long.  Accordingly, we encourage all Parties to work as expeditiously as possible to complete the project in a timely manner.  The Parties are to continue filing status reports every six months, as originally directed in our 2007 Order; THEREFORE, 



IT IS ORDERED:  



1.
That the Petition to Request a Partial Further Extension of Time filed by Norfolk Southern Railway Company on June 26, 2009, with reference to our Opinion and Order herein originally entered on October 9, 1997, as subsequently modified, is granted.  



2.
That our Opinion and Order herein originally entered on October 9, 1997, as subsequently modified, be further modified as outlined in the following Paragraph.

3.
That Ordering Paragraph No. 149 of our Opinion and Order herein originally entered on October 9, 1997, as subsequently modified, and referring to Crossing No. 28, be further modified to read as follows:

149.
That Norfolk Southern Railway Company, by December 31, 2010, at its sole cost and expense, furnish all materials and do all work necessary to remove the National Railroad Passenger Corporation’s transmission line towers from the bridge, and to re-suspend the line, in a manner satisfactory to National Railroad Passenger Corporation.  That National Railroad Passenger Corporation cooperate with Norfolk Southern Railway Company in the removal of said towers and re-suspension of the transmission line.


4.
That, in all other respects, our Opinion and Order herein originally entered on October 9, 1997, as subsequently modified, remains in full force and effect. 



5.
That the Pennsylvania Department of Transportation, the Townships of Bart, Martic and Sadsbury and Norfolk Southern Railway Company each continue to file status reports on the progress of this project, as originally outlined in our 2007 Order herein.  Said reports are to be filed with the Secretary of the Commission, with a copy to the Bureau of Transportation and Safety, Rail Division, every six months.

[image: image1.emf]







THE COMMISSION,







James J. McNulty








Secretary

(SEAL)

ORDER ADOPTED:  August 6, 2009
ORDER ENTERED:  August 12, 2009
�     In our 2007 Order, the pertinent paragraph is Ordering Paragraph No. 14, found on page 14 thereof.      





11
6

