SUMMARY

A Letter of Notification is being submitted by PPL Electric Utilities Corporation (“PPL Electric”) pursuant to the Pennsylvania Public Utility Commission’s (”Commission”) regulations at 52 Pa. Code §§ 57.71 through 57.77 for approval to reconstruct the single-circuit Otter Creek – Conastone 230 kV Transmission Line.  This transmission line is being reconstructed as part of PPL Electric’s Vintage Conductor program that was developed to address deteriorated transmission facilities within PPL Electric’s system that were generally constructed in the mid-1920s through the 1930s.  The Vintage Conductor Program is further described in Attachment 1.  

The Otter Creek – Conastone 230 kV project, as described in this filing, will rebuild approximately 12 miles of the single-circuit Otter Creek – Conastone 230 kV Transmission Line between PPL Electric’s Otter Creek Switchyard and the Maryland border.  This line traverses portions of Chanceford, Hopewell and East Hopewell Townships, all of which are in York County.  In Maryland, the line continues to Baltimore Gas and Electric’s (“BG&E”) Conastone Substation.  The portion of the line in Maryland is owned and operated by BG&E and is not a subject to this Letter of Notification.  The proposed reconstructed line will be designed for two 230 kV circuits, although only one circuit will initially be installed.  

The reconstruction of this transmission line will include the removal of the existing lattice towers, conductors, and hardware and will replace them with new single shaft steel poles, conductors, and hardware.  No new rights-of-way will be required because the proposed line will be rebuilt within the existing right-of-way between the Otter Creek Switchyard and the last tower in Pennsylvania.  

Due to the deteriorated condition of the Otter Creek – Conastone transmission line and towers, PPL Electric is expeditiously moving forward with this project before failure of this line occurs.  

The total estimated cost of the proposed transmission work is approximately $16,856,705.  This project has a scheduled construction start date of July 2012 in order to meet an in-service date of October 2013.

This document, which describes the need for the project and explains the engineering and siting analysis for the proposed construction, consists of the following:

Attachment “1”
Necessity Statement

Attachment “2”
Engineering Description

Attachment “3”
Siting Analysis and Environmental Assessment

Attachment “4”
PPL Electric Design Criteria and Safety Practices

Attachment “5”
PPL Electric Magnetic Field Management Program
Attachment “6” 
List of Involved Governmental Agencies, Municipalities, and Other Public Entities

Attachment “7” 
List of Owners of Property within the Right-of-Way

Attachment “8” 
Environmental Inventory Guidelines 

Attachment “9”
Land Use and Comprehensive Plan Assessment

Attachment “10”
Historic Architectural and Archeological Sites

Attachment “11” 
References 

[image: image1]
[image: image2.png]PPL ELECTRIC UTILITIES SERVICE TERRITORY

Northeast
Region

Honesdale

Susquehanna
Region

Central HONESDALE

WILKES-
BARRE

POCONO

HAZLETON

SCHUYLKILL

Lehigh

Harrisburg | .
Re ion Pottsville l Re |o||

LANCASTER

PENNSYLVANIA

Lancaster
Region

LANCASTER
EAST





Otter Creek – Conastone 230 kV Transmission Line








■ Manor









1
SUMMARY


