PENNSYLVANIA

PUBLIC UTILITY COMMISSION

Harrisburg, PA 17105-3265

                       Public Meeting held April 26, 2012
Commissioners Present:

Robert F. Powelson, Chairman

John F. Coleman, Jr., Vice Chairman

      Wayne E. Gardner


James H. Cawley

Pamela A. Witmer
Letter of Notification of PPL Electric 




A-2012-2284616
Utilities Corporation filed pursuant to 52 
Pa. Code Chapter 57 with respect to the 

construction of the West Trexlertown #1

and #2 138/69kV Tap Line in Upper 
Macungie Township, Lehigh County, Pennsylvania.
Petition of PPL Electric Utilities Corporation



P-2012-2284623
for a finding that a building to shelter
control equipment at the West Trexlertown
69-12 kV Substation to be constructed in
Upper Macungie Township, Lehigh County,
Pennsylvania is reasonably necessary for

the convenience or welfare of the public.  
ORDER

BY THE COMMISSION:

On January 20, 2012, PPL Electric Utilities Corporation (“PPL Electric”) filed a Letter of Notification (“LON”) pursuant to 52 Pa. Code § 57.72(d)(1)(vi) of the Commission’s transmission line siting regulations.  Section 57.72 authorizes the abbreviated “Letter of Notification” siting application process in lieu of an application for the following:

(i) An HV line which is proposed to be located entirely on an existing transmission line right-of-way, so long as the size, character, design, or configuration of the proposed HV line does not substantially alter the right-of-way.

            (ii)      An HV line which is proposed to be located entirely within a public road.

(iii)  An HV line which is proposed to be located entirely within applicant’s existing transmission line right-of-way and the property of the sole customer to be served by the line, so long as the size, character, design, or configuration of the proposed HV line does not substantially alter the right-of-way.

(iv) A line for which the voltage is proposed to be increased above its present levels, so long as the size, character, design, or configuration of the proposed HV line does not substantially alter the right-of-way.
(v)  An HV line which is to be reconductored or reconstructed so long as the size, character, design, or configuration of the proposed HV line does not substantially alter the right-of-way.  

(vi)    An HV line having a proposed route of 2 miles or less.


Copies of the Letter of Notification were served in accordance with Section 57.72(d) (3) and 57.74 (b), (c) on the PA Department of Transportation, PA Department of Environmental Protection, PA Historical and Museum Commission, Lehigh County Board of Commissioners, Lehigh County Planning Commission and other interested parties as listed in the Certificate of Service, including township supervisors and planning commissions.  No protests were filed.  A hearing was held.


PPL Electric seeks the Commission’s approval to construct the West Trexlertown #1 and #2 138/69kV Tap Line (“West Trexlertown Tap”) in Upper Macungie Township, Lehigh County. 


The line will be designed and constructed for double circuit 138kV operation, but will initially operate with a single circuit at 69kV.  The second circuit will be installed and the operating voltage increased to 138kV when future load increases make it appropriate to maintain service reliability.   


This project is necessary to resolve overload conditions and violations of reliability criteria while increasing the operating flexibility in the Trexlertown and South Fogelsville areas of Lehigh County.  PPL Electric proposes to install two new 12kV distribution lines that will be connected to and supplied by the new West Trexlertown 69-12kV Substation.  To accomplish this reinforcement, the proposed West Trexlertown Tap will extend 1,200 feet and connect the existing AT&T R&D #1 and #2 138/69kV Transmission Tap Line to the proposed West Trexlertown Substation, connecting the substation to the electric grid.  The new West Trexlertown Substation and the new 12kV distribution circuits will allow the transfer of load to relieve the existing overloading conditions on the Trexlertown 69-12kV Substation.  


Currently there are several violations of PPL Electric’s Reliability Principles and Practices (“RP&P”) which, if left unaddressed, could cause extended service interruptions, conductor damage or failure and transformer overloads.  PPL Electric has adopted RP&P guidelines in order to direct its planning process and to establish standards for its transmission and distribution systems which will enable it to provide safe and reliable service at a reasonable cost.  PPL Electric relies on the RP&P standards to determine the need to reinforce its transmission and distribution system.  



The proposed 1,200 foot long West Trexlertown Tap will require seven steel monopoles.  The tap structure will be 125 feet high and will have a concrete foundation.  The remaining poles will range in height between 70 and 100 feet.  The tangent structures will be direct embedded while the angle structures may either be installed on concrete foundations or guyed.  In addition to the steel monopoles, two load sectionalizing air brake switch poles will be installed to interconnect the West Trexlertown Tap with the AT&T R&D #1 and #2 138/69kV Transmission Tap Line.  


The transmission line will consist of six power conductors and one or two overhead ground wires.  The power conductors will be 556.5kcmil, 24/7 stranding ACSR.  Lightning protection will be provided by the 3/8 inch steel overhead ground wire.   



The West Trexlertown Tap and the West Trexlertown Substation will be constructed entirely on a 61 acre parcel in Upper Macungie Township, Lehigh County that is owned in fee by PPL Electric.  As a result, no additional rights-of-way are necessary for completion of this line.   


No communication towers, pipelines or other utilities will be affected by construction of the proposed line.  The closest airport, the Zettlemoyer Airport in Kutztown, is 3.1 miles from the project site.  PPL Electric will contact PENNDOT and the Federal Aviation Administration to ensure that the proposed construction will not be a flight hazard.  


The Pennsylvania Historical and Museum Commission (“PHMC”) has reviewed the project and identified archeological sites in the proximity.  PPL Electric had a Phase 1 Archeological Survey performed that resulted in no significant archeological artifacts on the site where the proposed facilities will be constructed, although artifacts were found on other portions of the property.  A Phase 2 report will be submitted to PHMC for the entire property.  


PPL Electric will obtain all permits from the Pennsylvania Department of Environmental Protection and the U.S. Army Corp of Engineers and will comply with all conditions placed on the permits.  The line will not cross any wetlands or aquatic resources.  


Regarding endangered and threatened species, PPL Electric has reviewed the Pennsylvania National Diversity Inventory and hired an outside consultant to conduct a study of the area.  As a result, all conflicts with species of concern have been resolved with appropriate agencies. 


PPL Electric states that the proposed construction will not create any unreasonable risk of danger to the health and safety.  The Transmission Lines will be designed, constructed, operated and maintained in a manner that meets or surpasses all applicable National Electric Safety Code (“NESC”) minimum standards and all applicable legal requirements.  


The estimated cost of the transmission line portion of this project, that is the subject of this LON, is $320,000 and will be borne by PPL Electric.  Construction of the project is scheduled to begin as soon as possible to reach an in-service date of April 2013, pending approvals.  



As stated earlier, the proposed West Trexlertown #1and #2 138/69kV Tap Line is planned in conjunction with the proposed West Trexlertown 69-12kV Substation.  Contemporaneously filed with this LON, PPL Electric, on January 20, 2012, also filed with the Commission a Petition for a finding that a building to shelter control equipment at the proposed West Trexlertown 69-12 kV Substation in Upper Macungie Township, Lehigh County, is reasonably necessary for the convenience or welfare to the public and, therefore exempt from any local zoning ordinance.  The tap line, that is the subject of the LON filing, will supply the proposed substation.  Issues related to the Zoning Petition are interrelated with this Letter of Notification.  


In the Zoning Petition, PPL Electric states that the proposed West Trexlertown Substation will include a building to shelter control equipment (“Control Equipment Building”).  The purpose of this Control Equipment Building is to protect certain switches, relays and other control equipment from the elements so that the line, equipment, and the entire substation, can function properly.  The building will not be intended for human occupancy; there will be no supply of water and no sanitary facilities.  The Control Equipment Building will be contained within the fenced perimeter of the substation.  The West Trexlertown Substation will be located on a 61 acre tract of land in Upper Macungie Township, Lehigh County and will occupy approximately .3 acres.   



PPL Electric states that the Pennsylvania Municipalities Planning Code ("MPC") provides, in relevant part, as follows: 

“This article shall not apply to any existing or proposed building, or extension thereof, used or to be used by a public utility corporation, if, upon petition of the corporation, the Pennsylvania Public Utility Commission shall, after public hearing, decide that the present or proposed situation of the building in question is reasonably necessary for the convenience or welfare of the public.”

Section 619 of the MPC, Act of July 31, 1968, P.L. 805, as amended, 53 P.S. § 10619.  Thus, a public utility building is subject to local zoning requirements for buildings unless, upon petition, the Commission determines that the proposed situation of the building in question is reasonably necessary for the convenience or welfare of the public. 53 P.S. §10619.
             PPL Electric argues, as explained above, that the proposed West Trexlertown #1 and #2 138/69kV Tap Line, two 12kV distribution lines and West Trexlertown 69-12kV Substation are necessary to resolve violations of reliability criteria and increase operating flexibility in the Trexlertown and South Fogelsville areas of Lehigh County.  The substation must include certain control equipment to operate properly, and said equipment must be protected from the elements, which requires the construction of a Control Equipment Building on the site proposed for the substation.  Because the West Trexlertown Substation is reasonably necessary for the public convenience and welfare, and because the Control Equipment Building is necessary to operate the West Trexlertown Substation, the Commission should find that the Control Equipment Building is reasonably necessary and, therefore, exempt from the Upper Macungie Township’s local zoning ordinance pursuant to Section 619 of the MPC.  Del-AWARE Unlimited, Inc. v. Pa. P.U.C., 513 A.2d 593 (Pa. Cmwlth. 1986).   


Further, on January 11, 2001, the Commission adopted a policy statement to further the Commonwealth's goal of making agency actions consistent with sound land use planning by considering the impact of its decision upon local comprehensive plans and zoning ordinances. See 31 Pa. Bull. 951 (Feb. 17, 2001).  Section 69.1101 of the Commission's Regulations provides: 
[T]he Commission will consider the impact of its decisions upon local comprehensive plans and zoning ordinances. This will include reviewing applications for: 

(1)  Certificates of public convenience. 

(2)  Siting electric transmission lines. 

(3) Siting a public utility "building" under section 619 of the Municipalities Planning Code (53 P.S. § 10619). 

(4) Other Commission decisions."
52 Pa. Code § 69.1101.


Furthermore, Upper Macungie Township (“UMT”) has adopted a zoning ordinance.  See UPPER MACUNGIE TOWNSHIP ZONING ORDINANCE, as amended (2011).  Under the Zoning Ordinance, a construction permit, zoning permit, and building permit are required for the construction of any building or structure.  See UMT ZONING ORDINANCE, Article 2, § 202, pp., 57-58, Article 10, Section 1006, p. 226. 


The UMT ZONING ORDINANCE defines a structure to include any man-made object having an ascertainable stationary location on land.  See UMT ZONING ORDINANCE Article 2, § 202, p. 68.  The UMT ZONING ORDINANCE also provides that any structure shall be subject to the principal or accessory setbacks of the Zoning Ordinance unless specifically exempted.  With respect to electrical substations, the UMT Zoning Ordinance provides that electrical substations with outdoor structures at least ten feet high are required to provide evergreen screening on the sides of the substation that are within 150 feet of a dwelling, undeveloped residentially zoned land, expressway or arterial street.  Furthermore, it requires specific fencing parameters for electrical substations, as well as specific setbacks for each zoning district.  



The site for the West Trexlertown Substation is zoned as a R1 Rural Residential District.  The UMT Zoning Ordinance provides that, unless exempted, public utility facilities are not permitted, as a permitted use or by special exemption, in any residential district, including R1 Rural Residential Districts.   


The UMT ZONING ORDINANCE expressly recognizes that public utilities may be exempt from local zoning and local regulations under Section 619 of the MPC.  Therefore, consistent with Section 619 of the MPC, the UMT Zoning Ordinance provides that a public utility building is exempt from local zoning upon a finding by the Commission that the building is necessary for the convenience or welfare to the public.  



In the absence of a finding by the Commission under Section 619 of the MPC, it is unlawful under the UMT ZONING ORDINANCE for PPL Electric to commence work on and begin to use the Control Equipment Building until zoning, construction and building permits have been obtained.  


PPL Electric states that if they were required to obtain zoning, construction and building permits prior to construction, the process, including appeals from adverse determinations, could consume substantial time and could delay the construction of the West Trexlertown Substation, West Trexlertown Tap and associated 12 kV distribution facilities which are reasonably necessary for the convenience or welfare of the public.



Additionally, PPL Electric has provided information to representatives of Upper Macungie Township and Lehigh County describing the West Trexlertown project.  These entities have not objected to the project.  A copy of the Petition was served upon the Upper Macungie Township Planning Board, Upper Macungie Township Board of Supervisors, Lehigh County Commissioners and Lehigh Valley Planning Commission. 


For these reasons, PPL Electric requests that the Commission find that the Control Equipment Building is reasonably necessary for the convenience or welfare of the public and is, therefore, exempt from the requirements of the Upper Macungie Township Zoning Ordinance that may, in Upper Macungie Township’s opinion, impose any restriction, condition, or regulation on the construction of the Control Equipment Building. 


Notice of the filing of the Petition was published in the February 4, 2012 Pennsylvania Bulletin at 42 Pa. B. 746 specifying a deadline of February 21, 2012 for filing protests or petitions to intervene.  No protests or petitions to intervene were filed.  



By Hearing Notice dated February 8, 2012, an Initial Hearing pursuant to the provision of 53 P.S. 10619 was scheduled for March 6, 2012, and the case was assigned to Administrative Law Judge Susan D. Colwell.  


The Initial Hearing convened as scheduled on March 6, 2012.  PPL Electric was represented by legal counsel.  No other entity was present.  A transcript of the hearing was produced.   


Since there was no objection, the matter was reassigned to the Bureau of Technical Utility Services for processing in an Order dated March 27, 2012.  



Upon review, the Commission finds that the PPL Electric Letter of Notification and manner in which it was filed conform to the requirements of 52 Pa. Code § 57.72(d)(1)(vi)  because the proposed West Trexlertown #1 and #2 138/69 kV Tap Line is less than two miles in length.  Moreover, the Commission has reviewed the filing and does not find it to be inconsistent with the applicable law or Commission policy regarding transmission line siting and, therefore, to be in the public interest.   We note that our approval of the Letter of Notification does not reach the issues of accounting treatment and cost recovery.  Also, PPL Electric’s Zoning Petition and manner in which it was filed conform to the requirements of 52 Pa. Code § 5.41 and 53 P.S. § 10619, and because there were no protests to the Petition, the Petition is granted; THEREFORE,
IT IS ORDERED:



1. That the Letter of Notification filed by PPL Electric Utilities Corporation with respect to the West Trexlertown #1 and #2 138/69kV Tap Line in Upper Macungie Township, Lehigh County, Pennsylvania, is hereby approved.


2. That the Petition of PPL Electric Utilities Corporation for a finding that a building to shelter control equipment at the proposed West Trexlertown 69-12 kV Substation in Upper Macungie Township, Lehigh County, Pennsylvania is reasonably necessary for the convenience or welfare of the public and, therefore exempt from any local zoning ordinance, is hereby granted.  

[image: image1.png]




BY THE COMMISSION,


Rosemary Chiavetta


Secretary

(SEAL)

ORDER ADOPTED: April 26, 2012
ORDER ENTERED:  April 26, 2012
PAGE  
11

