# PENNSYLVANIA

# PUBLIC UTILITY COMMISSION

# Harrisburg, PA 17105-3265

# Public Meeting held May 23, 2013

Commissioners Present:

Robert F. Powelson, Chairman

John F. Coleman, Jr., Vice Chairman

Wayne E. Gardner

James H. Cawley

Pamela A. Witmer

| Petition of Peoples Natural Gas Company, LLC for Approval of Limited Waivers of Certain Tariff Rules Related to Customer Service Line Replacement | Docket No. P-2013-2346161 |
| --- | --- |
| Petition of Peoples Natural Gas Company, LLC for Approval of its Long-Term Infrastructure Improvement Plan # Petition of Peoples Natural Gas Company, LLC for Approval of a Distribution System Improvement Charge | P-2013-2344596 P-2013-2344596 |
| Office of Consumer Advocate v. Peoples Natural Gas Company, LLC | C-2013-2348847 |

# OPINION AND ORDER

BY THE COMMISSION:

Before the Commission for consideration are the Petitions for approval of the Limited Waivers of Certain Tariff Rules Related to Customer Service Line Replacement (Waiver Petition), Long-Term Infrastructure Improvement Plan (LTIIP), and the Distribution System Improvement Charge (DSIC) of Peoples Natural Gas Company, LLC (Peoples or Company).

HISTORY OF THE PROCEEDING

Peoples is a corporation organized and existing under the laws of the Commonwealth of Pennsylvania.  Peoples is in the business of selling and distributing natural gas to retail customers within the Commonwealth, and is therefore a “public utility” within the meaning of Section 102 of the Public Utility Code, 66 Pa. C.S. §§ 102, subject to the regulatory jurisdiction of the Commission.  Peoples, as an NGDC, provides natural gas service to approximately 360,000 residential, commercial, and industrial customers in all or portions of 16 Southwestern Pennsylvania Counties.  Peoples provides service through approximately 8,000 miles of mains and 352,000 services that it owns, operates and maintains.

The Waiver Petition was filed on February 1, 2013.  Copies of the Waiver Petition were served upon the Bureau of Investigation and Enforcement (I&E), Office of Consumer Advocate (OCA), and Office of Small Business Advocate (OSBA).  The LTIIP was filed on January 23, 2013, with copies being served upon the statutory advocates in accordance with Implementation of Act 11 of 2012, Docket No. M-2012-2293611 (August 2, 2012) (Final Implementation Order).  The DSIC was filed on January 31, 2013.  Peoples’ DSIC Petition includes proposed Supplement No. 11 to Tariff Gas – Pa. P.U.C. No. 45 to introduce the DSIC Rider into the Company’s tariff with an effective date of April 1, 2013.  The filing was made pursuant to 66 Pa. C.S. § 1353 and the Final Implementation Order.

Regarding the Waiver Petition, OCA and I&E filed comments on February 21, 2013, in which they substantially agreed with Peoples’ request for limited waivers of certain tariff provisions relating to the replacement of customer-owned service lines.

The OCA filed comments pertaining to the LTIIP on February 12, 2013, but did not initially request hearings.  On February 20, 2013 OCA filed a Notice of Intervention and Public Statement, a Formal Complaint (Docket No. C-2013-2348847), and an Answer to Peoples’ DSIC Petition.  In its Answer to Peoples’ DSIC petition, OCA states that the Commission should deny Peoples’ Petition as filed, reject the proposed Tariff Supplement No. 11 to Tariff Gas – Pa. P.U.C. No. 45, and refer the matter to the Commission’s Office of Administrative Law Judge (OALJ) for a full hearing and investigation pursuant to OCA’s complaint.

On February 19, 2013 the Pennsylvania Independent Oil & Gas Association (PIOGA) filed a Petition to Intervene in Peoples’ DSIC proceeding.  PIOGA did not dispute any elements of Peoples’ DSIC.

On February 20, 2013 the OSBA filed a Notice of Intervention, Public Statement, and an Answer to Peoples’ DSIC Petition.  OSBA requested hearings and such relief as may be necessary or appropriate.  In its Answer, OSBA did not allege that any particular provision or relief requested by Peoples should be denied.

Daniel Killmeyer, an individual customer, filed a Formal Complaint on February 25, 2013.  Mr. Killmeyer asserted that Peoples should not be charging for upkeep to their equipment, as they should already have money set aside for such things.  He believes he should not have to pay for these items and that the DSIC should not be implemented.  Letters expressing opposition to the Peoples DSIC were received from 15 other individual customers, who all argued against implementation of a DSIC.

Peoples filed reply comments on March 4, 2013, in response to the OCA’s formal complaint and comments on Peoples’ DSIC petition.

On April 29, 2013, the United States Steel Corporation (U.S. Steel) filed a Petition to Intervene in the Peoples DSIC case.  We note that in waiting almost three months after the filing of Peoples’ DSIC Petition to file its intervention, U.S. Steel did not comply with the time period set forth in the Commission regulations for a party to declare itself as an intervener in a Commission case.  See 52 Pa. Code § 5.74(b).  Therefore, the Commission is rejecting U.S Steel’s petition as untimely and, thus, will not consider any comments of U.S. Steel to Peoples’ LTITP at this time.  However, U.S. Steel may file a petition to intervene nunc pro tunc in the hearings before the OALJ, but its intervention shall be limited only to the issues that have been referred to the OALJ as set forth in the body of this Order below.  See 52 Pa. Code § 1.2(a) and 5.71.

No objections or comments were received from federal, state or local governmental agencies.

BACKGROUND

On February 14, 2012, Governor Corbett signed into law Act 11 of 2012, (Act 11), which amends Chapters 3, 13 and 33 of Title 66.  Act 11, inter alia, provides jurisdictional water and wastewater utilities, electric distribution companies (EDCs), and natural gas distribution companies (NGDCs) or a city natural gas distribution operation with the ability to implement a DSIC to recover reasonable and prudent costs incurred to repair, improve or replace certain eligible distribution property that is part of the utility’s distribution system.  The eligible property for the utilities is defined in 66 Pa. C.S. §1351.  Act 11 states that as a precondition to the implementation of a DSIC, a utility must file a LTIIP with the Commission that is consistent with 66 Pa. C.S. §1352.

On April 5, 2012, the Commission held a working group meeting for discussion and feedback from stakeholders regarding its implementation of Act 11.  On May 10, 2012, the Commission issued a Tentative Implementation Order addressing and incorporating input from the stakeholder meeting.  Stakeholders filed comments to the Tentative Implementation Order on June 6, 2012.  On August 2, 2012, the Commission issued the Final Implementation Order, at Docket No. M-2012-2293611, establishing procedures and guidelines necessary to implement Act 11.

PEOPLES’ SERVICE LINE WAIVER PETITION

Peoples’ Petition

Before the Commission is the Waiver Petition of Peoples, for the approval of limited waivers of certain tariff rules relating to customer service line replacement, filed on February 1, 2013.  The tariff rules provide that certain customers are responsible for the installation, maintenance, and replacement of their customer-owned service lines as needed.  Peoples seeks limited waivers of these tariff provisions, where the customer-owned service lines must be replaced as a result of its Smart Modernization Plan (SMP).

Beginning in 2011, Peoples commenced its SMP program to replace all of its cast iron, unprotected bare steel, and some cathodically-protected steel gas mains – a total of roughly 2,300 miles of pipeline – over a twenty year period, the early years of which have been described and incorporated in Peoples’ LTIIP addressed in this Order.  Cast iron and bare steel mains are the highest risk pipe in Peoples’ system and as such, Peoples intends to replace them with hardened (polyethylene) plastic mains.  In carrying out this main replacement plan, Peoples also intends to replace the adjacent services – a “service” being the section of company owned line extending from the gas main to the curb box at a customer’s property.  Replacement of the services at the same time as replacement of the adjacent gas main is both a prudent and efficient practice, and Peoples estimates doing so to approximately 61,000 services over the span of its 20 year SMP.

The part of the gas line that runs from the curb box to the meter is designated as the customer service line, with the riser being the part of the service line that rises above the ground and connects to the meter.  On Peoples’ system (other than in the cities of Altoona and Johnstown), the customer is responsible for the installation, maintenance and replacement of the customer service line, including the riser.  A bare steel customer service line is subject to the same degrading elements that affect the bare steel gas mains being replaced by Peoples, and hence, Peoples believes that as it replaces its own gas lines and then reconnects and pressure tests the corresponding customer service lines, some will fail the required pressure test and have to be replaced before service can be restored to the customer.  If individual customers would have to bear the responsibility and cost of replacing the customer-owned service lines and risers, it would not be reasonable to expect that the Company would be able to coordinate replacement activities, achieve cost and time efficiencies, and minimize service down times that would otherwise be realized when all replacement activities are coordinated by the Company.

In order to effectively carry out its replacement program, it is necessary for Peoples to replace bare steel customer service lines and any other lines that fail the required pressure test.  Since these failed customer service lines must be replaced in conjunction with main replacements, it is only reasonable for Peoples to pay the cost of replacement.  Therefore, Peoples requests limited waivers of its tariff rules – specifically Rule 4 that governs the installation of customer service lines – to permit Peoples to control the replacement of these service lines and bear the costs thereof.  Peoples avers that the requested waivers are similar to the waivers requested by Columbia Gas of Pennsylvania Inc., at Docket No. P-00072337 and granted by Commission Order entered May 19, 2008.

Peoples states that this request is reasonable since the replacement of the customer service line would be a direct result of a main replacement upgrade program that is beneficial to all of Peoples’ customers in terms of system safety and reliability.  In addition, they state that it would result in lower costs for the replacement program due to the fact that Peoples would be able to coordinate all of the replacement activities, while also not forcing individual customers to replace their service lines when they may not have the financial means to do so.  For these reasons, Peoples proposes to replace all customer service lines, both company and customer-owned, that must be replaced at the time of the main replacement, with the end result being that all customers whose customer service lines must be replaced will be treated equally without regard to whether the customer owns the service line or not.

Peoples plans to capitalize the service line replacement costs, and although Peoples will replace all customer service lines that fail the pressure test at the time of main replacement, Peoples will not take ownership of, or maintain in the future, those customer-owned service lines.

The waivers being requested by Peoples are limited to those customers affected by the main replacement program who own customer service lines that must be replaced.  This limited waiver will not alter the rules regarding a customer’s obligation to replace or repair defective customer-owned service lines unrelated to the main replacement program, or change the duties of customer service line ownership and maintenance after the main replacements are complete.

Comments

The OCA filed an Answer to Peoples’ Waiver Petition in which they substantially agreed with Peoples’ request for limited waivers of certain tariff provisions relative to the replacement of customer-owned service lines.  OCA believes that, by granting the requested waivers, Peoples will be able to efficiently coordinate the replacement and in turn minimize disruptions in service to all of the Company’s customers.  OCA further states that if customers had the responsibility to replace their own service lines they may not have the financial resources to replace the lines when required in conjunction with Peoples’ replacement program and consequently, lose service when the new main for their service line is pressurized.  The OCA is also in favor of Peoples’ plan to hire local plumbers for much of the customer service line work, noting that this will ensure local businesses have the opportunity to participate in the program.

However, the OCA is concerned with the cost recovery implications of Peoples’ proposal.  The OCA does not object to the proposed cost recovery for base rate purposes but they do, however, urge the Commission to consider whether such costs should be recoverable through the DSIC, noting that DSIC-eligible property is limited to “costs incurred to repair, improve or replace eligible property that is part of the utility’s distribution system” per 66 Pa C.S. § 1351.

The OCA also expressed concern with how Peoples intends to handle customers who refuse the Company’s offer to replace their customer-owned service lines.  In such an instance, the OCA recommends that the customer be supplied with information regarding the cost to complete the upgrade himself and a deadline by which the upgrade must be completed.  OCA feels that the customer should be fully informed that they will lose service if the upgrades are not timely implemented, and OCA would be willing to work with Peoples in communicating with its customers about the benefits of Peoples replacing the customer service lines.

I&E filed an Answer to Peoples’ Waiver Petition in which they substantially agreed with Peoples’ request for limited waivers of certain tariff provisions relative to the replacement of customer-owned service lines.  However, I&E’s Gas Safety Division expressed concern that the customer-owned service lines present a safety issue because customers who own their service lines generally are not aware of the location of those lines.  In light of this, if Peoples’ Waiver Petition is granted, I&E recommends that Peoples be required to record the location of the line on their distribution maps, incorporate the risks associated with the service line in its Distribution Integrity Management Program (DIMP), and mark the line pursuant to the Pennsylvania One Call Act.

While I&E does not oppose the tariff relief requested by Peoples, they strongly urge the Commission to grant relief on the condition that Peoples engages in the proper marking and identification of newly-installed customer service lines in accordance with the requirements of PA One Call, and stand ready to identify the location of those lines as a way of satisfying the gas safety concerns previously identified by the Commission.

Resolution

According to Peoples’ existing tariff, certain customers are responsible for the installation, maintenance and replacement of their service lines.  Peoples asserts that it would be inequitable to require these customers to replace their service lines at the customers' expense when the replacement was a result of Peoples’ SMP, and as such, is requesting limited waivers of certain tariff provisions related to customer-owned service lines.  These waivers are "limited" in the sense that the Company will not take ownership of, or maintain in the future, the service lines replaced by Peoples in the areas delineated as customer-owned lines in Peoples’ tariff.  The OCA and I&E agree with Peoples’ request for limited waivers.  The Commission finds that Peoples’ request for limited waivers of the provisions of its tariff should be granted as filed.  We also find that it is in the public interest for Peoples to replace, at its expense, certain customer-owned service lines when the lines must be replaced as a result of the Company’s main replacement and upgrade program.

Peoples further believes that it is proper for the Company's costs to be capitalized, and presumably recouped through rates, because the service line replacements are necessary to complete the project and the project has overall benefits to all Peoples customers.  The OCA expressed concern over whether these costs should be eligible for collection under the DSIC.  The Commission will address this issue later on in the DSIC portion of this Order.

Moreover, the OCA is concerned with how Peoples intends to handle customers that refuse the Company’s offer to replace their customer-owned service lines.  OCA requests that the customer be made fully aware of the implications of not having the service line replaced, and has offered to work with Peoples in communicating to customers the benefits of Peoples providing the replacement of the customer service lines.  We commend OCA in this approach, and urge Peoples to collaborate with OCA in keeping its customers fully and properly informed as to the costs and benefits of their service line replacements.

Additionally, I&E strongly urges the Commission to grant relief on the condition that Peoples engages in the proper marking and identification of newly-installed customer service lines in accordance with the requirements of PA One Call.  The Commission fully supports the intentions of PA One Call, and in doing so, stands in support of I&E in requiring Peoples to properly locate and mark all customer service lines to fully comply with the standards of PA One Call.  Such action will further stand to alleviate the gas safety concerns associated with unmarked gas lines.

PEOPLES’ LTIIP PETITION

Peoples’ Petition

Before the Commission for consideration is the Petition for approval of Peoples’ LTIIP, filed on January 23, 2013.  Act 11 states that as a precondition to the implementation of a DSIC, a utility must file a LTIIP with the Commission that is consistent with 66 Pa. C.S. §1352.

Peoples’ LTIIP is a five year plan.  Peoples stated that it has undertaken a significant distribution evaluation, repair and replacement program that has thus far focused primarily on those portions of its system that were constructed using cast iron mains. This first phase of its long term replacement program is substantially complete, and the Company's LTIIP will now increase replacement of other portions of Peoples' distribution system, particularly replacement of unprotected bare steel pipe.

Peoples stated that as of June 30, 2012, it owns and operates, 780 miles of gathering pipeline, 398 miles of transmission/storage pipeline and 6,690 miles of distribution pipeline.  Within this system, Peoples currently operates 2,325 miles of unprotected bare steel pipeline.  Peoples stated that as of December 2012, it has replaced all 48 miles of its cast iron pipeline as a part of its existing distribution infrastructure replacement program. Utilizing the risk-based analysis incorporated in the Company's pipeline integrity management planning process, Peoples prioritized the 48 miles of cast iron pipe for removal by year-end 2012, as they were both the oldest facilities on Peoples' system and represented the most serious risk of developing leaks.  As a category, unprotected bare steel is Peoples next highest risk pipe.  Peoples intends to focus the majority of its replacement over the next five years on bare steel pipelines.

The removal of all cast iron pipes during 2012 was a component of a comprehensive modernization program initiated by Peoples in mid-2011 as its SMP.  The SMP targets infrastructure replacement, and particularly the removal and replacement of all cast iron, all unprotected bare steel pipeline, some cathodically protected bare steel (Target Pipe) and the company services associated with these types of pipe.  Peoples avers that candidate pipelines will be identified and prioritized for replacement and/or upgrade through a combination of risk ranking, capacity analysis, operating history, and overall reliability.

In General, unprotected bare steel is Peoples' next highest risk pipe, and Peoples’ goal under the SMP is to remove that pipe within 20 years.  Before the SMP and using historical average rates of pipeline replacement, Peoples stated it would have taken approximately 67 years to remove all Target Pipe.  With the SMP’s goal of removing all Target Pipe within 20 years serving as a strategic vision, Peoples has developed this LTIIP to guide the first five years of its accelerated infrastructure replacement.

In addition to addressing cast iron and bare steel mains and company service lines, as part of its SMP, Peoples stated that it must also address the customer service lines that connect to the company service lines.  Peoples avers that it has been replacing bare steel company-owned customer service lines when it replaces its own gas lines if they fail the pressure tests that are required by 49 C.F.R. § 192.725.   Peoples further mentioned that in most of its service territory, service lines are owned and maintained by customers.  However, it would be inefficient for Peoples to have customers replace their failing service facilities at the time the main is being replaced.

Therefore, Peoples sought permission from the Commission in a separate petition at P-2013-2346161 to capitalize the costs associated with its replacement of customer-owned service lines for accounting purposes.  Peoples has indicated that the cost of such replacements will be capitalized to its mains account, just like other customer-owned property such as sidewalks or driveways, when they are replaced as part of main replacement.

# Peoples has also filed a petition at P-2013-2344596 for approval of a DSIC.

# DSIC is a ratemaking mechanism that allows for the recovery of prudently incurred costs related to the repair, improvement and replacement of utility infrastructure through a surcharge on a timelier basis, subject to reconciliation, audit and other consumer protections.

The LTIIP will allow Peoples to replace an average of approximately 47 miles of pipeline per year during the five-year period of the LTIIP.  Further, Peoples plans to spend between $55 million and $71 million per year on pipeline, meter and service replacement, over the five-year period of the plan.

On March 14, 2013, the Commission issued a proposed rulemaking on the LTIIP at L-2012-2317274.  The proposed rulemaking acknowledged the Commission’s decision against establishing a separate Pipeline Replacement and Performance Plan filing process at Docket No. M-2011-2271982, because it would be duplicative of the Act 11 DSIC regulatory process, specifically, the filing of LTIIPs.  The Commission, nevertheless, determined that it would rather order additional actions from NGDCs if necessary, in order to safeguard the public.  The Commission also acknowledged that the implementation of a DSIC mechanism may lead to numerous construction projects by the utilities.  The Commission is aware that these construction projects could lead to significant disruptions as utilities perform work in the right of ways of the roadways and streets across the Commonwealth in order to repair or replace their infrastructure.  Therefore, the Commission has directed, by way of the proposed rulemaking, that a utility, as part of its LTIIP, should provide a description of its outreach and coordination activities with other utilities, Pennsylvania Department of Transportation (PennDOT), and local governments regarding their planned maintenance/construction projects and roadways that may be impacted by the plan.

As a result, the proposed rulemaking added an additional element, thereby increasing the original seven elements in the LTIIP to eight as shown below:

- Types and age of eligible property;

- Schedule for its planned repair and replacement;

- Location of the eligible property;

- Reasonable estimates of the quantity of property to be improved;

- Projected annual expenditures and measures to ensure that the plan is cost      effective;

- Manner in which replacement of aging infrastructure will be accelerated and how repair, improvement or replacement will maintain safe and reliable service;

- A workforce management and training program; and

- A description of a utility’s outreach and coordination activities with other 			utilities, PennDOT and local governments on planned 						maintenance/construction projects.

Peoples’ LTIIP addressed these eight elements as required in the Final Implementation Order of Act 11 and the proposed rulemaking of March 14, 2013, as outlined below.

- TYPES AND AGE OF ELIGIBLE PROPERTY

Peoples’ Petition

Peoples’ distribution system property is summarized thus; 7,868 miles of pipeline, 350,774 service lines and 373,713 meters; of average ages 43 years, 46 years and 32 years respectively.  Within this system, Peoples currently operates 2,325 miles of unprotected bare steel pipeline, at an average age of 69 years old.  The vast majority of Peoples' DSIC-eligible expenditures will be spent on replacing the bare steel pipelines, which are some of the oldest facilities on Peoples' system.  Peoples stated that the main objective of its LTIIP is to improve aging infrastructure in order to reduce system risk and maintain system integrity and safe, adequate and reliable service.  Most of Peoples’ planned improvements are in the area of pipeline and meter replacements.  For example, in 2013, 100% of Peoples projected DSIC-eligible expenditures will be spent on replacing pipelines and meters.  In addition to replacement of pipelines and meters, as part of its infrastructure upgrade, Peoples stated that it will also be replacing customer-owned service lines, and may eventually install automated meter reading systems.  Peoples proposed to replace all Target Pipe, predominantly unprotected bare steel, over a twenty year period.  Peoples asserts that facilities included in its LTIIP are considered "eligible property" under §135 1(2).

Peoples highlighted that its LTIIP also focuses on reducing risk and maintaining safe, adequate and reliable service on facilities that run from its main lines up to and including the meters located at a customer’s home or business, and improving reliability of service.  In view of this, Peoples has proposed to include three areas of “special consideration” within its LTIIP, for which it will be seeking DSIC recovery.  These areas include: 1) customer-owned service lines; 2) reliability improvements; and 3) special meter technology;

- Customer-owned Service Lines:  Peoples indicated that except in the cities of Altoona and Johnstown, the customer is responsible for installation, maintenance and replacement of the customer service lines.  As stated earlier, Peoples’ SMP will be primarily focused on removing unprotected bare steel pipeline and company-owned service lines throughout its system.   Peoples however, indicated that bare steel customer-owned service lines are subject to the same degrading elements that affect the physical integrity of its bare steel mains and Company services.  Peoples, therefore, explains that as it disconnects customer service lines during main replacement and then reconnects and tests those lines, some will fail the pressure test and have to be replaced before service can be restored.   Peoples believes that leaving the individual customers to bear the responsibility and cost of replacement of customer-owned service lines, would hamper its ability to coordinate replacement activities with the customers and may negatively impact cost and time efficiencies.   Therefore, Peoples has proposed in its LTIIP to repair or replace customer-owned service lines that fail the pressure test during main replacement and to include the associated costs as a recoverable item under the DSIC.  Peoples has maintained that it will not take ownership of, or maintain in the future, the customer-owned service lines that are replaced.  Peoples has filed a separate Petition for a waiver for these customer-owned service lines at Docket No. P-2013-2346161 as stated earlier.

- Reliability Improvements:  Peoples stated that reliability improvements are targeted to improve system reliability in distribution areas that may experience low pressure issues, or may have experienced considerable growth over the years.  Peoples identifies these systems as typically having one main pipeline source of supply into an area, thereby presenting a reliability risk in case of an emergency outage within that single delivery path.  To alleviate the constraint and reduce the reliability risk, Peoples would provide an additional delivery path into these systems by looping existing pipelines or extending facilities from higher pressure pipelines.  Peoples is proposing to include such reliability improvement projects as upgrades to existing infrastructure in its LTIIP and to include the associated capital costs as a recoverable item under the DSIC.  Peoples cited a project that it is considering completing this year, to improve the reliability of an area in Butler County.  According to Peoples, this area in its service territory has several thousand residential customers and numerous commercial customers relying on a single feed with limited capacity. The system Reliability Improvement project would be to install a second, high pressure supply feed into this area that would provide an additional supply feed as well as a backup feed of supply in case of failure of the existing feed.

- Special Meter Technology (SMT):  Peoples anticipates that during the term of this LTIIP, the opportunity will arise for it to implement a new metering technology in its system.  Some of the reasons that might warrant this implementation include such Commission requirements as the proposed rule to address unaccounted-for-gas, advances in metering technology, or customer demand for more usage data.  Peoples also anticipates that the metering technology would be an Automated Meter Reading (AMR) technology such as Encoder Receiver Transmitter (ERT).  Peoples stated that it plans to study the deployment of AMR technology during the first two years of the LTIIP.  Based on the study, AMR could be deployed in the 2015-2017 time-frame.  While no specific proposed meter technology program is listed in Peoples’ LTIIP at this time, Peoples has included (in the charts in Appendices 2, 4, and 5) an open space for a Special Meter Technology project to ensure such projects are included in the LTIIP.  Peoples further indicated that it will report the scope of the projects related to a broader scale deployment of AMR technology in its future Annual Asset Optimization Plans (AAO Plans).

Peoples also indicated that it plans to include two areas of investment (information technology support, and vehicles, tools and equipment) in the “Other Related Capitalized Costs” DSIC-eligible plant category in its LTIIP.

- Information Technology Support (ITS):  Peoples stated that soon it will begin to implement a new pipeline bar coding technology. This technology will allow Peoples to track critical information on all individual pipelines and all other required equipment including fittings, valves, couplings, etc.  This means that newly installed pipelines, fittings, valves, couplings, etc. will have bar codes that will contain information such as type of material, date of installation, location coordinates, pipeline manufacturer, installer, inspector, and many other pieces of pertinent data that can be tracked and accessed on an ongoing basis.   The ITS system is anticipated to be completed in 2014.  Peoples has stated that there is no cost estimate for this system yet because the assessment is still ongoing.

- Vehicles, Tools and Equipment:  Peoples further indicated in the LTIIP that its accelerated pipeline replacement program will require the purchase of additional general plant equipment in support of expanded field operations crews.  This equipment will include trucks, backhoes and trailers, line locating and leak detection equipment, and other related tools and equipment.  Peoples stated that it will only seek to recover via DSIC the capital spent in this category that is directly associated with DSIC projects and incremental to what was recovered in Peoples’ most recent rate case proceeding.

Comments

OCA had specific comments regarding Peoples’ DSIC-eligible plant items.  Below is a listing of some of OCA’s comments regarding specific DSIC-eligible properties.

- Meter: OCA requests that Peoples specify whether it plans to accelerate relocation of inside meters to outside, if needed, as part of its replacement strategy, as this information will help the Commission to review the effectiveness of Peoples’ plan.

- Customer-Owned Service Lines: OCA avers that the separate petition of Peoples for Limited Waivers of Certain Tariff Rules Related to Customer Service Line Replacement (Waiver Petition) at Docket No. P-2013-2346161 does not specifically address recovery of replacement costs for these lines through DSIC but only addresses the limited waiver of tariff rules to enable Peoples to capitalize the upfront cost to replace the relevant customer-owned service lines.  OCA, therefore, requests that Peoples’ proposal to recover the costs of replacing customer-owned service lines be more fully examined in the Tariff Waiver Petition or Peoples’ current DSIC filing and not in the LTIIP filing.

- Reliability Improvements:  In line with Peoples’ description of reliability improvements, OCA recommends that Peoples should address these types of projects through its normal capital planning process and recover the associated costs through its base rates and not through DSIC.  OCA argues that the potential reliability problem described by Peoples does not appear to be linked to concern over a particular pipe material type and risk of failure in the field but appears to be related to ongoing, routine operational planning for system growth and so should not be classified as DSIC-eligible property.

- Special Meter Technology: As with the reliability improvements, OCA opines that Peoples’ proposal to include special meter technology does not appear to fall within the scope of the projects to accelerate the replacement of aging infrastructure.  OCA further argues that the benefits of AMR technology outlined by Peoples are not within the purpose of DSIC and so any consideration for this form of advanced metering should be addressed in a separate proceeding that considers the costs and benefits of such a proposal.

- Information Technology Support: OCA argues that similar to the AMR technology deployment plan, Peoples described an innovation in field technology that may bring benefit but does not appear to be related to the accelerated replacement of aging infrastructure, which is the intended purpose of the DSIC.  Therefore, OCA submits that Peoples has not demonstrated that improvements to its existing capital management system should be recovered through a surcharge intended to allow the utility to accelerate the replacement of aging infrastructure rather than through base rates as part of its normal capital planning process.

- Vehicles, Tools and Equipment:  Peoples also included in its LTIIP, plans to purchase additional general plant equipment including trucks, backhoes, trailers, line locating and leak detection equipment and other related tools and equipment as part of its expanded field operations crews.  Peoples, however, seeks to only recover the capital spending that is directly associated with DSIC projects and incremental to the most recent base rate proceeding.  OCA requested the Commission to fully examine these costs since it is not clear that these equipment costs are eligible distribution system plant that may be included in the LTIIP and recovered through DSIC.

Resolution

In response to OCA’s concerns, Peoples provided specific information on each item listed below.  The Commission will address each of these concerns and make appropriate resolutions.

Meter:  In response to OCA’s concerns about Peoples’ plans to relocate inside customer meters, Peoples averred that there is no formal planned program to relocate inside meters outside.  Peoples indicated that during pipeline replacements, if encountered, it will recommend to the customer to relocate the meter to the outside.  66 Pa. C.S. § 1351(2)(viii) identifies meters as “DSIC-eligible property.”  Therefore, based on Peoples response to OCA’s concern on meter relocation, if relocations are made, we deem it adequate to approve such meters as DSIC-eligible property.

Customer-Owned Service Lines:  The Commission acknowledges OCA’s concerns regarding Peoples’ proposal to include service line work in its LTIIP and the description of the costs associated with customer-owned service lines as DSIC-eligible assets.  This Order combines the Waiver Petition, LTIIP, and DSIC proceedings.  We have already addressed the Waiver Petition as stated earlier in the Order.

Section 1352 of the Public Utility Code specifically requires a utility to submit a LTIIP for Commission approval in order to qualify for DSIC recovery.  This provision ensures that quarterly DSIC repairs, improvements, and replacements to eligible property are made consistent with a LTIIP that has been approved by the Commission through careful examination.

Peoples proposed to include customer-owned service lines in its LTIIP.  In particular, Peoples proposed to capitalize costs associated with the replacement of customer-owned service lines as part of its accelerated main replacement program.  This is consistent with Peoples’ Waiver Petition at Docket No. P-2013-2346161.  The Commission has approved Peoples’ petition to pay for the cost of replacing customer-owned service lines and to capitalize those costs.  Thus, we find that Peoples’ plan to coordinate customer-owned service line replacement along with its main replacement plans is reasonable, and that Peoples’ LTIIP is the logical vehicle for such coordination.  OCA asserts no reason to prohibit Peoples from addressing customer-owned service lines in its LTIIP other than the fact that it should have been addressed in the Waiver Petition or the DSIC filing.

OCA is concerned that Peoples’ inclusion of the customer-owned service lines in its LTIIP would lead to classification of the costs associated with customer-owned service lines as DSIC-eligible assets.

We conclude that such concerns do not warrant exclusion of the customer-owned service lines from Peoples’ LTIIP, especially since it is reasonable to include this work as part of Peoples’ overall infrastructure improvement plans and because customer-owned service line costs can now be capitalized by Peoples pursuant to the above Waiver Petition Order.  The LTIIP is a comprehensive planning document which may encompass more than what may be recoverable via the DSIC mechanism.  Act 11 requires that, for costs to be DSIC-eligible, the work underlying those costs must have been set forth within the utility’s LTIIP; however, it does not specify that all work and associated costs will be be DSIC-recoverable or that inclusion of such work would warrant rejection of the LTIIP.

Accordingly, we will approve the inclusion of customer-owned service lines as part of their LTIIP.  Inclusion in the LTIIP does not necessarily qualify customer-owned service lines, or any other expenditure, as DSIC-recoverable property.  We will address the issue of DSIC recovery in the DSIC portion of this Order.

Reliability Improvements:  Peoples indicated that the request for reliability improvements in the LTIIP was based on its experience with pipeline replacement.  The reliability improvements are targeted towards areas that may experience low pressure. These areas typically have one main pipeline source of supply into the area and may be a reliability risk in case of emergency.  Peoples gave an example of a reliability improvement project it is considering completing this year in Butler County, that would provide an additional supply feed as well as a backup feed of supply in case of emergency outage.  Peoples considers it prudent to include such projects as DSIC-eligible property in the LTIIP.  This is in line with the reasoning that this will potentially reduce outages on such systems and increase reliability of their infrastructure.

OCA argues that the potential reliability problem described by Peoples does not appear to be linked to concern over a particular pipe material type and risk of failure in the field but appears to be related to ongoing, routine operational planning for system growth and so should not be classified as DSIC-eligible property.

As we stated in our Final Implementation Order, “…the DSIC mechanism was granted to fixed utilities so that they could repair and replace their existing infrastructure….necessary upgrades to existing infrastructure serving existing customers…will be considered a DSIC-eligible project. See Final Implementation Order at 23-24.  This is in line with the reasoning that this will potentially reduce outages on such systems and increase reliability of their infrastructure.

Based on Peoples response on reliability improvements, we believe that upgrading existing facilities such as providing extra feed sources to areas that have limited capacity will decrease the likelihood of failure, thereby increasing reliability of their infrastructure.  Accordingly, we believe that any reliability improvements performed by Peoples as part of a planned repair and replacement project should be rightfully included in its LTIIP.

Special Meter technology:  Peoples anticipates that during the term of this LTIIP, the opportunity will arise for it to implement a new metering technology in its system.  Peoples states some of the reasons that might warrant this implementation include the establishment of Commission requirements addressing unaccounted-for-gas, advances in metering technology or customer demand for more usage.  Peoples also anticipates that the metering technology would be an Automated Meter Reading (AMR) technology such as Encoder Receiver Transmitter (ERT).  Peoples has stated that it plans to study the deployment of AMR technology during the first two years of the LTIIP and based on this study, AMR could be deployed in the 2015-2017 time-frame.  Thus, Peoples has no specific proposed meter technology program listed in its LTIIP at this time.

As with the reliability improvements, OCA opines that Peoples’ proposal to include special meter technology does not appear to fall within the scope of the projects to accelerate the replacement of aging infrastructure.  OCA asserts that the benefits of AMR technology outlined by Peoples are not within the purpose of DSIC and so any consideration for this form of advanced metering should be addressed in a separate proceeding that considers the costs and benefits of such a proposal.

We disagree with OCA’s strict reading of Act 11.  The Commission determines that improvements that are done to existing infrastructure fall within the scope of DSIC recovery and should be included in a utility’s LTIIP.  Act 11 contemplates the recovery of costs related to the repair, improvement and replacement of eligible property.  See 66 Pa. C.S. §§ 1350 and 1353 (Emphasis added).  Meters are defined as eligible property for NGDCs.  66 Pa. C.S. § 1351.  Thus, the improvement to existing distribution infrastructure by a utility in order to maintain safe, adequate and reliable service, even if such improvements have been instituted to meet new requirements established by us, can be included in the LTIIP.  The impetus of Peoples’ proposal to implement new metering technology throughout its distribution system is to address unaccounted for gas issues and other demands.  As this upgrade will result in an improvement to Peoples’ existing distribution system, we believe that Peoples’ proposal to implement AMR is within the scope of Act 11 and should be included in Peoples’ LTIIP.

Information Technology Support: Peoples has stated that it expects to implement this technology in 2014.  Peoples opines that this technology will be associated with newly installed pipelines, fittings, valves, couplings, etc.  While we acknowledge OCA’s position on including ITS in the LTIIP, the Commission believes that the introduction of this technology during pipeline improvement related projects are upgrades to existing infrastructure.  Accordingly, the Commission believes these upgrades will improve the reliability of Peoples’ service to customers.  Therefore, we approve ITS in Peoples’ LTIIP.

Vehicles, Tools and Equipment:  Peoples also indicated in the LTIIP that its accelerated pipeline replacement program will require the purchase of additional general plant equipment in support of expanded field operations crews.  This equipment will include trucks, backhoes and trailers, line locating and leak detection equipment and other related tools and equipment.  Peoples stated that it will only seek to recover via DSIC the capital spent in this category that is directly associated with DSIC projects and incremental to what was recovered in Peoples’ most recent rate case proceeding.  However, OCA requested the Commission to fully examine these costs since it is not clear that these equipment costs are eligible distribution system plant that may be included in the LTIIP and recovered through DSIC.

On April 8, 2013, Peoples filed a response clarifying the inclusion of these DSIC-eligible properties in its LTIIP.  Peoples avers that while these units are incremental to its current fleet inventory, the additional vehicles purchased, and equipment acquired may not always be assigned to DSIC projects, nor will they be the only vehicles in the fleet or equipment supporting DSIC-eligible projects.  Peoples has indicated that its accounting procedure allocates a pro rata portion of the costs (maintenance/license fees/depreciation, etc.) of vehicles and equipment to capital and expense based upon project use.  Hence, if a vehicle (existing or newly purchased) is used for a repair project, the cost will be charged to expense.  If the vehicle is used for a capital project, the cost will be charged as part of the overhead for the capital project.  If the capital project is a DSIC-eligible project, then the costs of the vehicle and equipment will be capitalized as overhead as part of the DSIC-eligible project.

In line with Peoples’ explanation and clarification on the need to include vehicles, tools, and equipment in its LTIIP, the Commission notes the use of the term “other related capitalized costs” in the definition of eligible property in Act 11.  See 66 Pa. C.S. § 1351.  More importantly, the Commission believes that the inclusion of these DSIC-eligible properties will encourage the acceleration of infrastructure upgrades by Peoples.  Therefore, we approve these DSIC-eligible properties in Peoples’ LTIIP.

Upon review of Peoples’ LTIIP and all supplemental information and explanations filed, the Commission finds that the requirements of element one of the Final Implementation Order of Act 11, types and age of eligible property, has been fulfilled.

- SCHEDULE FOR PLANNED REPAIR AND REPLACEMENT OF ELIGIBLE PROPERTY

Peoples’ Petition

Peoples plans to replace all Target Pipe, predominantly unprotected bare steel, over a 20-year period.  According to Peoples, the focus for the first 10 years of the program includes high pressure distribution and transmission pipelines and major distribution trunk lines and critical single feed dead-end pipelines.  Replacement of these lines will decrease the likelihood of failure and minimize customer impacts if such failures were to occur.  Peoples also states that for the first few years of the LTIIP, it is placing a high priority on its higher pressure distribution mains and transmission system.  Peoples avers that these pipelines are critical to maintaining reliable service to large numbers of customers throughout its system.  Peoples avers that it has removed an average of 13,350 meters per year during the five year period from 2007 through 2011, and expects to maintain a similar replacement rate during the term of its LTIIP.

Peoples provided a schedule in the LTIIP (Schedule 2-A in Appendix 2), showing the strategies employed for the planned repair and replacement of DSIC-eligible plant during the 5-year period covered by the LTIIP.  This schedule is based on an analysis of equipment failures, their nature, causes, locations, analysis of reliability performance indicators, and forecasts of future reliability concerns, all in consideration of and consistent with Peoples Distribution Integrity Management Plan (DIMP).

Peoples stated that the schedule for repair and replacement of plant during the 5-year period covered by the LTIIP reflects and maintains an acceleration of infrastructure replacement over Peoples historical level of capital improvement.

Comments

In its Comments, OCA indicates that Peoples has set a goal to remove all Target Pipe within the next 20 years.  However, Peoples did not specify why a 20-year replacement time-frame for Target Pipe was selected as being appropriate to provide and maintain safe and adequate service.  OCA further calls for Peoples to provide the Commission with the results of the risk assessments for mains and services and/or any applicable program reports, particularly the parameters Peoples selected when it conducted its analysis, leak histories, and other scoring systems considered by its engineering department.   OCA also requested that Peoples provide any outside reports from third-party consultants or engineers regarding its distribution system capital replacement or expansion that support the approach chosen for its replacement program.

OCA also requested Peoples to provide leak histories for the projects identified for replacement in 2013 and basic performance information for Peoples’ system, such as leak rates per 1,000 services by material type or leaks per mile of main by pipe material type, and a breakdown of the LTIIP projects showing pipe materials grouped by diameter.

Resolution

In response to OCA’s request, Peoples stated that while it did not perform a study to set the term of its accelerated pipeline replacement program, the management decision to propose a 20-year term balances the overall goal to accelerate its replacement of Target Pipe with the counterweighing goals of avoiding rate shock and attracting a sustainable basis of the level of capital needed to accomplish main replacements.   Peoples believes that DSIC will allow it to attract additional capital to accelerate the replacement in order to continue safe and reliable operation in the future.  Peoples also indicated that absent the accelerated main replacement program, it would have taken over 67 years to replace all unprotected bare steel pipelines in the system.

Peoples also indicated that it does not use the Incident Cause Analysis Method/Data (ICAM/D) analysis, but its risk analysis program is a proprietary company-developed model, which includes risk and consequence considerations.  According to Peoples, the model incorporates leak history, population, customer location, other utilities, and physical features into the algorithm to risk rank the pipeline section for replacement.  Based on the risk model, pipeline segments are prioritized for replacement, and the projects included for the first year of the LTIIP were the highest priority identified by the risk analysis program for the geographic area considered.  No other scoring systems or outside reports from third-parties or engineers were considered.

Peoples also provided information on leak rates per 1,000 services by material type or leaks per mile of main by pipe material type.  Peoples stated that in 2012, it completed 739 leak repairs which equates to 0.09 leak repairs per mile of pipe and 2.1 leak repairs per 1000 customers.

Upon review of Peoples’ LTIIP and all supplemental information and explanations filed, the Commission finds that the requirements of element two of the Final Implementation Order, schedule for planned repair and replacement of eligible property, has been fulfilled.

- LOCATION OF ELIGIBLE PROPERTY

Peoples’ Petition

Peoples identified two major categories of distribution plant to be replaced (pipes and meters).   Peoples is targeting pipeline replacement in each of its eight operating districts over the 20-year term of the SMP.  These districts are Altoona, Johnstown, Greensburg, Southern, Kiski/Valley, Gibsonia/Grove City, Hopewell, and Wilkinsburg/Pittsburgh.  Table 1 below shows the percent of pipeline that has been identified for replacement in each operating district as a percentage of the pipeline in that district.  Table 1 also shows pipe to be replaced in each district compared to total pipe system-wide.

As shown in Table 1, the pipe to be replaced in each district compared to the total pipe in the district ranges from 20 percent (Hopewell) to 39 percent (Kiski/Valley), with replacements in any given district based upon a risk-based approach.  Table 1 also shows that replacements in Kiski/Valley represent the highest percentage, at 25 percent, of the total pipe to be replaced in Peoples’ system.

Customer meters will be replaced throughout Peoples’ service territory based on a statistical, risk-based methodology.  As such, the replacement meter locations are undetermined at this point.  Peoples, however, provided a chart which depicts the number of customers by county to best illustrate where the customer meters are located (page 19 of the LTIIP).  Based on this chart, as of December 12, 2011, a majority of the meters are located in Allegheny County (148,261 customers) while the least number of meters is located in Clarion County (53 customers).

Table 1: Location of Eligible Pipeline Property

| District | Total Miles | Target Miles | % of District Target Miles as a % of Total | Target District Miles as a % of Total Company Target Miles |
| --- | --- | --- | --- | --- |
| Altoona | 540 | 184 | 34% | 8% |
| Johnstown | 569 | 214 | 38% | 9% |
| Greensburg | 1,269 | 261 | 21% | 11% |
| Southern | 951 | 343 | 36% | 15% |
| Kiski/Valley | 1,488 | 574 | 39% | 25% |
| Gibsonia/Grove City | 1,373 | 336 | 24% | 14% |
| Hopewell | 620 | 121 | 20% | 5% |
| Wilkinsburg/Pittsburgh | 1,058 | 291 | 28% | 13% |
| Total Company | 7,868 | 2,325 | 30% | 100% |

Comments

No comments were received regarding the location of eligible property.

Resolution

Upon review of the LTIIP, the Commission finds that element three, the location of eligible property requirement, of the Final Implementation Order has been fulfilled.

- REASONABLE ESTIMATES OF THE QUANTITY OF PROPERTY TO BE IMPROVED

Peoples’ Petition

Historically, Peoples replaced an average of 33 miles of pipeline per year  (2007 through 2011).  Peoples expects to replace approximately an average of 55 miles of pipeline during each of the five years (2013-2017) covered by the LTIIP.  Peoples has stated that the consistent rate over this period allows for more uniform staffing and project management, which promotes efficiency and cost effectiveness.  Peoples also expects that the customer-owned service line and reliability improvement project quantities will remain constant over the 5-year period.  In addition, Peoples will replace approximately 12,000 meters per year over the five years the period of the LTIIP compared to an annual average of 13,350 meters for the 2007 to 2011-period.  Table 2 below shows the projected miles of pipeline to be replaced annually, the annual number of company-owned service lines to be replaced, and annual meter replacements by Peoples.

Table 2: Peoples 2013-2017 Reasonable Estimates of the Quantity of Property to be

Improved.

| Category | 2013 | 2014 | 2015 | 2016 | 2017 | 5 Year Total |
| --- | --- | --- | --- | --- | --- | --- |
| Pipeline Replacement (miles) | 38 | 45 | 52 | 70 | 70 | 275 |
| Company-Owned Services-# | 2,800 | 4,200 | 4,600 | 4,600 | 4,600 | 20,800 |
| Customer-Owned Services-# | 500 | 0 | 0 | 0 | 0 | 500 |
| Meter Replacement | 12,000 | 12,000 | 12,000 | 12,000 | 12,000 | 60,000 |

Comments

No comments were received regarding the quantity of property to be improved.

Resolution

Upon review of the LTIIP, the Commission finds that element 4, the reasonable estimates of the quantity of property to be improved requirement, of the Final Implementation Order has been fulfilled.

- PROJECTED ANNUAL EXPENDITURES AND MEASURES TO ENSURE THAT THE PLAN IS COST EFFECTIVE

Peoples’ Petition

Peoples anticipates spending between $56.5 million and $71.0 million per year over the five-year period of the LTIIP.  Peoples has adopted several controls that it will implement to ensure that its infrastructure improvement expenditures are cost effective.  These controls include:

- Utilize computer modeling and simulations to determine optimal pipe size    for cost and reliability.

- Prepare optional designs that utilize different amounts of in-house and         outside contracting to relative expenses.

- Utilize competitively bid, blanket contracts to lock in most favorable pricing for multiple years.

- Utilize unit-based contracts to minimize change order variances.

- Utilize competitive bidding for individual, larger projects that are not covered by blanket contract.

- Negotiate locked-in prices with materials suppliers.

- Utilize on-site inspectors to monitor and verify all quantities that impact project cost.

- Established process requiring internal review of contractor invoices in comparison to as-built data to ensure accuracy of all invoices before payment.

- Established procedures for periodic internal audit of project activities and costs.

- Established procedures for project reporting that utilizes multiple data sorting options so reports can be made by, for example and not limited to, individual project, by type of activity, by year, by shop, and by contractor.

Peoples stated that in addition to the controls and procedures established to ensure cost containment, Operations Management will review cost reports on a regular basis to understand the ongoing costs being incurred.  These cost reports include statistics such as costs per foot, costs per service line replacement, costs per meter replacement and other relevant data.  Further, Peoples will coordinate construction activities with other utilities, agencies and local municipalities that may be planning their own sewer, water and paving projects.  This will result in costs sharing between entities when their projects overlap.  Peoples also indicated that it will benefit from a Shared Service Company with Peoples TWP.  According to Peoples, the service company organizational structure will enable it to incorporate best practice purchasing strategies and encourage more efficient and consistent operational practices, procedures and controls that will drive cost containment.  Furthermore, Peoples believes that replacing customer-owned service lines at the same time as unprotected bare steel mains will help it achieve cost and time efficiencies and minimize service downtime associated with replacement activities.

Table 3: Peoples Projected Annual LTIIP Budget 2013-2017 ($ Millions)

| Year | 2013 | 2014 | 2015 | 2016 | 2017 | 5 Year Total |
| --- | --- | --- | --- | --- | --- | --- |
| Projected Annual Budget | $71.0 | $56.5 | $60.8 | $63.8 | $65.5 | $317.6 |

Comments

In its Comments, OCA avers that in July 2012, Peoples and Peoples TWP formed a service company organizational structure as per the approval of the development of the Service Company by the Commission at Docket Nos. G-2012-2290014 and G-2012-2290018.  Peoples had mentioned in its LTIIP that it will use the Service Company to incorporate best practice strategies and to encourage more efficient operational practices, procedures and controls to improve cost containment.  Peoples also highlighted that the practices will include a more streamlined project design, engineering and management for a more efficient construction cycle and to provide economies of scale.

OCA therefore called for Peoples to provide more information on Peoples’ anticipated streamlined project design, engineering and management structure to ensure that costs are appropriately allocated between the companies and to ensure that the coordination of replacements is efficient and cost-effective.

Resolution

In response to OCA’s concerns, Peoples indicated that the benefits from the Service Company structure in support of the DSIC programs are in Procurement and Engineering Design.  Peoples emphasized that managing the combined procurement and supply chain functions through the Service Company for both Peoples and Peoples TWP will result in a more efficient and cost effective purchasing of DSIC project materials such as pipes, fittings, and meters.  Peoples explained that the procurement of these materials for the combined companies will reduce unit costs through increased economies of scale associated with bulk purchasing.  Peoples also expects cost efficiencies in the contractor service area.  Peoples indicated that most of the DSIC project work for Peoples and Peoples TWP will be performed through contractor services which will be contracted on a combined basis through the Service Company structure.

Peoples believes this will lower the overall contractor costs that Peoples and Peoples TWP will incur as separate companies.  Peoples also indicates that the Service Company structure will result in more efficient management of the planning, design, and engineering work for DSIC projects.  It will also allow for consistent application of planning and design work and result in a more effective coordination and scheduling of construction activities with other utilities, local municipalities, and government authorities.

Upon review of Peoples’ LTIIP and all supplemental information and explanations filed, the Commission finds that the requirements of element five of the Final Implementation Order, projected annual expenditures and measures to ensure that the plan is cost effective, has been fulfilled.

- ACCELERATED REPLACEMENT AND MAINTAINING SAFE AND RELIABLE SERVICE

Peoples’ Petition

The Commission’s Final Implementation Order noted that utilities should reflect and maintain acceleration of infrastructure replacement.  Utilities that have already taken substantial steps towards increasing capital investment to address the issue of aging infrastructure needed to reflect in their LTIIP how the DSIC will maintain or augment acceleration of infrastructure replacement and prudent capital investment.

Peoples implemented its SMP in 2011, which accelerated its distribution infrastructure replacement compared to historical spending.  Peoples' goal under its SMP was to first remove all of the cast iron mains on its system, then to remove all unprotected bare steel pipe within 20 years.  Before the SMP and using historical, average rates of pipeline replacement, it would have taken approximately 67 years to remove all Target Pipe. Consistent with the Commission's order, Peoples' LTIIP continues this accelerated pace.  Peoples began to accelerate infrastructure replacement in 2011 and completed the cast iron replacement project in 2012.  Peoples will begin the bare steel pipe replacement component of the 20 year SMP in 2013.  Prior to the accelerated program, Peoples replaced approximately 33 miles of distribution pipeline per year.  As a result of the accelerated program and the LTIIP, the estimated pipeline replacement will cover 55 miles of distribution pipeline.

During the period 2007 through 2011, Peoples’ average annual capital expenditure for DSIC eligible plant was $29.7 million.  During 2012, Peoples’ DSIC eligible capital expenditure was $78.3 million.  Peoples intends to spend $71.0 million in the first year of the LTIIP.  This is a 139 % increase over the average amount spent during the historic 2007 through 2011 period. The slight decrease in miles of distribution mains replaced in 2013 is a result of the Company's focus on replacing higher cost, larger diameter high pressure transmission mains.  Peoples stated that during the five-year period of the LTIIP (2013 to 2017), it will increase its capital investment by 108% percent over the historic five-year period from 2007 to 2011.

Peoples believes that the repair, improvement, and replacement of aging distribution equipment and facilities will reduce the number of gas leaks as pipe replacement occurs.  The customer-owned service lines and meter replacement component of the LTIIP is also expected to reduce leakage and unaccounted-for-gas.  Peoples indicated that these savings will be reflected in future purchased gas cost rates and transportation retainage rates.  But most importantly, Peoples believes that the LTIIP will help provide safer and more efficient service to customers.  Table 4 below shows the historical main replacement by Peoples and the projected main replacement in the LTIIP.

Table 4: Peoples Historical (2007-2011) Compared to LTIIP replacements.

| Category | 5-year Avg. (2007-2011) | 2012 Projected | 2013 Est. | 2014 Est. | 2015 Est. | 2016 Est. | 2017 Est. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Pipelines Replacement(miles) | 38 | 84 | 38 | 45 | 52 | 70 | 70 |
| Company-owned Services Lines (#) | 2,275 | 6,000 | 2,800 | 4,200 | 4,600 | 4,600 | 4,600 |
| Meter Replacement(#) | 13,621 | 8,000 | 12,000 | 12,000 | 12,000 | 12,000 | 12,000 |

Comments

In its comments, OCA states that if upgrades to Peoples’ system will add capacity, Peoples should specify by what amount capacity will increase or how the additional capacity will be used and useful in the provision of utility service.  According to OCA, if the plant is not currently used and useful in the service to customers, then it should be classified as plant held for future use rather than charged to customers through the DSIC.  OCA therefore, suggested that Peoples provide a breakdown of its LTIIP projects to show pipe diameter of the current and replacement pipe so that increased capacity can be evaluated.

OCA also indicated that on a going-forward basis, for each main project that increases system pressure or is not a ‘like-for-like” pipe diameter replacement, the Commission should have Peoples provide the results of system network analysis before and after the segment installation to confirm that the project(s) is DSIC-eligible.

Resolution

Peoples stated that for the first year of the LTIIP, all pipeline projected to be replaced is unprotected bare steel.  For later years, it is estimated that at least 95 percent of the pipes to be replaced annually will be bare steel pipelines.  According to Peoples, the only instances where coated steel or plastic pipelines are anticipated to be replaced during the five year period covered by the LTIIP would be for government mandated relocations (highway, road construction, etc.), third party damages, or service interruptions.

In response to OCA’s concern regarding Peoples reporting on system network analysis before and after DSIC-eligible projects, the Commission believes that there are sufficient consumer protection mechanisms in place at the Commission to address such concerns.  Section 1356 requires a utility with an approved DSIC to file an AAO Plan.  The elements of an AAO Plan include (1) a description of all eligible property repaired, improved and replaced in the preceding 12 months and (2) a detailed description of all facilities to be improved in the upcoming 12 months.  Also, the AAO Plan is expected to demonstrate compliance in meeting the LTIIP and to identify a utility’s near-term construction projects that will be funded by the DSIC, consistent with the LTIIP.  The Commission’s Bureau of Audits also conducts periodic review of DSIC related projects.

Therefore, the Commission concludes that, while it will not specifically require Peoples to submit results of system analysis network before and after the segment installation to confirm DSIC eligibility of related projects, OCA’s concern will be addressed through the AAO Plan review and through other various Commission reviews of DSIC-related projects.

Upon review of Peoples’ LTIIP and all supplemental information and explanations filed, the Commission finds that the requirements of element six of the Final Implementation Order, manner in which replacement of aging infrastructure will be accelerated and how repair, improvement or replacement will maintain safe and reliable service, have been fulfilled.

- WORKFORCE MANAGEMENT AND TRAINING PROGRAM

Peoples’ Petition

Peoples’ workforce is comprised of both employees who work directly for Peoples, and the workers who are hired by contractors of Peoples.  Peoples is continuously involved in workforce planning and has developed a workforce management and training plan to ensure that it will have access to a qualified workforce to perform work in a cost-effective, safe, and reliable manner.  Peoples indicated that it has identified two areas in gas operations with the potential for both turnover due to an aging workforce and increased work due to pipeline replacement.  Those two groups are the bargaining unit field workers and gas operations front-line supervisors.  To address these areas and other future needs, Peoples has taken steps to increase its ability to hire and/or promote employees with the required knowledge and skill sets during the next two years that it anticipates the greatest amount of turnover.

One way Peoples plans to address this issue is by collaborating with Three Rivers Workforce Investment Board (TRWIB), Peoples, Columbia Gas and Equitable Gas, collectively to offer a natural gas pipeline training program at Community College of Allegheny County (CCAC).  This training is a 60-hour program that will provide students with an introduction to the gas industry and cover topics such as natural gas basics, pipeline maintenance, line locating and OSHA Safety.  The goal of the program is to graduate interview-ready candidates.

Peoples has also participated in a variety of industry community outreach programs to recruit and train potential employees, including the natural gas pipeline training program at CCAC and the Allegheny Conference Workforce Initiative.  In addition, Peoples works with local trade schools, veterans’ organizations, and other community organizations to inform skilled workers of employment opportunities with Peoples.

Furthermore, upon hiring, Peoples provides a training program to ensure that its employees are capable of doing field work.  Peoples also has procedures to ensure that DSIC-eligible work is performed by qualified personnel, specifically through an extensive Operator Qualification Program under which the Safety and Training Department is responsible for re-qualifying one-third of the Operations workforce each year.

On the use of contractors, Peoples avers that it continually verifies ongoing contractor compliance with respect to safety requirements by subjecting contractors and subcontractor employees to qualification according to the provisions of Peoples’ Operator Qualification Rule, which governs Peoples’ own operations.  Contractors must also provide Peoples with written evidence of their qualification programs.  On a quarterly, basis, a contractor is required to submit a list of qualified individuals that also identifies the covered tasks the individuals are qualified to perform.  In addition, contractor work is inspected by Peoples personnel trained in all aspects of pipeline construction.  Inspectors verify that work methods adhere to established standards.  Inspectors will also verify quantities and quality of installations prior to invoice payment.

Comments

No comments were received regarding the quantity of property to be improved.

Resolution

As part of the planning for DSIC projects, a utility may experience the need for increased workforce, internal and contractor.  Utilities should be able to identify the projected number of jobs (or full-time equivalents) that are expected to be created through specific replacement projects.  When a utility submits its information on the eligible projects, it should supply the number of anticipated new jobs to be created by those projects.  When the DSIC funds are audited for annual reconciliation, the utility should be able to provide actual numbers for the jobs created due to specific replacement projects.

Upon review of Peoples’ LTIIP, the Commission finds that the requirements of element seven of the Final Implementation Order, a workforce management and training program, have been fulfilled.

- DESCRIPTION OF OUTREACH AND COORDINATION ACTIVITIES WITH OTHER UTILITIES, PENNDOT AND LOCAL GOVERNMENTS ON PLANNED PROJECTS

Peoples’ Petition

Peoples indicated that it will coordinate construction activities with other utilities, agencies and local governments that may be planning their own sewer, water and paving projects.  As part of such planning, Peoples will routinely review planned projects with PennDOT to identify and coordinate highway reconstruction projects and work with local governments to project and coordinate paving schedules with its construction projects along common streets.  Peoples will also exchange project lists with other utilities to identify potential overlap projects where both companies may be able to coordinate activity and share in restoration costs.

Comments

In its comments, OCA acknowledged Peoples’ plans to coordinate construction activities with other utilities, PennDOT, agencies, and local municipalities that may be planning sewer, water and paving projects.  However, OCA requests Peoples to coordinate with other local natural gas distribution utilities, given the several overlapping gas distribution mains in the area served by Peoples.  OCA further suggests that Peoples provide further information in this regard to ensure an efficient and cost-effective main replacement program.

Resolution

In response to OCA, Peoples stated that it plans to share replacement projects with other public utilities (including local natural gas distribution utilities in overlapping service territories), local municipalities, government authorities, PennDOT, etc. to coordinate construction activities with these entities.  Peoples further stated that it has also reached out to the larger municipalities (or the engineering firms that represent them) in the service territory to request annual paving schedules to cross reference potential pipeline replacement projects.  Peoples indicated that most municipalities typically provide these schedules in the March/April timeframe once their final budgets are passed.  According to Peoples, its operations personnel and Peoples operations personnel have developed an action plan to accomplish these objectives and are implementing the plan.

Upon review of Peoples’ LTIIP and all supplemental information and explanations filed, the Commission finds that the requirements of element eight of the Final Implementation Order, a description of a utility’s outreach and  coordination activities with other utilities, PennDOT and local governments on planned maintenance/construction projects, have been fulfilled.

LTIIP SUMMARY

The Commission has reviewed each of the eight required elements of Peoples’ Petition for Approval of its LTIIP individually and has taken into account the comments received on this petition.  We have determined that customer-owned service lines may be included in the LTIIP as eligible-property, in addition to addressing the other issues identified in element one of the Final Implementation Order ‒ types and age of eligible property.

While the Commission’s Final Implementation Order stated, at page 18, that the LTIIP “need only address the specific property eligible for DSIC recovery,” the inclusion of arguably non-DSIC-eligible property does not void the LTIIP application, nor is the inclusion of such property in the LTIIP dispositive of whether the cost of that project will be afforded DSIC recovery.  The issues of eligibility and cost recovery, for all property claimed as DSIC-eligible, are to be addressed and resolved in the subsequent DSIC petition and calculation.  Accordingly, Peoples’ LTIIP is approved.

PEOPLES’ DISTRIBUTION SYSTEM IMPROVEMENT CHARGE PETITON

Section 1353 requires utilities to file a petition seeking approval of a DSIC that includes the following:

- An initial tariff that complies with the Model Tariff adopted by the Commission, which includes:

  - A description of eligible property;

  - The effective date of the DSIC;

  - Computation of the DSIC;

  - The method for quarterly updates of the DSIC; and

  - A description of consumer protections.

- Testimony, affidavits, exhibits, and other supporting evidence demonstrating that the DSIC is in the public interest;

- A Long Term Infrastructure Improvement Plan (LTIIP) as described in Section 1352, 66 Pa. C.S. § 1352;

- Certification that a base rate case has been filed within five years prior to the filing of the DSIC petition; and

- Other information required by the Commission.

Peoples’ petition addresses each of the elements listed in the statute, as detailed below.

(1) Tariff Filing

Section 1353 requires utilities to file an initial tariff that complies with the Model Tariff adopted by the Commission.  Peoples’ proposed Supplement No. 11 to Tariff Gas – Pa. P.U.C. No. 45 (Supplement No. 11) closely reflects the language of the Model Tariff.  However, Peoples shall make the tariff sufficiency modifications as spelled-out in Appendix A at the conclusion of this Order.  We shall review each item in turn.

(a) Eligible Property

Peoples’ Petition

Peoples designates the same property as DSIC-eligible as it included in its LTIIP, including piping, couplings, gas service lines, valves, risers, and meters.  Details of Peoples’ DSIC-eligible property are discussed thoroughly in the LTIIP section of this Order.  Eligible property for NGDCs is defined in Section 1352, 66 Pa. C.S. § 1351(2).

As noted in the LTIIP discussion above, Peoples proposes to include its investment in customer-owned gas service lines in its DSIC.  Replacing these service lines is an integral part of Peoples’ strategy for improving the safety and quality of its distribution system.  The bare-steel customer-owned service lines have been subject to the same elements that affect the physical integrity of the company-owned mains that are being replaced.  Peoples asserts that replacing the customer-owned service lines as part of its SMP will result in lower overall costs for the replacement program, in addition to achieving time efficiencies and minimizing service down times.  While the customer owns these service lines, it is necessary for Peoples to undertake replacement of them on its own in order to maintain the speed and efficiency of its replacement strategy.

The Commission previously approved a petition by Columbia Gas of Pennsylvania Inc. (Columbia), at Docket No. P-00072337 and granted by Commission Order entered May 19, 2008, to allow replacement of all customer-owned service lines at the Company’s cost where doing so is necessitated by Columbia’s main replacement and upgrade program.  The cost of replacement of customer-owned service lines has been included in all of Columbia’s rate cases since such approval; therefore, Peoples maintains that inclusion of customer-owned service lines in the DSIC is logical.

In addition to the customer-owned service lines, Peoples has proposed including multiple other “special considerations” and “other related capitalized costs” as part of its LTIIP that would be eligible for DSIC recovery.  Those other categories include:  reliability improvements; special meter technology; information technology support; and vehicles, tools and equipment – all of which are discussed in their entirety in the LTIIP section of this Order.

Comments

The OCA submits concern over Peoples’ proposal to treat the costs associated with replacing customer-owned service lines as DSIC-eligible property.  The OCA requests that this should be fully examined by the Commission, as the statute limits DSIC-eligible property to “costs incurred to repair, improve or replace eligible property that is part of the utility’s distribution system.”  66 Pa. C.S. § 1351.

As to the areas of reliability improvements, special meter technology, information technology support, and vehicles, tools and equipment, OCA questions whether these assets actually serve to accelerate the replacement of aging infrastructure, hence making them ineligible for recovery through the DSIC mechanism.  OCA asserts that these categories of DSIC-eligible property should be reviewed by the Commission to determine whether their costs should be properly recovered through base rates as part of the Company’s normal capital planning process, as opposed to the DSIC surcharge which is intended to accelerate the replacement of aging infrastructure.

Resolution

As noted above in the LTIIP and Service Line Waiver sections of this Order, the Commission approved Peoples’ petition to pay for the cost of replacing customer-owned service lines and to capitalize those costs, while also allowing for the inclusion of these service lines in the Company’s LTIIP as eligible property.  We further found that it is in the public interest for Peoples to replace at its expense certain customer-owned service lines that allow for the efficient coordination with Peoples’ main replacement and upgrade program.

As addressed as part of our discussion of Peoples’ LTIIP above, the Commission agrees with Peoples that such service line projects are reasonable to include in Peoples’ LTIIP and that the costs associated with replacing customer-owned service lines that are part of its accelerated main replacement program/LTIIP may qualify as DSIC-eligible projects.  However, since the OCA has challenged the recovery of these costs in the DSIC, the Commission will refer the issue of whether the costs associated with customer-owned service lines are recoverable through the DSIC mechanism to the OALJ for hearing and recommended decision.

When it comes to the elements of reliability improvements, special meter technology, information technology support, and vehicles, tools and equipment, Peoples claims that such items will provide for greater overall system reliability and improve the Company’s infrastructure to the benefit of its customers, and as such, qualify as reasonable and prudent costs to be recovered through the DSIC.  The Commission has ruled in the LTIIP section of this Order as to which of these items will be permitted for inclusion in Peoples’ LTIIP as eligible-property.  We will align our stance on whether these items should be DSIC-recoverable with the determinations made in that LTIIP discussion.  However, noting that OCA has challenged the recovery of these costs in the DSIC, the Commission will refer the issue of whether the costs associated with reliability improvements, special meter technology, information technology support, and vehicles, tools and equipment are recoverable through the DSIC mechanism to the OALJ for hearing and recommended decision.

(b) Effective Date

Peoples’ Petition

Peoples’ proposed Supplement No. 11 has an issued date of January 31, 2013 and an effective date of April 1, 2013.  Company witness Andrew P. Wachter states that, while Peoples used an effective date of April 1, 2013 to illustrate what a quarterly calculation would look like, the Company understands that actual results for the spending for the three months ending one month prior to the effective date of the DSIC will be used to determine the DSIC rate calculation.

Comments

OCA submits that Peoples should not be permitted to implement its DSIC rate until the issues raised about the recovery of certain costs through the DSIC have been resolved, and it has been determined that the DSIC rate has been calculated in accordance with Act 11 and the Commission’s Final Implementation Order.

Resolution

Peoples asserts that the OCA’s position is contradicted by precedent.  Specifically, they refer to a court ruling which held that implementation of an adjustable rate mechanism that had a year-end proceeding for determining whether any over/under collections were received, and adjusting rates accordingly with the inclusion of interest for any such discrepancies, did not violate due process.  Peoples further states that the legislature passed Act 11 to ensure that public utilities could maintain their financial integrity while expending large sums of capital in distribution system infrastructure improvements, and hence Peoples’ DSIC should be implemented as of the proposed effective date, subject to a refund for any over-collection.

Given that OCA has raised issues and requested hearings regarding certain elements of Peoples’ DSIC petition, we shall refer those issues to OALJ for hearing and recommended decision.  However, consideration of those issues need not delay implementation of the DSIC mechanism itself.  We shall permit Peoples to implement a DSIC mechanism, pursuant to a tariff filed on a 10-day notice and in compliance with the directives in this Order, but note that the rates charged pursuant to the DSIC surcharge shall be subject to recoupment and refund after final resolution of the issues brought before the OALJ.  Therefore, based on requirements for DSIC quarterly updates, as more fully described below, the Commission directs Peoples to file a tariff no later than June 20, 2013, if Peoples wishes to have an effective date of July 1, 2013.  Peoples’ tariff must be modified in a tariff filing as directed by the Commission in this Order.

(c) Computation of the DSIC

Peoples’ Petition

With Supplement No. 11, Peoples proposes a DSIC of .71%, which the Company avers was calculated consistent with the Model Tariff in the Final Implementation Order.  The formula for calculation of the DSIC is as follows:

DSIC	       =	(DSI * PTRR)+Dep+e

PQR

Where:

DSI            =	Original cost of eligible distribution system improvement projects net of accrued depreciation.

PTRR        =	Pre-tax return rate applicable to DSIC-eligible property.

Dep           =	Depreciation expense related to DSIC-eligible property.

e                =	Amount calculated under the annual reconciliation feature or Commission audit.

PQR          =	Projected quarterly revenues for distribution service (including all applicable clauses and riders) from existing customers plus revenue from any customers which will be acquired by the beginning of the applicable service period.

Peoples’ calculation (in thousands) is:

DSIC	       =	(11,219,307 * 2.92%)+51,531

53,300,000

Peoples’ estimated DSIC rate of .71% was calculated using projected costs and capital structure that would be suitable for an April 1, 2013 effective date.  Peoples will update this computation ten days before the actual approved effective date of the DSIC rate to reflect the following:  the costs of all DSIC-eligible projects that were placed into service during the three month period ending one month prior to the approved effective date; Peoples’ actual capital structure and cost of long term debt as of one month prior to the effective date; and the Commission-allowed rate of return on equity.  Therefore, for a DSIC effective July 1, 2013, a three-month period of March through May should be used when calculating the appropriate DSIC rate.

Peoples used a rate of return on equity (ROE) of 10.4% in calculating its DSIC.  Peoples avers that this ROE was based on the Commission’s decision in the fully litigated rate case of PPL Electric Utilities Corporation, at Docket No. R-2012-2290597.  Peoples states that when the Commission publishes a ROE to be used for DSIC purposes, it will revise its tariff filing to reflect the allowed ROE.

Peoples proposes to use one-fourth of its projected annual distribution revenues to calculate projected quarterly revenues, which, according to the Company, makes the DSIC more simple and reflective of the fixed nature of Peoples’ investments.  Peoples witness Wachter adds that this approach will result in a more consistent DSIC rate from quarter to quarter.  The Company has chosen to base its quarterly revenues on one-fourth of its projected annual revenues to better align the fixed nature of the investment that the DSIC will be recovering with the DSIC rate itself.

Comments

The OCA claims that Peoples’ DSIC calculation is incorrect because the DSIC computation does not reflect the impact of accumulated deferred income taxes (ADIT) associated with DSIC investments made by the Company, which in turn permits Peoples to earn a return on an investment balance that exceeds Peoples’ actual investment, and because the calculation of the state income tax component of the DSIC revenue requirement determination requires further examination to ascertain whether it is consistent with the actual taxes paid doctrine.

OCA also expressed concern over Peoples’ proposal to include expenditures related to gathering facility upgrades as DSIC-eligible investment.  These investments stem from the Settlement of Peoples’ 2012 base rate proceeding (Docket No. R-2012-2285985) in which Peoples agreed to spend $3.8 million per year on gathering system upgrades in order to reduce lost and unaccounted for gas.  OCA notes that Peoples proposes to include $241,000 of its expenditures for these upgrades in its initial DSIC, and that this proposal should be reviewed to ensure that it is consistent with the Settlement and won’t result in double-recoveries of amounts to be collected through base rates.

OCA states that the DSIC surcharge proposed by Peoples is contrary to the established principles of sound ratemaking and would contribute to bad regulatory policy.  The OCA requests that the Commission reject the proposed surcharge, and that the matter be referred to the OALJ for the development of an evidentiary record.

Resolution

The Commission acknowledges that Peoples’ calculations are merely estimates and will not be the exact numbers used in the final DSIC calculation because:  1) The inputs for eligible plant were based on forecasted, not actual, data for the three months; 2) The current capital structure and cost rates for long-term debt and common equity were as of February 28, 2013, and should be reflective of the capital structure and cost rates as of one month prior to the approved effective date; and 3) The ROE was an estimate based on another utility’s rate case and did not reflect that of the DSIC ROE as determined by the Commission.

Based on requirements for DSIC quarterly updates, as more fully described below, the Commission directs Peoples to file a DSIC tariff using actual data for eligible property placed into service during the three-month period ending one month prior to the approved effective date of the DSIC.

In the calculation of its proposed DSIC, Peoples used one-fourth of the annual depreciation expense based on the eligible-property placed in service for the quarter.  This calculation is consistent with Peoples’ tariff and the Commission’s Model Tariff.  However, to be consistent with what has been allowed for the water utility DSICs as accepted by the Bureau of Audits and approved by the Commission, Peoples should use one-fourth of the annual depreciation expense amount as the basis for its initial accumulated depreciation amount.  Each quarter going forward, the calculated depreciation expense for DSIC purposes should be added to the prior quarters calculated depreciation expense to determine the accumulated depreciation amount.

The cost of equity determinations in the Commission’s Staff Report on Quarterly Earnings of Jurisdictional Utilities (Quarterly Report) are used for DSIC calculations if more than two years have elapsed since a utility’s last fully litigated base rate case.  66 Pa. C.S. § 1357(b)(3).  If, in any quarter, a utility will earn more than the ROE used for the DSIC calculations (which may be the ROE determined in the Staff Quarterly Report), the DSIC will be reset to zero.  66 Pa. C.S. § 1358(b)(3).  Accordingly, the DSIC must remain at zero until such time that the utility, in a subsequent quarter, earns less than the ROE used for the purpose of DSIC calculation.

It is clear that Peoples’ cost of equity used in the calculation of the estimated DSIC does not comply with these regulations.  Peoples used an estimated ROE of 10.4%, which was taken from the recent PPL base rate case at Docket No. R-2012-2290597.  Peoples’ ROE of 10.4% was not obtained according to 66 Pa. C.S. § 1357(b)(3).  Therefore, consistent with Section 1357(b)(3), and as would be appropriate for a July 1, 2013 tariff effective date, the current Staff Quarterly Report for the period ending December 31, 2012 (4th Quarter Report) contains appropriate ROE calculations.

Furthermore, the Commission directs that, along with its updated capital structure and cost rates filed one month prior to the approved effective date of the tariff, Peoples shall file a comprehensive debt schedule, outlining all outstanding debts and their associated interest rates that were used to calculate the long term debt cost rate figure.

The Model Tariff makes available to utilities two options for calculating projected quarterly revenues:  1) The summation of projected revenues for the applicable three-month period; or 2) One-fourth of projected annual revenues.  In order to maintain a more consistent DSIC rate from quarter to quarter, Peoples chose to use one-fourth of its projected annual distribution revenues as its projected quarterly revenues.  The Model Tariff permits the use of one-fourth of annual revenues and the Final Implementation Order recognized the seasonality of revenue issues.  Therefore, Peoples’ use of one-fourth of its projected annual distribution revenues as its projected quarterly revenues is appropriate.

OCA expressed concern that Peoples may double-recover costs associated with gathering line upgrades meant to reduce lost and unaccounted for gas.  Peoples argues that, while in the Settlement Agreement to its last base rate case the Company did agree to spend $3.8 million per year toward improving its gathering facilities used to deliver gas to Peoples and its customers, nothing in the Settlement Agreement provides that Peoples would not recover the costs associated with any capital investment related to that commitment.  Peoples is claiming $241,000 of these upgrades as part of its initial DSIC filing, and notes that these expenditures are expected to result in direct benefits to ratepayers through the reduction of unaccounted-for-gas.  Peoples asserts that recovery of DSIC-eligible portions of these improvements do not constitute double-recovery.  The Commission agrees with Peoples’ assertion and certifies that we will review all claims of DSIC recovery to ensure that they were not included for recovery in any previously implemented base rates.

OCA opines that Peoples’ DSIC calculation should be adjusted to reflect the impact of ADIT associated with DSIC investments made by the Company; otherwise Peoples will earn a return on an investment balance that exceeds Peoples’ actual investment.  That is, ADIT can be viewed as a source of zero cost capital.  The Commission, in its Implementation Order, has determined that the “adjustment, which was not previously used in the DSIC by the water industry, would add unnecessary complexities to the DSIC and, accordingly, will not be included in the model tariff.” Final Implementation Order, p. 39.

Additionally, OCA is reviewing the calculation of the state income tax component of the DSIC revenue requirement determination to ensure that ratepayers receive the full benefit of the tax deductions consistent with the actual taxes paid doctrine.

We will refer OCA’s issues related to the impact of ADIT associated with DSIC investments and the calculation of the state income tax component of the DSIC revenue requirement, to the OALJ for further disposition.  To the extent that Peoples may be permitted to implement a DSIC pending the OALJ proceeding and chooses to do so while these matters are pending in the OALJ, the DSIC recovery shall be subject to recoupment and refund after final resolution.

(d) Quarterly Updates

Peoples’ Petition

A utility’s DSIC is subject to quarterly updates to reflect eligible plant additions placed in service during the three-month period ending one month prior to the effective date of any DSIC update.  Proposed Supplement No. 11 includes a chart of the effective dates of Peoples’ proposed DSIC updates, and the corresponding period for eligible plant additions that will be reflected in each update.  The Company states that once its DSIC is implemented, customers will receive notice of quarterly changes in the DSIC through bill messages, consistent with Act 11 and the Final Implementation Order.

Comments

No comments were filed regarding this aspect.

Resolution

In accordance with 66 Pa. C.S. § 1358(e)(2), the revenue received under the DSIC for the reconciliation period shall be compared to the utility's eligible costs for that period. The difference between revenue and costs shall be recouped or refunded, as appropriate, in accordance with section 1307(e), over a one-year period or quarterly period commencing April 1 of each year.  Based on the statute mandating over/under collections be refunded commencing April 1 of each year, the Commission directs any utility filing for a DSIC to schedule the effective dates of their proposed DSIC updates, and the corresponding period for eligible plant additions that will be reflected in each update, to align quarterly with the months of April, July, October, and January.  Peoples has suggested such a schedule in the filing of their proposed Supplement No. 11, and hence, the Commission deems Peoples’ tariff to be compliant with Section 1353 as it pertains to the issue of quarterly updates.

(e) Consumer Protections

Peoples’ Petition

In accordance with the Model Tariff and consistent with Section 1358, Peoples’ proposed Supplement No. 11 also includes the following customer safeguards:

- A 5.0% cap on the total amount of distribution revenue that can be collected through the DSIC by Peoples as determined on an annualized basis;

- Annual reconciliations performed by Peoples;

- Audits conducted by the Commission;

- Customer notice of any changes in the DSIC;

- A reset of the DSIC to zero as of the effective date of new base rates that include the DSIC-eligible plant; and

- Provisions for the charge to be set at zero if, in any quarter, Peoples’ most recent earnings report shows that Peoples is earning a rate of return that exceeds the allowable rate of return used to calculate its fixed costs under the DSIC.

As a customer safeguard, the Model Tariff states that the DSIC shall be applied equally to all customer classes.  Peoples added to this a provision that specifies that the Company may reduce or eliminate the Rider DSIC to any customer with competitive alternatives or potential competitive alternatives and customers having negotiated contracts, which is consistent with the Final Implementation Order.  Peoples has excluded the Rider DSIC charge from tariffs for customers with competitive alternatives and negotiated contracts.  Testimony submitted by Peoples’ Wachter states, “It is Peoples’ intention to apply the DSIC to all customers where it can.  However, due to contractual constraints, we do have instances of competitive accounts that are not currently eligible for the application of a rider such as DSIC.”

Comments

OCA claims that the language in Peoples’ proposed tariff relating to customers with competitive alternatives is not consistent with Act 11 and the Final Implementation Order.  More specifically, OCA states that Peoples’ proposed language would allow the Company to reduce or eliminate the DSIC for customers with “potential” competitive alternatives.  OCA submits that this language is overly broad and not consistent with the Commission’s intent.

OCA further expressed concern about Peoples’ proposal to use the Service Company that serves both Peoples and Peoples TWP as part of the implementation of its LTIIP.  OCA avers that the proposed DSIC rate must be reviewed to ensure that it includes only Peoples and Service Company expenses that are directly related to Peoples and are not fully reflected in base rates.

Resolution

Peoples’ proposed Supplement No. 11 is consistent with the Model Tariff and complies with the customer safeguards required by 66 Pa. C.S. § 1358.  Additionally, the Company has provided language in its tariff which excludes those customers with competitive alternatives or negotiated contracts that is consistent with the Final Implementation Order.  Prior to such a change going into effect, the Commission must review any future tariff change that would exclude and/or include any customer class.  Therefore, the current language as provided which excludes customers with competitive alternatives or negotiated contracts will be allowed.

Peoples counters OCA’s concerns regarding the Service Company by noting that, at the outset, the DSIC will not recover Company and Service Company expenses, but rather is limited to the recovery of capitalized costs associated with the repair and replacement of DSIC-eligible property, and that those costs are new amounts not currently reflected in base rates.  Peoples further states that review of the costs recovered as part of Peoples’ DSIC, and whether those costs are directly related to Peoples, is not possible at this time, and such an inquiry is more appropriately conducted at the annual reconciliation.  The Commission agrees with Peoples that the issue of whether DSIC costs have an actual cost consequence to Peoples would be best evaluated after any such capitalized costs are claimed in a future DSIC filing, and as such, any language referencing the utilization of the Service Company in aiding the implementation of the LTIIP is appropriate at the current time.

(2) Public Interest Considerations

Peoples’ Petition

According to the Company, implementing the proposed DSIC and allowing proposed tariff Supplement No. 11 to go into effect is in the public interest because the DSIC will ensure that customers continue to receive safe and reliable service in the future as required by Section 1501, 66 Pa. C.S. § 1501.

In mid-2011, Peoples implemented its SMP program to target infrastructure replacement, particularly the removal and replacement of all cast iron, all unprotected bare steel pipeline, some cathodically protected bare steel and the services associated with these types of pipe.  Over 25% of Peoples’ pipeline system was constructed prior to 1955, and more than 30% of the distribution pipe is unprotected bare steel, which is subject to corrosion and damage from exposure and age.  Cast iron pipe is generally recognized as the highest risk pipe within a gas utility’s system, and as such, Peoples removed all 48 miles of cast iron pipeline from its system as the first goal in its SMP.  Peoples’ next goal under the SMP is to remove all unprotected bare steel pipe within 20 years, whereas absent the accelerated main replacement program Peoples claims it would have taken roughly 67 years to replace all of the unprotected bare steel pipes in its system.  Peoples avers that the DSIC is an important element in successful implementation of the SMP because it will provide the necessary capital to make continued rapid investment possible.

Prior to the accelerated program, Peoples claims it replaced approximately 33 miles of distribution pipeline per year, but with the introduction of the SMP and the LTIIP, they estimate replacing 55 miles of distribution pipeline per year from 2013-2017.  Continuing with that trend, Peoples states that during the five-year period of the LTIIP (2013 to 2017), it will increase its capital investment by 108 percent over the historic five-year period from 2007 to 2011.  Peoples believes that this increased level of investment in the repair, improvement, and replacement of aging distribution facilities will reduce the number of gas leaks, reduce leakage and unaccounted-for-gas, and bring about savings in future purchased gas cost rates and transportation retainage rates.  All of these measures, Peoples asserts, will help to provide safer and more efficient service to customers, and hence lend credence to the fact that the LTIIP and its associated DSIC are in the public interest.

Peoples notes that base rate filings are unpredictable and would add risk of delay and uncertainty to Peoples’ planning process, as well as causing customers to experience spikes in their rates.  They claim, however, that the DSIC will result in gradual quarterly rate changes which should be more acceptable to customers over time.  Peoples declares that the implementation of a DSIC rate is vital in supporting its efforts to replace its aging distribution system, by ensuring the resources the Company needs to carry out its SMP and LTIIP strategies.

Comments

No comments were received regarding the supporting evidence that Peoples’ DSIC is in the public interest.

Resolution

Section 1353 requires testimony, affidavits, exhibits, and other supporting evidence to be submitted demonstrating that the DSIC is in the public interest.  Based on Peoples’ submitted direct testimonies by the Company’s Manager of Rates & Regulatory Affairs and Sr. Vice President & Chief Operations Officer, as well as exhibits demonstrating how the proposed DSIC supports accelerated infrastructure improvement, the Commission concludes that the DSIC filing is in the public interest and that the Company has met its obligation under Section 1353.

(3) Long Term Infrastructure Improvement Plan

Section 1353 requires that the utility have an approved Long Term Infrastructure Improvement Plan (LTIIP).  Peoples filed a LTIIP with the Commission on January 23, 2013, which is recommended for approval concurrently with the DSIC.

(4) Base Rate Case

Section 1353(b)(4) requires a utility to certify that it has filed a base rate case within the five years prior to the date of its DSIC petition.  Peoples has provided the required certification that its last base rate case, under which Peoples’ current base rates were established, was filed on February 28, 2012.

(5) Other Information Required by the Commission

Section 1354 - Customer Notice

Pursuant to Section 1354, a utility is required to provide customer notice of:  1) Submission of the DSIC petition; 2) Commission’s disposition of the DSIC petition; 3) Any quarterly changes to the DSIC rate; and 4) Any other information required by the Commission.  Peoples has verified that it will provide customer notice of the proposed DSIC, Commission action thereon, and quarterly updates through bill inserts, consistent with Act 11 and the Final Implementation Order.

Peoples will provide a bill insert to all customers informing them of the filing, the estimated impact of a DSIC on their bills, and their rights to intervene in the proceeding.  The language on the bill insert was developed through feedback from the Commission and other interested parties.  In addition to the bill insert, Peoples vows to notify customers through their Peoples View newsletter, which is mailed to customers along with their monthly billing statement.  Peoples also says it will post the newsletter, bill insert, and other pertinent information regarding the DSIC on its website.

The Commission agrees that this is consistent with the notice requirements set forth in the Model Tariff, Act 11, and the Final Implementation Order.

Bills Rendered or Service Rendered

The Final Implementation Order directed utilities to bill customers for the DSIC on a bills rendered basis versus a service rendered basis, based on current practice and procedure for water companies.  (See 66 Pa. C. S. § 1358).  Peoples’ proposed tariff did not specify whether billing for the DSIC would be on a bills rendered or a service rendered basis.  Therefore, in accordance with the Final Implementation Order, we direct Peoples to modify the language in the proposed tariff to specify that customers would be billed for the DSIC on a bills rendered basis.

Section 1355 – Commission Review

Section 1355 provides that the Commission shall, after notice and opportunity to be heard, approve, modify or reject a utility’s proposed DSIC and initial tariff.  The Bureau of Technical Utility Services has reviewed Peoples’ proposed DSIC and proposed tariff Supplement No. 11 and has determined that the filing contains all necessary items identified in Section 1353.

DSIC SUMMARY

We will approve the proposed DSIC calculation and tariff subject to the modifications consistent with this Order, including the following:

- A tariff filed on ten days’ notice with an effective date no earlier than July 1, 2013;

- A three-month period of March through May for eligible plant additions;

- An initial quarterly depreciation expense being equal to the initial accumulated depreciation; and,

- An appropriate return on equity as displayed in the Commission’s Quarterly Report for the period ending December 31, 2012.

Section 1355 also states that the Commission shall hold evidentiary and public input hearings as necessary to review the petition.  As noted above, OCA, OSBA, PIOGA, and U.S. Steel have petitioned to intervene in Peoples’ DSIC proceeding, and there were requests to hold evidentiary hearing on several aspects of the DSIC.

Accordingly, we will refer the matters of DSIC recovery of costs associated with customer-owned service lines, reliability improvements, special meter technology, information technology support, and vehicles, tools and equipment to the OALJ for hearing and recommended decision.  We shall also refer the impact of ADIT associated with DSIC investments, as well as the calculation of the state income tax component of the DSIC revenue requirement, to the OALJ for evidentiary hearings and preparation of a recommended decision.  To the extent that Peoples elects to implement a DSIC mechanism prior to resolution of these matters, any recovery will be subject to refund or recoupment consistent with final determinations on these matters referred to OALJ.

We note the filings of PIOGA, OSBA, U.S. Steel, L.A. Goldstrom, Mr. Felix, Mr. Gaydos, Ms. Pauloni, Mr. Frumerman, Mr. Sedei, Mr. Stepnick, Mr. Eckenrod, Ms. Brown, Mr. Kovach, Mr. Johnsonbaugh, Mr. Miller, Ms. Caird, Mr. Yanizeski, and Mr. Pokusa.  We conclude that they have not articulated a basis for denying Peoples the opportunity to implement a DSIC mechanism, consistent with our discussion above.

CONCLUSION

# Upon review, the Commission finds that Peoples’ request for limited waivers of the provisions of its tariff relating to customer service line replacement should be granted as filed; and that Peoples shall comply with I&E’s recommendation to properly mark and identify all newly-installed customer service lines so as to fully comply with the standards of PA One Call.

# Additionally, the Commission finds that the Peoples Long-Term Infrastructure Improvement Plan and manner in which it was filed conforms to the requirements of Act 11 and our Final Implementation Order.

# Furthermore, the Commission finds that the Petition of Peoples for a Distribution System Improvement Charge complies with the requirements of Act 11 and our Final Implementation Order.  Moreover, the Commission has reviewed the filing and does not find it to be inconsistent with the applicable law or Commission policy.  Subject to recoupment and/or refund pending final resolution of the matters referred herein to the OALJ, Peoples may elect to implement a DSIC mechanism consistent with this order on ten days’ notice; THEREFORE,

IT IS ORDERED:

- That the Petition for approval of Limited Service Line Waivers filed by Peoples Natural Gas Company, LLC is approved, consistent with this Order.

- That the Petition for approval of a Long-Term Infrastructure Improvement Plan (LTIIP) filed by Peoples Natural Gas Company, LLC is approved, consistent with this Order.

# 3.	That the Petition for approval of a Distribution System Improvement Charge (DSIC) filed by Peoples Natural Gas Company, LLC is approved, consistent with this Order.

4. 	That Peoples Natural Gas Company, LLC shall file a tariff, consistent with this Order, on ten days’ notice to be effective July 1, 2013.  Revenues collected pursuant to said tariff will be subject to refund and recoupment based on the Commission’s final resolution of the matters referred herein to the Office of Administrative Law Judge for hearing and recommended decision.

# 5. 	That the following issues be assigned to the Office of Administrative Law Judge for hearing and preparation of a recommended decision:

  - DSIC-recovery of costs related to customer owned service lines, reliability improvements, special meter technology, information technology support, and vehicles, tools and equipment;

  - Impact of accumulated deferred income taxes associated with DSIC investments; and

  - Calculation of state income tax component of the DSIC revenue requirement.

# 6. 	The Complaint of Daniel Killmeyer is dismissed.

- The Commission denies the United States Steel Corporation’s Petition to Intervene as untimely.

- United States Steel Corporation may file a petition to intervene nunc pro tunc in the proceeding before the Office of Administrative Law Judge but only as to the remaining issues that have been referred to the Office of Administrative Law Judge as set forth in the body of this Order.

- That Peoples Natural Gas Company, LLC provides the estimated number of anticipated new jobs to be created for specific replacement projects with its revised DSIC tariff and to track such employment in order to have actual numbers of jobs created when the DSIC fund information is submitted for annual audit and reconciliation.

BY THE COMMISSION,

Rosemary Chiavetta

Secretary

(SEAL)

# ORDER ADOPTED: May 23, 2013

# ORDER ENTERED:  May 23, 2013

Appendix A

Tariff Sufficiency Modifications

- On pages 3, 3a, 4, and 4b, the issued date listed in the bottom corner of the page needs to match the issued date displayed on the title page.

- On the List of Changes page (page No. 2), the first statement reading, “In addition to the net charges provided for in this Tariff, a charge of 0.71% will apply consistent with the Commission Order dated xx/xx/xx at Docket No. _________ approving the DSIC.” needs to be included as the first statement made on the RIDER K DSIC page (page No. 74).

- On page No. 74, the Effective Date should read: “The DSIC will become effective for bills rendered on and after 7/1/2013.”

- On page No. 74, under the Computation of the DSIC section, within the table the column entitled “Date to which DSIC-Eligible Plant Additions Reflected” should reflect the full range of dates (i.e. “March 1 through May 31”).

- On page No. 75, under the Quarterly Updates section, the Commission’s Bureau of Audits should be added as a party to be served.

- On page No. 75, under “2. Audit/Reconciliation” of the Customer Safeguards section, the fourth line that reads, “The revenue received during the DSIC…..” should be changed to, “The revenue received under the DSIC…..”

- On page No. 76, under “4. Customer Notice” of the Customer Safeguards section, the last word in the first line, “no”, should be changed to “on”.

- On page No. 76, under “6. Earnings Reports” of the Customer Safeguards section, on the second line the word “report” should be changed to “reports”.

http://www.legis.state.pa.us/WU01/LI/LI/US/HTM/2012/0/0011..HTM.

In preparing its LTIIP, Peoples relied on its current DIMP.  While the Commission is not making a determination as to the adequacy of Peoples’ DIMP in this proceeding, our review is limited to the determination of whether Peoples’ LTIIP and DIMP are consistent.

See Allegheny Ludlum Steel Corp. v. Pa. P.U.C., 501 Pa. 71; 459 A.2d 1218 (Pa 1983).

The quarters are fixed by statute.  If Peoples does not have an effective date of July 1, 2013, the next earliest effective date would be October 1, 2013.

The ROE to be used in the DSIC calculation will be that which is calculated by the Commission in its most recent Quarterly Report on the Earnings of Jurisdictional Utilities.

The DSIC is subject to continuous Commission review and audit as well as reconciliation reports in accordance with Section 1307(e) of the Public Utility Code, 66 Pa. C.S. §1307(e).

Docket No. R-2012-2285985, Final Order entered on September 27, 2012.

“Bills rendered” bills are computed based on the effective tariff rate at the time of the bill.  “Service-rendered” bills are prorated based on service rendered before and after a tariff rate change.