	
	PENNSYLVANIA

PUBLIC UTILITY COMMISSION

Harrisburg, PA  17105-3265
	


	
	Public Meeting held May 22, 2014

	Commissioners Present:
	


	Robert F. Powelson, Chairman
	

	John F. Coleman, Jr., Vice Chairman
	

	James H. Cawley
	

	Pamela A. Witmer
	

	Gladys M. Brown
	

	
	

	Petition of Duquesne Light Company for Waiver of Certain Provisions of the Public Utility Commission’s Regulations at 52 Pa. Code § 57.71 et seq., for the Siting and Relocation of Existing Transmission Facilities in Brighton, Vanport, Potter and Center Townships, Beaver County, PA to Accommodate a Potential New Industrial Facility 
	P-2014-2401906


OPINION AND ORDER
BY THE COMMISSION:

Before us for consideration is a Petition of Duquesne Light Company (Petition) for Waiver of Certain Provisions of the Public Utility Commission’s (Commission) Regulations at 52 Pa. Code § 57.71 et seq., for the Siting and Relocation of Existing Transmission Facilities in Brighton, Vanport, Potter and Center Townships, Beaver County, PA to Accommodate a Potential New Industrial Facility.  For the reasons that follow, we grant the Petition. 

BACKGROUND

Petitioner Duquesne Light Company (Duquesne) is a certificated electric distribution utility furnishing service to approximately 588,000 customers throughout portions of Allegheny and Beaver Counties, Pennsylvania.  Duquesne owns approximately 677 miles of transmission lines operating at 69 kV or higher and approximately 8,210 miles of distribution lines operating at less than 69 kV. 


Petitioner filed its Petition on January 22, 2014.  The Petition was served on the following governmental parties: PA Historical and Museum Commission, PA Department of Transportation, PA Department of Environmental Protection, PA Office of Consumer Advocate, PA Office of Small Business Advocate and Commission Office of Investigation and Enforcement.  Petitioner filed its Petition on the following affected private parties: GSC Real Estate, LP; Pennsylvania Lines LLC; Jochar Corporation; Interstate Chemical Company; Peoples Natural Gas Company; Associated Medical Specialists; Drug and Alcohol Services of Beaver Valley, Inc.; Sunoco Partners Marketing Team LP; Lloyd Grimes & Karen O’Neill; Micheal Dobish & Cherie Zercher; Gerald & Eddi K. Mathews; Caryl M. & George E. Belich.  No protests, interventions or letters were filed by any of the served parties. 

Duquesne’s Petition requests waiver of the Commission’s regulations at 
57 Pa. Code §§  57.71 et seq. to permit Duquesne to proceed by means of a Letter of Notification (LON) for the potential siting and relocation of existing 138 kV transmission lines in Brighton, Vanport, Potter, and Center Townships, Beaver County, Pennsylvania to serve a potential new customer currently evaluating the feasibility of constructing a  major industrial plant in Duquesne Light’s service territory in Beaver County.

The proposed site for the potential new industrial plant currently is traversed by Duquesne Light’s Valley-Raccoon (Z-81/Z-83) 138 kV Transmission Lines.
  The potential new customer has requested that Duquesne’s existing transmission lines, which currently traverse the proposed site for the potential new industrial plant, be relocated to the eastern and southern perimeter of the proposed facility site to accommodate the construction of the proposed industrial plant.  The relocated transmission lines will ultimately be the source of electric supply for the proposed new industrial plant to the electrical grid.  As part of the construction of the proposed new industrial plant, a new customer-owned 138 k V substation will connect to Duquesne Light’s Valley-Raccoon (Z-81) 138 kV Transmission Line.  Duquesne states that the proposed new industrial plant cannot be completed until the existing transmission facilities are relocated.

Duquesne Light has identified a route feasible to accommodate the construction of the proposed new industrial plant.  The proposed route primarily utilizes property owned by the potential new customer as replacement right-of-way to relocate the facilities outside of the plant construction area.  The route begins on the north shore of the Ohio River approximately 2,100 feet from the riverbank at the existing Valley-Raccoon (Z‑81/Z-83) 138 kV transmission line utilizing existing right-of-way.  The route then proceeds southeast for a distance of approximately 850 feet to the vicinity of the existing Valley-Hopewell (66141) 69 kV Tower 320.  The 850’ segment of the route requires new rights-of-way to be acquired by Duquesne Light.

At the Valley-Hopewell (66141) 69 kV Tower 320, the route proceeds 
east-southeast for approximately 3,800 feet which consists of existing right-of-way 
and the width of the Ohio River.  After crossing the Ohio River, the route proceeds 
south-southeast for approximately 3,810 feet where it turns southwest and continues approximately 2,820 feet to intercept the existing Valley-Raccoon (Z-811Z-83) 138 kV transmission line right-of-way.   At this point, the route turns northeast and proceeds approximately 1,840 feet to the vicinity of an existing customer-owned substation.  
This segment of the proposed route will be located entirely on the property of the potential new customer.  In total, Duquesne states that the relocation will require approximately 10.2 acres of new right-of-way on the north side of the Ohio River.  
On the south side of the Ohio River, all of the relocated facilities will be located on the property of the potential new industrial plant.

The tower structures for the relocated 138 kV transmission line will consist primarily of self-supporting, double-circuit tubular steel poles.  The relocation will require approximately 28 self-supporting tubular steel poles with an average 
height of approximately 170 feet.  The proposed relocation also will require 
four (4) self-supporting lattice steel tower structures to support the lines crossing the 
Ohio River.
  Each circuit of the relocated lines will operate as a three phase alternating current transmission line and will consist of three phase conductors and one shield wire.
The project will require approximately 2.5 miles of existing double circuit 138 kV transmission lines to be relocated.  The project can be separated into three distinct components: 

(1) The first component of the project requires the relocation of approximately 1.7 miles of existing 138 kV transmission lines solely on the property of the potential new industrial plant to be owned and operated by the new customer. 

(2) The second component of the project is the relocation of approximately 0.4 miles of 138 kV transmission lines within new rights-of-way to be acquired by Duquesne Light.
(3)
The third component of the project is the relocation of approximately 0.4 miles of 138 kV transmission lines within a river crossing of the Ohio River. The proposed river crossing will reduce the total number of existing river crossings by relocating the existing 138 kV line and 69 kV lines (as well as the existing distribution lines), which currently occupy separate river crossings, within the same river crossing of the Ohio River.


Duquesne estimates that the total estimated cost of the project to be $33.47 million, which includes $5.90 million for substation work, $20.74 million of transmission work and $6.83 million of distribution work.   Duquesne states that the entire cost of the proposed relocation will be paid for by the new customer if the construction of the proposed industrial plant goes forward and the project is required to accommodate the construction of the new plant.  Upon Commission approval of the to-be-filed LONs, the project has a scheduled construction start date of September 2014 to meet an in-service date of June 2015.   Duquesne avers that the proposed new industrial plant cannot be completed unless and until the existing transmission facilities are relocated.  Importantly, Duquesne states that it will not relocate the existing transmission lines if the new customer does not proceed with its plans to construct the proposed new industrial plant.

Duquesne states that 1.7 miles of the project will be constructed entirely on the property of the new potential customer, 0.4 miles of the project will be constructed within right-of-way of land to be purchased by Duquesne and 0.4 miles will be constructed within a river crossing for a total route distance of 2.5 miles.  Under the circumstances, Duquesne submits that the most practical and efficient method to obtain Commission review and approval for the siting of the project is an LON filing under 52 Pa. Code 
§ 57.72(d) rather than a full Application under 52 Pa Code §§ 57.71(a)-(c). The use of an LON will provide all the information necessary for the Commission and interested parties to fully review and evaluate the project.
Duquesne contends that use of an LON filing will permit the utility to complete the filings required for approval in a much shorter period of time than would be required to prepare a complete siting application for the project.  Regulatory review in a shorter period of time will enable Duquesne to complete construction of the project and maintain the construction and in-service dates without jeopardizing or otherwise delaying the construction schedule required for the potential new industrial plant.

DISCUSSION

The Commission’s regulation at 52 Pa. Code § 57.72(d) sets forth the circumstances under which an electric public utility may seek Commission approval for the siting and construction of a proposed high voltage transmission line by means of an LON instead of a full Application as follows:
(d)
Letter of notification in lieu of Application:

(1) A Letter of Notification may be filed with the commission in lieu of the Application process set forth in §§ 57.71 - 57.76 for the following:

(i) An HV line which is proposed to be located entirely on an existing transmission line right-of-way, so long as the size, character design, or configuration of the proposed HV line does not substantially alter the right-of-way.

(ii) An HV line which is proposed to be located entirely within a public road.

(iii) An HV line which is proposed to be located entirely within the applicant’s existing transmission line right-of-way and the property of the sole customer to be served by-the line, so long as the size, character, design, or configuration of the proposed line does not substantially alter the right-of-way.

(iv)
A line for which the voltage is proposed to be increased above its present levels, so long as the size, character, design or configuration of the proposed line does not substantially alter the right-of-way.

(v)
An HV line which is to be re-conductored or reconstructed so long as the size, character, design or configuration of the proposed line does not substantially alter the right-of-way.

(vi)
An HV line having a proposed route of 2 miles or less.
52 Pa Code § 57.72 (d).

As proposed, the potential project does not meet the strict definition of any one of the circumstances in which an LON may be used, as set forth above.  The potential project, however, nearly fits within several of the circumstances in which an LON may be used in lieu of an Application.  Duquesne Light is requesting a waiver of the strict Application of the aforementioned regulations to allow Duquesne Light to file an LON in lieu of an application for Commission review and approval to site and construct the potential project.

The Commission’s Rules of Administrative Practice and Procedure at 52 Pa. Code § 5.43 allow for petitions for waiver of any of the Commission’s regulations.  More specifically, the Commission’s transmission line siting regulations at 52 Pa. Code § 57.72(e) specifically permit petitions to request that portions of these specific siting regulations be waived.  It states:

(e)
The Commission or the presiding officer may- upon the petition of any party, upon the Commission’s own motion, or upon the presiding officer’s own motion - waive one or more or all of the requirements in this subchapter. The petition shall clearly state the requirements sought to be waived and the reasons therefor.  52 Pa. Code § 57.72(e).

Duquesne Light requests a waiver of the strict application of 52. Pa Code 
§ 57.72(d)(1 ) to permit Duquesne Light to seek approval of the siting and construction of the potential project, if and when necessary to accommodate a new industrial plant proposed by a new customer in Beaver County.

Duquesne Light has identified a route feasible to accommodate the construction of the proposed new industrial plant. The proposed route primarily utilizes property owned by the potential new customer as replacement right-of-way to relocate the facilities outside of the plant construction area.

LONs are permitted if the proposed transmission line has “a proposed route 
of 2 miles or less.”  52 Pa. Code § 57.72(d)(1)(vi).  LONs are also permitted if the proposed transmission line is "proposed to be located entirely within ... the property of the sole customer to be served by the line." 52 Pa. Code § 57.72(d)(1)(iii).

As explained above and based on the route ultimately selected, the potential project would require approximately 2.5 miles of existing 138 kV transmission lines to be relocated.  Although the proposed route for the potential project is only slightly greater than the 2-mile threshold for an LON, the individual components of the project qualify for an LON.
The first component of the potential project is approximately 1.7 miles of 138 kV transmission lines that will be located solely on the property of the new potential customer.  Duquesne Light submits that this component of the potential project qualifies as an LON because it is less than 2 miles and is located solely on the property of the potential new customer.
The second component of the potential project requires construction within new right-of-way.  This component of the potential project will require the relocation of approximately 0.4 miles of 138 kV within new right-of-way to be acquired by Duquesne Light.  Duquesne Light submits that this component of the project qualifies for LON treatment because it is less than 2 miles.

The third component of the potential project is a river crossing that will extend approximately 0.4 miles over the Ohio River.  Duquesne Light submits that this component of the potential project qualifies for LON treatment because it is less than 
2 miles and because it would minimize the existing impacts of the river crossings.

Although the potential project does not meet the strict definition of any one of the circumstances in which an LON may be used, we find that the specific components of the potential project satisfactorily meet the requirements for LON treatment in lieu of an Application.  We will grant Duquesne Light’s Petition for Waiver of the Commission’s regulations at 52 Pa. Code §§ 57.71 et seq.
The Commission has approved similar requests granting waivers of certain regulations regarding Commission Review of Siting and Construction of Electric Transmission Lines at 52 Pa Code § 57.71 et seq.  See, e.g., Letter of Notification of West Penn Power Company filed pursuant to 52 Pa. Code Chapter 57 with respect to reconstruction and relocation of the Allegheny Ludlum No.2 138 kV Transmission Line in the City of Lower Burrell, Westmoreland County, Pennsylvania, Docket No. A‑2012‑2281399 (March 1, 2012) (approving the construction of a 2.7 mile transmission line project under 52 Pa. Code § 57.72(d)(1)(v) and (vi) because a portion of the line transmission line is to be re-conductored or reconstructed and a separate portion being relocated is less than two miles in length); Petition for Waiver of Certain Provisions of the Pennsylvania Public Utility Commission’s Regulations for Commission Review of Siting and Construction of Electric Transmission Lines set forth at 52 Pa. Code 
§ 57.71 et seq., Docket No. P-2008-2037618 (June 27, 2008) (approving a for a waiver from Section 57.72(d) for the construction of a 3.9 mile 115 kV transmission line to connect a new ethanol plant to the grid); Letter of Notification of Pennsylvania Electric Company pursuant to 52 Pa. Code § 57. 72(d) to install the East-Towanda Mansfield 
115 kV Transmission Line Tap to the Tennessee Gas Pipeline Substation located in Troy Township, Bradford County, Pennsylvania (Penelec/Tennessee Gas), Docket No. A‑110400F0045 (February 6, 2006) (approving a request for waiver of certain provisions of 52 Pa. Code § 57.72(d)(1) for a 2.6 miles long transmission line project located along the rights-of-way of an existing line and across the property of the sole customer to be served by the line).
Although the potential project does not meet the strict definition of any one of the circumstances in which an LON may be used, we find that the specific components of the potential project satisfactorily meet the requirements for LON treatment in lieu of an Application.  We will grant Duquesne Light’s Petition for Waiver of the Commission’s regulations at 52 Pa. Code §§ 57.71 et seq.
THEREFORE,

IT IS ORDERED:

1. That Duquesne Light Company’s Petition for Waiver of Certain Provisions of the Commission’s regulations at 52 Pa. Code § 57.71 et seq. is granted.
2. That if it intends to construct the proposed facilities, Duquesne Light Company shall file the required Letters of Notification for the potential project pursuant to 52 Pa. Code § 57.72(d).
[image: image1.png]


BY THE COMMISSION

Rosemary Chiavetta

Secretary

(SEAL)

ORDER ADOPTED:  May 22, 2014
ORDER ENTERED:  May 22, 2014
� The proposed site also is currently traversed by the Valley-Hopewell (66141) 69 kV Transmission Line and the Kobuta 69 kV Tap, as well as by two 23 kV circuits, the Raccoon Monaca 22831 and Raccoon D-23621 circuits. Because Duquesne Light does not need Commission approval to site, construct, or relocate transmission lines operating at less than 100 k V, see 52 Pa. Code § 57.71, these 69 kV and 23kV circuits are not the subject of this Petition for Waiver or any future filing seeking Commission approval of the siting and construction of the Potential Project. 


� Two of these towers will be used for the 69 kV relocation and two will be used for the 138 kV relocation.





PAGE  
11

