VONDLE & ASSOCIATES, INC.

PROPOSAL TO PERFORM A STRATIFIED MANAGEMENT AND OPERATIONS AUDIT OF

PPL ELECTRIC UTILITIES CORPORATION

FOR THE

PENNSYLVANIA PUBLIC UTILITY COMMISSION

BUREAU OF AUDITS

REVISED COST AND PRICE ANALYSIS SUBMITTAL

April 28, 2015

# COST AND PRICE ANALYSIS

This separately bound chapter presents the Vondle & Associates, Inc. Cost and Price Analysis to conduct the Stratified Management and Operations Audit of PPL Electric Utilities Corporation for the Pennsylvania Public Utility Commission Bureau of Audits.  It is presented in the Request for Proposals specified format:

- Phase I - Diagnostic Review

- Phase II – Pre-Identified Areas or Issues

- Phase III – Focused Analysis

- Total Management Audit Costs

## PHASE I – DIAGNOSTIC REVIEW

| Phase I Diagnostic Review |  |  |  |  |
| --- | --- | --- | --- | --- |
| Task Area: 1. Financial and Operating Statistics |  |  |  |  |
| Consultant | Role | Hours | Rate | Dollars |
| Vondle | Co-Project Manager | 64 | $225 | $14,400 |
| Whitman | Co-Project Manager | 112 | $225 | $25,200 |
| Mickey | Lead Consultant | 104 | $200 | $20,800 |
| Stein | Lead Consultant | 72 | $200 | $14,400 |
| Contacos-Sawyer | Lead Consultant | 36 | $225 | $8,100 |
| Wright | Support Consultant | 36 | $200 | $7,200 |
| Morgan | Lead Consultant | 204 | $200 | $40,800 |
| Doherty | Lead Consultant | 104 | $200 | $20,800 |
| Paxton | Lead Consultant | 104 | $200 | $20,800 |
| Collins | Administrative Manager | 96 | $100 | $9,600 |
| Total Hours and Fees |  | 932 |  | $182,100 |
| Personnel Expenses |  |  |  |  |
| Hotel |  |  |  | $9,057 |
| Per Diem |  |  |  | $4,528 |
| Air Transportation |  |  |  | $9,057 |
| Ground Transportation |  |  |  | $4,528 |
| Miscellaneous Expenses |  |  |  | $2,600 |
| Subtotal |  |  |  | $29,770 |
| Equipment* |  |  |  |  |
| Personal Computers |  |  |  | 0 |
| Printers |  |  |  | 0 |
| Project Management & Communication Software |  |  |  | 0 |
| Subtotal |  |  |  | 0 |
| Supplies & Materials* |  |  |  |  |
| Word Processing |  |  |  | 0 |
| Computer |  |  |  | 0 |
| Copying |  |  |  | 0 |
| Communication |  |  |  | 0 |
| Miscellaneous |  |  |  | 0 |
| Subtotal |  |  |  | 0 |
| Total Phase I Cost |  |  |  | $211,870 |

*Vondle & Associates, Inc. has no overhead charges.  All project related expenses are charged by a specific consultant as a discrete expense item with appropriate documentation on his or her monthly time and expense report.  Therefore, all non-travel expenses are shown as “Miscellaneous Personnel Expenses.”  There are no separate Equipment or Supplies and Materials charges.  Miscellaneous Personnel Expenses typically include report printing and shipping costs, overnight shipping charges, and other administrative type costs.

## PHASE II – PRE-IDENTIFIED AREAS OR ISSUES

Following are separate fee and expense tables for each of the six Phase II Pre-Identified areas or issues.

| Phase II Pre-Identified Areas or Issues |  |  |  |  |
| --- | --- | --- | --- | --- |
| Area 1. Governance |  |  |  |  |
| Consultant | Role | Hours | Rate | Dollars |
| Vondle | Co-Project Manager | 32 | $225 | $7,200 |
| Whitman | Co-Project Manager | 208 | $225 | $46,800 |
| Collins | Administrative Manager | 24 | $100 | $2,400 |
| Total Hours and Fees |  | 264 |  | $56,400 |
| Personnel Expenses |  |  |  |  |
| Hotel |  |  |  | $3,000 |
| Per Diem |  |  |  | $1,500 |
| Air Transportation |  |  |  | $3,000 |
| Ground Transportation |  |  |  | $1,500 |
| Miscellaneous Expenses |  |  |  | $1,000 |
| Subtotal |  |  |  | $10,000 |
| Equipment* |  |  |  |  |
| Personal Computers |  |  |  | 0 |
| Printers |  |  |  | 0 |
| Project Management & Communication Software |  |  |  | 0 |
| Subtotal |  |  |  | 0 |
| Supplies & Materials* |  |  |  |  |
| Word Processing |  |  |  | 0 |
| Computer |  |  |  | 0 |
| Copying |  |  |  | 0 |
| Communication |  |  |  | 0 |
| Miscellaneous |  |  |  | 0 |
| Subtotal |  |  |  | 0 |
| Total Task Area Cost |  |  |  | $66,400 |

*Vondle & Associates, Inc. has no overhead charges.  All project related expenses are charged by a specific consultant as a discrete expense item with appropriate documentation on his or her monthly time and expense report.  Therefore, all non-travel expenses are shown as “Miscellaneous Personnel Expenses.”  There are no separate Equipment or Supplies and Materials charges.  Miscellaneous Personnel Expenses typically include report printing and shipping costs, overnight shipping charges, and other administrative type costs.

| Phase II Pre-Identified Areas or Issues |  |  |  |  |
| --- | --- | --- | --- | --- |
| Area 2. Affiliate Relationships |  |  |  |  |
| Consultant | Role | Hours | Rate | Dollars |
| Vondle | Co-Project Manager | 240 | $225 | $54,000 |
| Whitman | Co-Project Manager | 40 | $225 | $9,000 |
| Collins | Administrative Manager | 24 | $100 | $2,400 |
| Total Hours and Fees |  | 304 |  | $65,400 |
| Personnel Expenses |  |  |  |  |
| Hotel |  |  |  | $3,600 |
| Per Diem |  |  |  | $1,800 |
| Air Transportation |  |  |  | $3,600 |
| Ground Transportation |  |  |  | $1,800 |
| Miscellaneous Expenses |  |  |  | $1,200 |
| Subtotal |  |  |  | $12,000 |
| Equipment* |  |  |  |  |
| Personal Computers |  |  |  | 0 |
| Printers |  |  |  | 0 |
| Project Management & Communication Software |  |  |  | 0 |
| Subtotal |  |  |  | 0 |
| Supplies & Materials* |  |  |  |  |
| Word Processing |  |  |  | 0 |
| Computer |  |  |  | 0 |
| Copying |  |  |  | 0 |
| Communication |  |  |  | 0 |
| Miscellaneous |  |  |  | 0 |
| Subtotal |  |  |  | 0 |
| Total Task Area Cost |  |  |  | $77,400 |

*Vondle & Associates, Inc. has no overhead charges.  All project related expenses are charged by a specific consultant as a discrete expense item with appropriate documentation on his or her monthly time and expense report.  Therefore, all non-travel expenses are shown as “Miscellaneous Personnel Expenses.”  There are no separate Equipment or Supplies and Materials charges.  Miscellaneous Personnel Expenses typically include report printing and shipping costs, overnight shipping charges, and other administrative type costs.

| Phase II Pre-Identified Areas or Issues |  |  |  |  |
| --- | --- | --- | --- | --- |
| Area 3. Customer Assistance Programs |  |  |  |  |
| Consultant | Role | Hours | Rate | Dollars |
| Vondle | Co-Project Manager | 32 | $225 | $7,200 |
| Stein | Lead Consultant | 168 | $200 | $33,600 |
| Collins | Administrative Manager | 24 | $100 | $2,400 |
| Total Hours and Fees |  | 224 |  | $43,200 |
| Personnel Expenses |  |  |  |  |
| Hotel |  |  |  | $2,100 |
| Per Diem |  |  |  | $1,050 |
| Air Transportation |  |  |  | $2,100 |
| Ground Transportation |  |  |  | $1,050 |
| Miscellaneous Expenses |  |  |  | $700 |
| Subtotal |  |  |  | $7,000 |
| Equipment* |  |  |  |  |
| Personal Computers |  |  |  | 0 |
| Printers |  |  |  | 0 |
| Project Management & Communication Software |  |  |  | 0 |
| Subtotal |  |  |  | 0 |
| Supplies & Materials* |  |  |  |  |
| Word Processing |  |  |  | 0 |
| Computer |  |  |  | 0 |
| Copying |  |  |  | 0 |
| Communication |  |  |  | 0 |
| Miscellaneous |  |  |  | 0 |
| Subtotal |  |  |  | 0 |
| Total Task Area Cost |  |  |  | $50,200 |

*Vondle & Associates, Inc. has no overhead charges.  All project related expenses are charged by a specific consultant as a discrete expense item with appropriate documentation on his or her monthly time and expense report.  Therefore, all non-travel expenses are shown as “Miscellaneous Personnel Expenses.”  There are no separate Equipment or Supplies and Materials charges.  Miscellaneous Personnel Expenses typically include report printing and shipping costs, overnight shipping charges, and other administrative type costs.

| Phase II Pre-Identified Areas or Issues |  |  |  |  |
| --- | --- | --- | --- | --- |
| Area 4. Executive Compensation |  |  |  |  |
| Consultant | Role | Hours | Rate | Dollars |
| Whitman | Co-Project Manager | 40 | $225 | $9,000 |
| Mickey | Support Consultant | 50 | $200 | $10,000 |
| Contacos-Sawyer | Lead Consultant | 60 | $225 | $13,500 |
| Wright | Support Consultant | 50 | $200 | $10,000 |
| Collins | Administrative Manager | 24 | $100 | $2,400 |
| Total Hours and Fees |  | 224 |  | $44,900 |
| Personnel Expenses |  |  |  |  |
| Hotel |  |  |  | $1,800 |
| Per Diem |  |  |  | $900 |
| Air Transportation |  |  |  | $1,800 |
| Ground Transportation |  |  |  | $900 |
| Miscellaneous Expenses |  |  |  | $600 |
| Subtotal |  |  |  | $6,000 |
| Equipment* |  |  |  |  |
| Personal Computers |  |  |  | 0 |
| Printers |  |  |  | 0 |
| Project Management & Communication Software |  |  |  | 0 |
| Subtotal |  |  |  | 0 |
| Supplies & Materials* |  |  |  |  |
| Word Processing |  |  |  | 0 |
| Computer |  |  |  | 0 |
| Copying |  |  |  | 0 |
| Communication |  |  |  | 0 |
| Miscellaneous |  |  |  | 0 |
| Subtotal |  |  |  | 0 |
| Total Task Area Cost |  |  |  | $50,900 |

*Vondle & Associates, Inc. has no overhead charges.  All project related expenses are charged by a specific consultant as a discrete expense item with appropriate documentation on his or her monthly time and expense report.  Therefore, all non-travel expenses are shown as “Miscellaneous Personnel Expenses.”  There are no separate Equipment or Supplies and Materials charges.  Miscellaneous Personnel Expenses typically include report printing and shipping costs, overnight shipping charges, and other administrative type costs.

| Phase II Pre-Identified Areas or Issues |  |  |  |  |
| --- | --- | --- | --- | --- |
| Area 5. Emergency Response |  |  |  |  |
| Consultant | Role | Hours | Rate | Dollars |
| Whitman | Co-Project Manager | 40 | $225 | $9,000 |
| Morgan | Lead Consultant | 200 | $200 | $40,000 |
| Collins | Administrative Manager | 24 | $100 | $2,400 |
| Total Hours and Fees |  | 264 |  | $51,400 |
| Personnel Expenses |  |  |  |  |
| Hotel |  |  |  | $2,700 |
| Per Diem |  |  |  | $1,350 |
| Air Transportation |  |  |  | $2,700 |
| Ground Transportation |  |  |  | $1,350 |
| Miscellaneous Expenses |  |  |  | $900 |
| Subtotal |  |  |  | $9,000 |
| Equipment* |  |  |  |  |
| Personal Computers |  |  |  | 0 |
| Printers |  |  |  | 0 |
| Project Management & Communication Software |  |  |  | 0 |
| Subtotal |  |  |  | 0 |
| Supplies & Materials* |  |  |  |  |
| Word Processing |  |  |  | 0 |
| Computer |  |  |  | 0 |
| Copying |  |  |  | 0 |
| Communication |  |  |  | 0 |
| Miscellaneous |  |  |  | 0 |
| Subtotal |  |  |  | 0 |
| Total Task Area Cost |  |  |  | $60,400 |

*Vondle & Associates, Inc. has no overhead charges.  All project related expenses are charged by a specific consultant as a discrete expense item with appropriate documentation on his or her monthly time and expense report.  Therefore, all non-travel expenses are shown as “Miscellaneous Personnel Expenses.”  There are no separate Equipment or Supplies and Materials charges.  Miscellaneous Personnel Expenses typically include report printing and shipping costs, overnight shipping charges, and other administrative type costs.

| Phase II Pre-Identified Areas or Issues |  |  |  |  |
| --- | --- | --- | --- | --- |
| Area 6. Diversity/Equal Employment Opportunities |  |  |  |  |
| Consultant | Role | Hours | Rate | Dollars |
| Whitman | Co-Project Manager | 40 | $225 | $9,000 |
| Mickey | Support Consultant | 50 | $200 | $10,000 |
| Contacos-Sawyer | Lead Consultant | 60 | $225 | $13,500 |
| Wright | Support Consultant | 50 | $200 | $10,000 |
| Collins | Administrative Manager | 24 | $100 | $2,400 |
| Total Hours and Fees |  | 224 |  | $44,900 |
| Personnel Expenses |  |  |  |  |
| Hotel |  |  |  | $1,800 |
| Per Diem |  |  |  | $900 |
| Air Transportation |  |  |  | $1,800 |
| Ground Transportation |  |  |  | $900 |
| Miscellaneous Expenses |  |  |  | $600 |
| Subtotal |  |  |  | $6,000 |
| Equipment* |  |  |  |  |
| Personal Computers |  |  |  | 0 |
| Printers |  |  |  | 0 |
| Project Management & Communication Software |  |  |  | 0 |
| Subtotal |  |  |  | 0 |
| Supplies & Materials* |  |  |  |  |
| Word Processing |  |  |  | 0 |
| Computer |  |  |  | 0 |
| Copying |  |  |  | 0 |
| Communication |  |  |  | 0 |
| Miscellaneous |  |  |  | 0 |
| Subtotal |  |  |  | 0 |
| Total Task Area Cost |  |  |  | $50,900 |

*Vondle & Associates, Inc. has no overhead charges.  All project related expenses are charged by a specific consultant as a discrete expense item with appropriate documentation on his or her monthly time and expense report.  Therefore, all non-travel expenses are shown as “Miscellaneous Personnel Expenses.”  There are no separate Equipment or Supplies and Materials charges.  Miscellaneous Personnel Expenses typically include report printing and shipping costs, overnight shipping charges, and other administrative type costs.

Total Phase II Costs

The following table summarizes the total costs for Phase II.

Total Phase II Costs

| Area | Area Name | Hours | Fees | Expenses | Total |
| --- | --- | --- | --- | --- | --- |
| II.1 | Governance | 264 | $56,400 | $10,000 | $66,400 |
| II.2 | Affiliate Relationships | 304 | $65,400 | $12,000 | $77,400 |
| II.3 | Customer Assistance Programs | 224 | $43,200 | $7,000 | $50,200 |
| II.4 | Executive Compensation | 224 | $44,900 | $6,000 | $50,900 |
| II.5 | Emergency Response | 264 | $51,400 | $9,000 | $60,400 |
| II.6 | Diversity/EEO | 224 | $44,900 | $6,000 | $50,900 |
|  | Phase II Total Costs | 1,504 | $306,200 | $50,000 | $356,200 |

## PHASE III – FOCUSED ANALYIS

As specified in the Request for Proposals, the Phase III costs are estimated at 50% of the Phase I costs, or $105,935.

## TOTAL MANANGEMENT AUDIT COSTS

The V&A total proposed management audit cost for all three phases of this project is $674,005.  The following table presents the total management audit costs in the RFP specified format.

Total Management Audit Costs

| Phase/Area | Area Name | Hours | Fees | Expenses | Total |
| --- | --- | --- | --- | --- | --- |
| I | Diagnostic Review | 932 | $182,100 | $29,770 | $211,870 |
| II | Pre-Identified Areas | 1,504 | $306,200 | $50,000 | $356,200 |
| III | Focused Analysis* | 466 | $91,050 | $14,885 | $105,935 |
|  | Project Total | 2,902 | $579,350 | $94,655 | $674,005 |

The consulting hour estimates are based upon eight hour days.  V&A consultants normally bill no more than eight hours in a single day.

## PHASE III AND TESTIMONY RATES

Additional work for Phase III focused analyses or for testimony arising from the management audit will be billed at the same fee rates as Phases I and II plus expenses at cost.

## EXPENSE MANAGEMENT

Every effort will be made to keep expenses to a minimum.  To contain expenses we plan to:

- Apply for government rates when making hotel reservations

- Make travel arrangements in advance as practical to qualify for airline discounts

- To minimize air and car travel expenses, each consultant will typically spend three to five days on-site during each trip to the Company

- Use available discounts when renting cars

## INVOICING

Vondle & Associates, Inc. invoices at the beginning of each month for the fees and expenses incurred the previous month.  All requested documentation will be provided.  Payment is due by the end of the month.