	[image: image2.png]



	COMMONWEALTH OF PENNSYLVANIA

PENNSYLVANIA PUBLIC UTILITY COMMISSION

P.O. BOX 3265, HARRISBURG, PA 17105-3265
	IN REPLY PLEASE REFER TO OUR FILE


March 3, 2017
A-2013-2374997
TO ALL PARTIES

Application of the Department of Transportation of the Commonwealth of Pennsylvania for the approval to alter the   grade crossing by the installation of automatically operated flashing-light railroad crossing warning signals with short arm gates where Diller Avenue crosses, at grade, (DOT No. 517 759 D) a single track of Norfolk Southern Railway Company in New Holland Borough, Lancaster County; all in accordance with the Federal Highway Grade Crossing Safety Program; and the allocation of costs incident thereto.  

To Whom It May Concern:

This matter is before us by reason of a petition filed November 4, 2016 by Norfolk Southern Railway Company, that seeks an extension of time to complete construction of the crossing involved in this proceeding.
By Secretarial Letter dated July 3, 2014, Norfolk Southern Railway Company was directed, among other things, to complete the project by December 31, 2015.  In a previous petition filed on December 18, 2015, Norfolk Southern Railway Company requested an extension of time due to issues with utilities in the area.  By Secretarial Letter dated April 25, 2016 the Commission granted an extension of time that established a revised completion date of December 31, 2016.  
In its petition filed November 4, 2016, Norfolk Southern Railway Company states that it has encountered further delays due to utility relocations and requests that the completion date be extended till March 31, 2017.  Due to the recurrence of the construction delays associated with this project the Commission will extend the completion date request from Norfolk Southern Railway Company to September 30, 2017.
On December 7, 2016 by letter to this Commission, Norfolk Southern Railway Company additionally requested a modification to the approved plans approved under a Secretarial Letter dated November 19, 2015.  
Norfolk Southern Railway Company states that the plans modification is necessary to avoid utility conflicts and to enhance the visibility of the railroad warning lights with respect to an adjacent business parking lot. 
Norfolk Southern Railway Company avers that each party to the proceeding was served with a copy of the plans for review.  None of the parties have advised this Commission that it objects to approval of the modified plans.
Upon a field review by Borough and Norfolk Southern field personnel it was agreed upon to adjust the location of the single mast pole in the northwest quadrant. By electronic email on February 23, 2017 the Commission received the sheet 1 replacement of Exhibit A reflecting this minor field adjustment.  
Upon full consideration of the matters involved, we determine that Norfolk Southern Railway Company’s request for an extension of time to complete alteration of the crossing will be granted in this instance and the modified plans will be approved.
The Commission issues this Secretarial Letter in accordance with Section 2702 of the Public Utility Code and finds that:
1.
The petition filed by Norfolk Southern Railway Company on November 4, 2016, be and is hereby granted.
2.
Paragraph 14 of the Secretary Letter dated July 3, 2014, modified on April 25, 2016, which reads as follows:

“14.
The alteration of the crossing be completed on 




or before December 31, 2016, and that on or before

                                  
said date, Norfolk Southern Railway Company 




report to this Commission the date of actual completion




of the work.”

be and is hereby modified to read as follows:

14.
The alteration of the crossing be completed on 




or before September 30, 2017, and that on or before

                                  
said date, Norfolk Southern Railway Company 




report to this Commission the date of actual completion




of the work.

3.
Norfolk Southern Railway Company, install the railroad warning devices and alter the public crossing (DOT 517 759 D) where proposed in New Holland Borough, Lancaster County, generally in accordance with the modified plans entitled: “Exhibit A” consisting of six (6) sheets, which were submitted to the Commission and all parties of record on December 7, 2016; which plans are made part hereof and are hereby approved except insofar as they may relate to the division of work, deletion of work, or the allocation of costs and expenses incident to the installation of the project.
4.
In all other aspects, our Secretarial Letter dated July 3, 2014, remains in full force and effect.


The Parties are reminded that failure to comply with this or any Order or Secretarial Letter in this proceeding may result in an enforcement action seeking civil penalties and/or other sanctions pursuant to 66 Pa. C.S. § 3301.
If you are dissatisfied with the resolution of this matter, you may, as set forth in 52 Pa. Code §§ 1.31 and 5.44, file a Petition for Reconsideration from Staff Action (Petition) with the Commission within twenty (20) days of the date of this letter.  The Petition shall be sent to: Secretary, PA Public Utility Commission, P.O. Box 3265, Harrisburg, PA 17105-3265, and must be filed within twenty (20) days, or if no timely request is made, the action will be deemed to be a final action of the Commission. 

The Petition MUST include: (1) a written statement (divided into numbered paragraphs) outlining the reasons for the request; (2) the case docket number (it is provided for you at the top right hand corner of this letter); (3) the party on whose behalf the petition is made; (4) a Certificate of Service on the other parties of record; and (5) a Verification with original signature in accordance with 52 Pa. Code § 1.36. 

[image: image1.png]P
POOO®

PENNSYLVANIA

PUC

PUBLIC UTILITY COMMISSION










Very truly yours,




Rosemary Chiavetta 




                                                Secretary 

                                       

