# PENNSYLVANIA

# PUBLIC UTILITY COMMISSION

# Harrisburg, PA 17105-3265

# Public Meeting held August 31, 2017

Commissioners Present:

Gladys M. Brown, Chairman

Andrew G. Place, Vice Chairman

John F. Coleman, Jr.

David W. Sweet

| Petition of Philadelphia Gas Works for Approval # of its Second Long-Term Infrastructure Improvement Plan for the Period Beginning September 1, 2017, and Ending August 31, 2022 | Docket Numbers: P-2017-2602315 |
| --- | --- |

# OPINION AND ORDER

BY THE COMMISSION:

Before the Commission for consideration is the Petition for approval of the Second Long-Term Infrastructure Improvement Plan (Second LTIIP) of Philadelphia Gas Works (PGW).  PGW filed its Second LTIIP on May 3, 2017.  Copies of the Second LTIIP were served on the statutory advocates and the parties of record from PGW’s most recent base rate case proceeding.  PGW also served a copy of the Second LTIIP on the parties of record for its petition regarding its request to increase its Distribution System Improvement Charge (DSIC) cap.

The Commission’s Bureau of Investigation and Enforcement (BIE) filed comments on June 2, 2017.  BIE did not oppose the Second LTIIP, but stated that it would be conducting an audit of PGW’s Distribution Integrity Management Plan (DIMP) in the third quarter of 2017.  BIE stated that if it was to find issues within the company’s DIMP, a revised Second LTIIP may need to be filed if those issues required a major modification (BIE Comments at 4 and 5).  BIE noted that it was concerned with the manner in which PGW was prioritizing funds for riskier pipeline replacement (BIE Comments at 5).

On July 31, 2017, PGW filed a letter (July 31 Letter) in response to BIE’s Comments.  In the July 31 Letter, PGW explained that BIE performed its audit of PGW’s DIMP on June 21, 2017.  PGW stated that BIE’s audit found that PGW’s DIMP and replacement expenditures allocation in its Second LTIIP were satisfactory, and that no revisions or major modifications to PGW’s Second LTIIP are necessary at this time.

No other comments were received.

BACKGROUND

On February 14, 2012, Governor Corbett signed into law Act 11 of 2012, (Act 11), which amends Chapters 3, 13 and 33 of Title 66.  Act 11, inter alia, provides jurisdictional water and wastewater utilities, electric distribution companies (EDCs), and natural gas distribution companies (NGDCs) or a city natural gas distribution operation with the ability to implement a DSIC to recover reasonable and prudent costs incurred to repair, improve or replace certain eligible distribution property that is part of the utility’s distribution system.  The eligible property for the utilities is defined in 66 Pa. C.S. §1351.  Act 11 states that as a precondition to the implementation of a DSIC, a utility must file a LTIIP with the Commission that is consistent with 66 Pa. C.S. §1352.

The Commission promulgated regulations relating to LTIIPs at 52 Pa. Code §§ 121.1 – 121.8 that became effective December 20, 2014.  In accordance with the regulations, an NGDC must include the following elements in its LTIIP:

- Types and age of eligible property;

- Schedule for its planned repair and replacement;

- Location of the eligible property;

- Reasonable estimates of the quantity of property to be improved;

- Projected annual expenditures and measures to ensure that the plan is cost      effective;

- Manner in which replacement of aging infrastructure will be accelerated and how repair, improvement or replacement will maintain safe and reliable service;

- A workforce management and training program; and

- A description of a utility’s outreach and coordination activities with other 			utilities, PennDOT and local governments on planned 						maintenance/construction projects.

PGW’S FIRST AND MODIFIED LTIIP

PGW’s First LTIIP was approved on April 4, 2013, and covered the fiscal years 2013 through 2017.  PGW’s 2017 fiscal year ends on August 31, 2017.  PGW's DSIC was approved on May 9, 2013.  On September 1, 2015, PGW filed its Petition for Waiver of Provisions of Act 11 to Increase the Distribution System Improvement Charge Cap and Permit Levelization of DSIC Charges (DSIC Cap Increase Petition) at Docket No. P-2015-2501500.

The DSIC Cap Increase Petition sought, inter alia, approval to increase the DSIC cap and to permit PGW to use an annualized, levelized charge as the basis for establishing a DSIC.  The Commission issued an Order on January 28, 2016, which, inter alia, authorized PGW to increase its DSIC cap to 7.5% of distribution revenues (including any reconciliation recovery); and directed PGW to file a petition to amend (referenced in the regulation as a petition to modify) its LTIIP detailing PGW’s proposed accelerated main replacement program and how it planned to expend the additional DSIC revenues.  PGW filed its petition for a Modified LTIIP on February 12, 2016.  The Modified LTIIP was approved on June 9, 2016, and replaced PGW’s First LTIIP and continued by its terms until August 31, 2017.

PGW’S SECOND LTIIP PETITION

PGW is owned by the City of Philadelphia and is the largest municipally owned gas utility in the country.  PGW is in the business of selling and distributing natural gas to retail customers within the Commonwealth of Pennsylvania, and is therefore a “city natural gas distribution operation” within the meaning of Section 102 of the Public Utility Code, 66 Pa. C.S. §§ 102, subject to the regulatory jurisdiction of the Commission.  PGW manages a distribution system of approximately 6,000 miles of gas mains and service lines supplying approximately 500,000 customers.

PGW’s Second LTIIP is a five-year plan covering the fiscal years 2018 through 2022.  PGW has removed or replaced approximately 111 miles of cast iron main with plastic and protected coated steel over the last 4 years based on the company’s Annual Asset Optimization Plans.  This is an average of nearly 28 miles per year.  PGW averred that the accelerated main replacement set forth in the Second LTIIP will, over time, reduce risk and costs compared to that which PGW would experience if it did not accelerate its pipeline replacement program.  PGW noted that the Second LTIIP would also result in more adequate, efficient, safe, reliable, and reasonable natural gas distribution service.

PGW identified categories of cast iron main that would be most suitable for replacement based on its risk management analysis programs.  PGW stated that the information used to formulate its Second LTIIP was primarily drawn from its DIMP, and the Benchmarking Summary Final Report dated January 28, 2016.

Based on the DIMP and the gas main replacement prioritization model and benchmarking analyses/studies, PGW identified property for replacement in its Second LTIIP as shown in Table 1, below.

Table 1: Property Classes Targeted for Replacement

| Asset Group | Material | Size | Pressure |
| --- | --- | --- | --- |
| Services | Steel | 1" - 1/4" and smaller | Low |
| Mains | Cast Iron | 10" and smaller | Low |
| Mains | Cast Iron | 12" and larger | High |
| Mains | Cast Iron | 12" and larger | Low |

PGW uses a Mains Replacement Prioritization (MRP) software package to determine the specific segments of the company’s system that will be replaced in each year.  The relative risk rankings from PGW’s DIMP are used to inform this software package and produce the appropriate mix of assets for replacement or removal from service.  If PGW’s Second LTIIP is approved, PGW estimates it will remove cast iron main from its inventory at a rate of approximately 31.7 miles per year, for a total of just over 158 miles over the span of the entire Second LTIIP.

PGW, in their petition, addressed the eight LTIIP elements required by 52 Pa. Code § 121.3, as discussed below:

(1) TYPES AND AGE OF ELIGIBLE PROPERTY

PGW’s Position

PGW’s distribution system contains approximately 3,000 miles of gas mains as well as approximately 478,000 service lines.  The total inventory mileage by age range for the cast iron main categories that PGW plans to target during the Second LTIIP is summarized in Table 2, below.  As seen in Table 2, PGW’s targeted cast iron main inventory totals approximately 1,400 miles.  PGW’s Second LTIIP is expected to replace over 158 miles of the target cast iron main.  PGW replaces bare steel service lines along with the coincident section of main as the main is being replaced.

Table 2 – Mileage of PGW’s Cast Iron Inventory by Age Range

| Year Range | 12” and Larger Cast Iron High Pressure (10-35 psig) | 12” and Larger Cast Iron Low Pressure (4.5" WC - 14" WC) | 8” and Smaller Cast Iron (4.5” WC - 5 psig) |
| --- | --- | --- | --- |
| 1971-2010 | 0.00 | 0.00 | 0.00 |
| 1961-1970 | 0.50 | 1.00 | 10.68 |
| 1951-1960 | 9.09 | 21.49 | 133.93 |
| 1941-1950 | 14.65 | 29.95 | 148.47 |
| 1931-1940 | 7.03 | 8.03 | 74.00 |
| 1921-1930 | 17.47 | 24.57 | 220.72 |
| 1911-1920 | 2.62 | 11.72 | 130.12 |
| 1900-1910 | 4.09 | 22.59 | 201.55 |
| Pre 1900 | 15.62 | 70.62 | 219.73 |
| Total | 71.07 | 189.97 | 1,139.2 |

Comments

In its Comments, BIE raised questions regarding PGW’s decision to include 12” and larger low pressure (LP) cast iron mains in its Second LTIIP, and whether the resources being devoted to these mains would be better spent on smaller diameter cast iron mains.

Resolution

As noted, above, PGW stated in its July 31 Letter that BIE determined PGW’s replacement expenditures allocation in its Second LTIIP were satisfactory, and that no revisions or major modifications to PGW’s Second LTIIP were necessary.

Upon review of PGW’s Second LTIIP, the Commission finds that PGW’s Second LTIIP fulfills the requirements of 52 Pa. Code § 121.3(a)(1) by identifying the types and ages of eligible property for which it seeks DSIC recovery.

(2) SCHEDULE FOR PLANNED REPAIR AND REPLACEMENT OF ELIGIBLE PROPERTY

PGW’s Position

PGW’s replacement program, beginning with PGW’s 2018 fiscal year, is detailed in Table 3, below.

Table 3: PGW’s Schedule for Miles of Main Replacement, FY 2018-2022

|  | FY 2018 | FY 2019 | FY 2020 | FY 2021 | FY 2022 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 8" and Smaller Low Pressure / Intermediate Pressure | 25.00 | 25.00 | 25.00 | 25.00 | 25.00 | 125.00 |
| 12" and Larger Low Pressure | 1.30 | 1.35 | 1.40 | 1.34 | 1.20 | 6.59 |
| 12" and Larger High Pressure | 5.50 | 5.50 | 5.30 | 5.25 | 5.15 | 26.70 |
| Abandonment for Non-Use | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Total | 31.80 | 31.85 | 31.70 | 31.59 | 31.35 | 158.29 |

Comments

No comments were received regarding the schedule for planned repair and replacement of eligible property.

Resolution

Upon review of PGW’s Second LTIIP, the Commission finds that PGW’s Second LTIIP fulfills the requirements of 52 Pa. Code § 121.3(a)(2) by providing a schedule for planned repair and replacement of eligible property.

(3) LOCATION OF THE ELIGIBLE PROPERTY

PGW’s Position

Eligible property is located throughout the City of Philadelphia as follows:

- Approximately 190 miles of 12” and larger LP cast iron main (4.5” WC to 14” WC).  PGW plans to remove 6.59 miles during the Second LTIIP period.

- Approximately 71 miles of 12” and larger high pressure (HP) cast iron main (10 to 35 psig).  PGW plans to remove 26.7 miles during the Second LTIIP period.

- Approximately 1,139 miles of 10” and smaller LP/Intermediate Pressure (IP) cast iron main (4.5” WC to 5 psig).  PGW plans to remove 125 miles during the Second LTIIP period.

Comments

No comments were received regarding the location of eligible property.

Resolution

Upon review of PGW’s Second LTIIP, the Commission finds that PGW’s Second LTIIP fulfills the requirements of 52 Pa. Code § 121.3(a)(3) by providing a general description of the location of eligible property.

(4) REASONABLE ESTIMATES OF THE QUANTITY OF PROPERTY TO BE IMPROVED and

(5) PROJECTED ANNUAL EXPENDITURES AND MEASURES TO ENSURE THAT THE PLAN IS COST EFFECTIVE

(6) ACCELERATED REPLACEMENT AND MAINTAINING SAFE AND RELIABLE SERVICE

PGW’s Position

PGW’s baseline main replacement program removes 18 miles of 8” or smaller cast iron main annually.  PGW will seek recovery, via its DSIC mechanism, for expenditures above the cost of the baseline program on a pay-as-you-go basis.  The DSIC mechanism is normally used to recover the return on capital placed in service by a utility.  PGW does not operate under the normal rate of return regulatory framework and had been recovering actual one-for-one expenditures through its DSIC.  However, PGW found that the construction season, typically Spring and Summer, did not match the high gas usage times of late Fall and Winter.  This made it difficult for PGW to capture the required revenues as customer bills, for those not on budget billing, are much lower in Spring and Summer.  With its DSIC cap waiver, PGW was granted the ability to charge a levelized DSIC throughout the year.  PGW states that it will utilize its approved 7.5% DSIC surcharge for the recovery of approximately $33 million per year.  PGW does not plan to issue any long-term debt to fund its accelerated main replacement program at this time.  Tables 4 and 5, below, detail the quantities of property to be improved for each year of the Second LTIIP and the projected expenditures, respectively.

Table 4 – Quantity of Property to Be Improved (Miles), FY 2018-2022

|  | FY 2018 | FY2019 | FY 2020 | FY 2021 | FY 2022 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| CURRENT BASELINE PROGRAM |  |  |  |  |  |  |
| 8" and Smaller LP/IP | 18.00 | 18.00 | 18.00 | 18.00 | 18.00 | 90.00 |
| ACCELERATED PROGRAM |  |  |  |  |  |  |
| 8" and Smaller LP/IP | 7.00 | 7.00 | 7.00 | 7.00 | 7.00 | 35.00 |
| 12" and Larger LP | 1.30 | 1.35 | 1.40 | 1.34 | 1.20 | 6.59 |
| 12" and Larger HP | 5.50 | 5.50 | 5.30 | 5.25 | 5.15 | 26.70 |
| Abandonment for Non-Use | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Accelerated Total | 13.80 | 13.85 | 13.70 | 13.59 | 13.35 | 68.29 |
| Annual Total | 31.80 | 31.85 | 31.70 | 31.59 | 31.35 | 158.29 |

Table 5 – Annual Projected Expenditures on Main Replacement, FY 2018-2022

|  | FY 2018 | FY2019 | FY 2020 | FY 2021 | FY 2022 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| CURRENT BASELINE PROGRAM |  |  |  |  |  |  |
| 8" and Smaller LP/IP | $21,003,840 | $21,384,000 | $21,859,200 | $22,239,360 | $22,714,560 | $109,200,960 |
| ACCELERATED PROGRAM |  |  |  |  |  |  |
| 8" and Smaller LP/IP | $8,168,160 | $8,316,000 | $8,500,800 | $8,648,640 | $8,833,440 | $42,467,040 |
| 12" and Larger LP | $4,456,320 | $4,760,870 | $5,188,681 | $5,026,051 | $4,657,922 | $24,089,844 |
| 12" and Larger HP | $20,446,800 | $20,249,856 | $19,575,227 | $19,653,148 | $20,289,108 | $100,214,139 |
| Abandonment for Non-Use | $0 | $0 | $0 | $0 | $0 | $0 |
| Accelerated Total | $33,071,280 | $33,326,726 | $33,264,708 | $33,327,839 | $33,780,470 | $166,771,023 |
| Annual Total | $54,075,120 | $54,710,726 | $55,123,908 | $55,567,199 | $56,495,030 | $275,971,983 |

PGW contends that its pay-as-you-go method is the most cost effective way to fund its main replacement program, as compared to the issuance of long-term bonds.  PGW explains that it utilizes a competitive bidding process for all relevant aspects of its pipeline replacement program, and prioritizes work based on those segments of main that are most likely to leak and/or break while in service.  The company also avers that its program is cost effective by reducing PGW’s maintenance costs over time, as the number of leaks and breaks in mains is reduced by replacing the sections of main before they fail.

The approval of PGW’s first LTIIP required PGW to file quarterly reports detailing certain reliability and safety metrics, including information on leaks and leak repairs.  Figures 1 and 2, below, are based on the data in these reports and show a slight downward trend in total leaks on PGW’s system, as well as the number of leaks repaired.

PGW’s replacement program will noticeably reduce the company’s timeline to remove all cast iron mains from their system, down from 136 years to 45 years.

Comments

No comments were received regarding the reasonable estimates of the quantity or expenditures of property to be improved, cost effectiveness, or the manner in which infrastructure replacement will be accelerated.

Resolution

Upon review of PGW’s Second LTIIP, the Commission finds that PGW’s Second LTIIP fulfills the requirements of 52 Pa. Code §§ 121.3(a)(4)-(6) by providing reasonable estimates of the quantity of property to be improved, the projected annual expenditures and means to finance the expenditures, and a description of the manner in which infrastructure replacement will be accelerated and how repair, improvement, or replacement will ensure and maintain adequate, efficient, safe, reliable, and reasonable service to customers.

(7) WORKFORCE MANAGEMENT AND TRAINING PROGRAM

PGW’s Position

PGW’s Second LTIIP outlines the measures it undertakes to ensure a skilled work force to perform operations, maintenance, and construction activities on the company’s distribution system.  PGW states that their employees are trained and qualified to the standards set forth by the US Department of Transportation’s Pipeline and Hazardous Materials Safety Administration.  PGW also utilizes the Northeast Gas Association’s Gas System Operator Qualification Plan.

PGW explains that they have a dedicated Training Section, with a program that ensures employee competence through evaluations.  PGW notes its makes sure that each employee can perform the necessary tasks, recognize and respond appropriately to abnormal operating conditions, and that it maintains necessary records of their work.

PGW described the range of training provided, including classroom training in addition to simulated and actual field training.  PGW also notes that they provide annual training for all field and management personnel, covering tasks such as:

- Proper trench and shoring techniques

- Leak investigation and mitigation practices

- Damage prevention methodologies

- Proper use of gas detection equipment

- Plastic pipe fusion qualifications

- Steel pipe welding qualifications

- Proper respirator use

PGW states that their most recent Collective Bargaining Agreement allows outside contractors to perform live gas work on the PGW system.  PGW avers the company’s Training Section ensures that contractors are properly qualified for live gas work.

Comments

No comments were received regarding the workforce management and training program.

Resolution

Upon review of the Second LTIIP, the Commission finds that PGW’s Second LTIIP fulfills the requirements of 52 Pa. Code § 121.3(a)(7) by providing a workforce management and training program that is designed to ensure that PGW will have access to a qualified workforce to perform the work in a cost-effective, sage and reliable manner.

(8) DESCRIPTION OF OUTREACH AND COORDINATION ACTIVITIES WITH OTHER UTILITIES, PENNDOT AND LOCAL GOVERNMENTS ON PLANNED PROJECTS

PGW’s Position

PGW describes its coordination with outside agencies in conjunction with its replacement of mains and services affected by others.  PGW specifically notes that it frequently coordinates work with the Philadelphia Water Department’s water and sewer main replacements, PennDOT’s highway construction projects, and the City of Philadelphia’s paving projects.  PGW explains that they have several checks and balances to help avoid potential conflicts for each project.  PGW cites examples including Design One Calls, the City of Philadelphia’s Gas Plant Information System (GPIS) permitting system, and meetings with the Committee of Highway Supervisors.

PGW states that they utilize the City’s GPIS permitting system to identify conflicts with various paving programs.  PGW describes how it enters multiple years of proposed replacement projects at a very preliminary stage, which allows the identification of conflicts far in advance.

When conflicts are identified with any outside agencies, PGW explains that coordination meetings are arranged.  The proposed infrastructure improvements are then overlaid onto PGW’s Detail Main Maps to determine the extent of the conflict.  Once this is done, PGW considers a number of factors to determine whether its facilities will be replaced.

Comments

No comments were received regarding the description of outreach and

coordination activities with other utilities, PennDOT and local governments on planned projects.

Resolution

Upon review of the Second LTIIP, the Commission finds that PGW’s Second LTIIP fulfills the requirements of 52 Pa. Code § 121.3(a)(8) by providing a description of PGW’s outreach and coordination activities with other utilities, PennDOT and local governments on planned projects and roadways that may be impacted by the Second LTIIP.

SECOND LTIIP SUMMARY

The Commission’s review of an LTIIP must determine if the LTIIP:

- Contains measures to ensure that the projected annual expenditures are cost-effective.

- Specifies the manner in which it accelerates or maintains an accelerated rate of infrastructure repair, improvement or replacement.

- Is sufficient to ensure and maintain adequate, efficient, safe, reliable and reasonable service.

- Meets the requirements of 52 Pa. Code § 121.3(a).

The utility has the burden of proof to demonstrate that its proposed LTIIP and associated expenditures are reasonable, cost effective and designed to ensure and maintain sufficient, safe, adequate, reliable and reasonable service to consumers.

The Commission has reviewed PGW’s Second LTIIP and any resulting comments.  The Commission finds that PGW has meet its burden of proof by demonstrating that its Second LTIIP contains measures to ensure that the projected annual expenditures are cost-effective, specifies the manner in which it accelerates or maintains an accelerated rate of infrastructure repair, improvement, or replacement, is sufficient to ensure and maintain adequate, safe, reliable, and reasonable service, and meets the requirements of 52 Pa. Code § 121.3(a).  Accordingly, PGW’s Second LTIIP is approved.

The Commission finds PGW’s Second Long-Term Infrastructure Improvement Plan and manner in which it was filed conforms to the requirements of Act 11 and our Regulations.  The plan, as approved herein, is designed to maintain safe, adequate and reliable service and, as such, PGW shall be required to comply with the infrastructure replacement schedule and elements of that plan; THEREFORE,

IT IS ORDERED:

1.	That the Petition for Approval of a Second Long-Term Infrastructure Improvement Plan filed by Philadelphia Gas Works is approved, consistent with this Order.

2.	That the proceeding at Docket No. P-2017-2602315 be closed.

BY THE COMMISSION,

Rosemary Chiavetta

Secretary

(SEAL)

# ORDER ADOPTED: August 31, 2017

# ORDER ENTERED:  August 31, 2017

Docket No. R-2017-2586783.

See Docket No. P-2015-2501500.

See 52 Pa. Code § 121.5(a).

http://www.legis.state.pa.us/WU01/LI/LI/US/HTM/2012/0/0011..HTM.

See 52 Pa. Code § 121.3.

See Petition of Philadelphia Gas Works for Approval of its Long-Term Infrastructure Plan, Order entered April 4, 2013, at Docket No. P-2012-2337737.

See Petition of Philadelphia Gas Works for Approval of a Distribution System Improvement Charge, Order entered May 9, 2013 at Docket No. P-2012-2337737.

See Docket No. P-2015-2501500.

See Petition of Philadelphia Gas Works for Approval of a Modified Long-Term Infrastructure Improvement Plan, Order entered June 9, 2016, at Docket No. P-2015-2501500.

See also 66 Pa. C.S. § 2212, relating to city natural gas distribution operations.

PGW owns and operates all the service lines from the mains to the meters.  There are no customer-owned service lines in the PGW territory.  Service lines are also referred to as services.

See Docket Nos. M-2014-2417231, M-2015-2484331, M-2015-2518294, and M-2016-2573637.

See Appendix A of PGW’s Petition for Modification of Long-Term Infrastructure Improvement Plan, filed on February 12, 2016, at Docket No. P-2012-2337737.

psig – Pounds per square inch gauge.  This is a measure of pressure relative to atmospheric pressure.

WC – Inches of Water Column.  This is a unit of pressure used to measure low pressures.  27.7 WC is approximately equal to 1 psi (pound per square inch).

See Docket No. P-2015-250150.

See Petition of Philadelphia Gas Works for Approval of Its Long Term Infrastructure Improvement Plan, Order entered April 4, 2013, at Docket No. P-2012-2337737.

See 49 CFR 192 Subpart N.

See 52 Pa. Code § 121.4(e).

See 52 Pa. Code § 121.4(d).