# PENNSYLVANIA

# PUBLIC UTILITY COMMISSION

# Harrisburg, PA 17105-3265

# Public Meeting held August 27, 2020

Commissioners Present:

Gladys Brown Dutrieuille, Chairman

David W. Sweet, Vice Chairman

John F. Coleman, Jr.

Ralph V. Yanora

| Petition of Pittsburgh Water and Sewer Authority for Approval of its Amended Long-Term Infrastructure Improvement Plan for Wastewater Operations | Docket Number: P-2018-3005039 |
| --- | --- |

# OPINION AND ORDER

BY THE COMMISSION:

Before the Commission for consideration is the Petition for approval of the Amended Long-Term Infrastructure Improvement Plan (Amended LTIIP) of the Pittsburgh Water and Sewer Authority (PWSA) for its Wastewater Operations, Utility Code 2320555.  PWSA filed its original LTIIP Petition on September 28, 2018.  As detailed below, on April 27, 2020, PWSA filed its Amended LTIIP pursuant to the Commission’s March 26, 2020 Order.  Both the original and Amended LTIIPs addressed water and wastewater operations and were docketed accordingly.  Copies of the Amended LTIIP were served on the statutory advocates and the parties of record from PWSA’s most recent base rate case proceeding.  The Amended LTIIP did not include any of the unchanged Appendices that were submitted with PWSA’s initial LTIIP filing on September 28, 2018.  As a result, on July 7, 2020, PWSA filed an Amended LTIIP that includes all appendices including those unchanged from the initial filing and those revised as part of the April 27, 2020 filing.

HISTORY OF THE PROCEEDING

On September 28, 2018, PWSA filed its original LTIIP, which was docketed at Docket Nos. P-2018-3005037 (water) and P-2018-3005039 (wastewater), along with its Compliance Plan at Docket Nos. M-2018-2640802 (water) and M-2018-2640803 (wastewater).  These proceedings were subsequently consolidated, upon motion by the PWSA, and were consolidated at Docket No. M-2018-2640802.

By Corrected Secretarial Letter dated November 28, 2018, the Commission assigned the consolidated matters, including the LTIIP, to the Office of Administrative Law Judge (OALJ) for hearings and established a two-stage review process for PWSA’s Compliance Plan.

On March 26, 2020, the Commission entered an Order that, inter alia, modified and approved the Joint Petition for Partial Settlement (Partial Settlement) filed by the Pittsburgh Water and Sewer Authority, the Bureau of Investigation and Enforcement of the Pennsylvania Public Utility Commission, the Office of Consumer Advocate, the Office of Small Business Advocate, Pittsburgh UNITED and Pennsylvania-American Water Company on September 19, 2019, as well as directed PWSA to file an amended LTIIP.  The Partial Settlement dispensed several matters in the PWSA Compliance Plan, including that of the original LTIIP.  PWSA filed its Amended LTIIP on April 27, 2020, to the same docket numbers as the original LTIIP.

No comments were filed to the Amended LTIIP.  All parties have had ample opportunity to address any LTIIP concerns through the adjudication process of the Compliance Plan and no new comments were filed to the amended LTIIP.  Therefore, we shall not address any comments that were filed to the original LTIIP in this Order.

BACKGROUND

Effective February 14, 2012, Act 11 of 2012, (Act 11) provides jurisdictional water and wastewater utilities, electric distribution companies (EDCs), and natural gas distribution companies (NGDCs) or a city natural gas distribution operation with the ability to implement a Distribution System Improvement Charge (DSIC) to recover reasonable and prudent costs incurred to repair, improve or replace certain eligible distribution property that is part of the utility’s distribution system.  The eligible property for the utilities is defined in 66 Pa. C.S. §1351.  Act 11 states that as a precondition to the implementation of a DSIC, a utility must file a LTIIP with the Commission consistent with 66 Pa. C.S. §1352.

The Commission promulgated regulations relating to LTIIPs at 52 Pa. Code §§ 121.1 – 121.8 that became effective December 20, 2014.  In accordance with the regulations, DSIC-eligible utilities must include the following elements in an LTIIP:

- Types and age of eligible property;

- Schedule for planned eligible property repair and replacement;

- Location of the eligible property;

- Reasonable estimates of the quantity of property to be improved;

- Projected annual expenditures and measures to ensure that the plan is cost      effective;

- Manner in which replacement of aging infrastructure will be accelerated and how repair, improvement or replacement will maintain safe and reliable service;

- A workforce management and training program; and

- A description of a utility’s outreach and coordination activities with other 			utilities, PennDOT and local governments on planned 						maintenance/construction projects.

PWSA’S AMENDED LTIIP

PWSA is an authority as defined in 66 Pa. C.S. § 3201 and therefore is regulated in the same manner as a public utility, pursuant to 66 Pa. C.S. § 3202(a).  PWSA through its wastewater operations collects and conveys wastewater in a largely combined sewer and stormwater system for the City of Pittsburgh (City) and 24 neighboring suburban municipalities to the interceptors for the Allegheny County Sanitary Authority (ALCOSAN).  PWSA through its water operations also treats and provides water to over 300,000 people throughout the City and surrounding areas, Utility Code 2220554.

PWSA’s wastewater collection system is comprised of a network of approximately 1,213 miles of sanitary, storm, and combined sewers.  These conveyance pipes are located along the rivers and tributaries that deliver the flow to ALCOSAN’s wastewater treatment facility (WWTF) for treatment prior to discharge into the Ohio River.  PWSA’s system also includes: 29,000 manholes, including flow dividers and diversion chambers; approximately 30,000 inlets, including catch basins and storm inlets; 38 combined sewer overflow (CSO) outfalls; 185 storm sewer outfalls; four wastewater pump stations; and ancillary facilities.

PWSA states that approximately 77% of their sewer system is combined sewers, designed so that during wet weather events, a portion of the collected stormwater and diluted wastewater that exceeds the ALCOSAN conveyance and treatment capacity is discharged into natural watercourses through 98 CSO diversion chambers.  PWSA notes approximately 23% of the sewer system consists of separate sewers that are dedicated separate sanitary and storm sewer pipelines.

PWSA’s Amended LTIIP is for the fiscal years (FY) 2019 through 2023 with projected DSIC-eligible spending for those years of approximately $603 million for water, sewer, and hybrid programs.  PWSA’s overall 5-year Capital Improvement Plan (CIP) from FY 2019-2023 includes significant investments in the water, sewer and stormwater systems to address aging infrastructure, improvements necessary to meet regulatory requirements, and improve infrastructure reliability and performance.  PWSA has an overall 5-year budget of approximately $775 million, including non DSIC-eligible property.

PWSA notes that the wastewater system renewal priorities in the CIP include: relocation of sewers under structures to reduce failure risk (including consequential damages) of service disruptions and improve performance; projects to remove stormwater inflows and groundwater infiltration from the existing sanitary sewer system; and general sewer rehabilitation of the sewer system to improve the structural condition of the assets.  The 5-year budget for DSIC-eligible property in these areas is approximately $138 million.

PWSA reports the CIP also includes a smaller number of “hybrid” projects, defined as those that contain both water and sewer elements or sanitary and storm sewer elements.  PWSA notes that it cannot effectively segregate the costs for these projects between water and wastewater.  The 5-year budget for DSIC-eligible property for hybrid projects is approximately $7.3 million.

PWSA’s CIP also includes stormwater system priorities as well.   The highlights include stormwater projects such as: the 4-Mile Run stream separation project; separated stormwater sewer upgrades including water quality management systems to reduce siltation and errant sewer connections; and stormwater water detention projects to help mitigate peak stormwater flow impacts on the combined sewer systems and to reduce CSO and sanitary sewer overflows (SSOs).  These stormwater impacts primarily include basement sewage backups and localized street flooding.  Approximately $245 million has been allocated to address priority issues in the stormwater area.

PWSA reports that despite its ongoing effort and substantial actual and planned expenditures, drainage and infrastructure problems are numerous, with surface flooding and sewer system basement backups the most visible issues.

PWSA, in its petition, addressed the 8 LTIIP elements required by 52 Pa. Code § 121.3, as discussed below:

(1) TYPES AND AGE OF ELIGIBLE PROPERTY

PWSA’s Position

PWSA’s eligible property associated with its sewer system consists of approximately 1,080 miles of sewer comprising separate sanitary and combined sanitary and storm, overflows, and sanitary force mains.  Approximately three-quarters of PWSA’s sewers are combined pipes that carry both sanitary and storm flows.  The eligible property within PWSA’s system includes lift stations also referred to as pump stations.  PWSA operates and maintains the following four sanitary sewer lift stations: Browns Hill Road Pump Station, Evergreen Road Pump Station, Mifflin Road Pump Station, and Rodgers Street Pump Station.

PWSA provided substantial detail on the material composition and age of their pipes, mains and services in its Amended LTIIP to include:

- Sewer length by type (miles)

- Sewer length by diameter (miles)

- Sewer length by material construction (miles)

PWSA notes that it has three eligible property project categories that they have categorized as hybrid projects to include:

- Utility Cost Shares: Infrastructure replacement which is carried out as a result of projects in the vicinity by other agencies or utilities.

- Smallman Street Reconstruction: Sewer separation and water main replacement in association with local redevelopment.

- Maytide Storm and Sanitary Sewer System Improvements: described as reconstruction and realignment of local storm and sanitary sewers.

PWSA states that not all eligible property is currently logged into their Geographic Information Systems (GIS), and that PWSA’s database is being updated constantly.  PWSA maintains that the data upload to the GIS system is an on-going effort, and the statistics may change as a result of ongoing system data review and clean-ups.

Table1 below details PWSA’s Sewer System Eligible Properties to be repaired, improved or replaced through the Amended LTIIP.

Table 1: Sewer System DSIC-Eligible Project Categories

| Project Name | Project Descriptions |
| --- | --- |
| Small Diameter Sewer Rehabilitation | Proactive, trenchless rehabilitation of less than 36-inch diameter sewer mains to restore structural integrity, reduce root intrusion, and reduce infiltration and inflow, includes cleaning, pre and post construction CCTV inspections, and if necessary, excavated point repairs and manhole rehabilitation. Provides the Authority a means to address inflow and infiltration and several moderate/major structural defects in a pipe segment prior to complete failure. This trenchless pipe renewal method eliminates disruptive digging and restoration and is cost effective. |
| Large Diameter Sewer Rehabilitation | Proactive, trenchless rehabilitation of 36-inch diameter or greater sewer mains to restore structural integrity, reduce root intrusion, and reduce infiltration and inflow, includes cleaning and pre and post construction CCTV inspections. Provides the Authority a means to address several moderate/major structural defects in a pipe segment prior to complete failure. This trenchless pipe renewal method eliminates disruptive digging and restoration and is cost effective. |
| Sewer Reconstruction (Annual IDIQ Contracts) | Reconstruction of existing sewers, manholes, catch basins, and inlets due to emergency situations or pipe failures. |
| Sewers Under Structures | Rehabilitation, relocation, and abandonment, if applicable, of existing sewer infrastructure located under or adjacent to buildings, bridges, or railroads or located on steep slopes. |
| Utility Cost Shares | Infrastructure replacement due to coordination with other agencies or utilities. Coordination with other utilities can reduce expenditures up to 75% of the total project cost and reduces the length of time that the public is inconvenienced due to construction efforts. |
| Tide Gate Installations | Installation of tide gates at 44 combined sewer overflow diversion chamber locations to assist in preventing river water intrusion. |
| 2019 Wastewater System Improvements | Reconstruction of existing structurally deficient sewer mains on Wiese Street, Wilbur Street, Creedmoor Avenue, Ornament Way, Cooperfield Avenue, N. Sheridan Avenue, Port Way, and Swimburne Street. |
| 31st Ward Sewer System | Evaluation to identify and locate the source(s) of the infiltration and inflow (I/I), removal of public I/I sources, and rehabilitation/replacement of the Rogers Street and Mifflin Road Pump Station and force main. Project will be designed and constructed in a minimum of two phases to ensure the pump stations are properly sized and the flow conveyed will not negatively impact the downstream sewer sub shed. |
| Ivyglen and Odette Sewer Reconstruction and Separation Project | Installation of a new sanitary sewer and storm sewer on Odette and Ivyglen, which will eliminate the combined sewer outfall and a sewer on an unstable slope. |

Comments

No comments were received regarding the types and age of eligible property.

Resolution

Upon review of PWSA’s Amended LTIIP, the Commission finds that PWSA’s Amended LTIIP fulfills the requirements of 52 Pa. Code § 121.3(a)(1) by identifying the types and ages of eligible property for which it seeks DSIC recovery.

(2) SCHEDULE FOR PLANNED REPAIR AND REPLACEMENT OF ELIGIBLE PROPERTY

PWSA’s Position

PWSA states that in order to cost-effectively prioritize future sanitary sewer rehabilitation, they will employ a risk-based approach to prioritize the neighborhoods and/or pipe segments that are included in the annual projects, where risk is defined as: “Risk = Likelihood of Failure X consequence of Failure X Redundancy.”

PWSA notes that this analysis will assign a risk score to each pipe segment within its system when complete.  PWSA further notes that to reduce the impact to customers and save on mobilization and demobilization costs, projects will be formed by grouping prioritized assets by geographic proximity and similar risk rankings.

PWSA plans to accomplish this cost-effective prioritization by performing a GIS desktop analysis, which is anticipated to be completed by the first quarter of 2021.  This analysis will assign a risk score to each pipe segment within its system when complete.  PWSA notes projects will be formed by grouping prioritized assets by geographic proximity and similar risk ranking in order to reduce the impact to customers and save on mobilization and demobilization costs.

PWSA states that this approach will ensure the success of the program, measured in large part by cost savings.  PWSA states that it recognizes the need for continual renewal of its sewer collection and conveyance system to maintain quality and reliable service to its customers.  PWSA notes that little sewer system investment other than annual repair construction contracts and a few miles of sewer separation has been made to the PWSA sewer system in the past 20 years.

PWSA reports that it has established three annual rehabilitation and pipe reconstruction project types to accelerate the renewal of its wastewater system to include:

- Sewers Under Structures

- Small Diameter Sewer Rehabilitation

- Large Diameter Sewer Rehabilitation

PWSA reports that its sewers under structures will target existing sewer infrastructure located under or adjacent (within 20 feet) to buildings, bridges, or railroads or located on steep slopes.  PWSA maintains that its Small and Large Diameter Sewer Rehabilitation projects will utilize cost effective trenchless technologies to restore the structural integrity, reduce root intrusion, and reduce infiltration and inflow on mains less than 36-inch in diameter and 36- inch diameter or greater, respectively.

PWSA did not provide detailed projections of actual eligible property to be repaired or replaced beyond FY 2020 as it will rely on its risk-based approach to prioritize the specific areas in its system in the three project types noted above.  Table 3-6 of Appendix B of the Amended LTIIP provides detail on actual and projected expenditures by FY from 2018-2023.  Table 4-2 of Appendix B provides detail on the hybrid actual and planned spending for PWSA’s hybrid projects.

Comments

No comments were received regarding the schedule for planned repair and replacement of eligible property.

Resolution

Upon review of PWSA’s Amended LTIIP, the Commission finds that PWSA’s Amended LTIIP fulfills the requirements of 52 Pa. Code § 121.3(a)(2) by providing a schedule for planned repair and replacement of eligible property.

(3) LOCATION OF THE ELIGIBLE PROPERTY

PWSA’s Position

PWSA in its Amended LTIIP notes that work on water, wastewater, and hybrid programs will occur throughout PWSA’s service territory in the City.  As noted in element 2 discussed above, PWSA’s risk model will determine specific locations for work for each FY.

Comments

No comments were received regarding the location of eligible property.

Resolution

Upon review of PWSA’s Amended LTIIP, the Commission finds that PWSA’s Amended LTIIP fulfills the requirements of 52 Pa. Code § 121.3(a)(3) by providing a general description of the location of eligible property.

(4) REASONABLE ESTIMATES OF THE QUANTITY OF PROPERTY TO BE IMPROVED and

(5) PROJECTED ANNUAL EXPENDITURES AND MEASURES TO ENSURE THAT THE PLAN IS COST EFFECTIVE

PWSA’s Position

As noted in element 3, above, PWSA did not provide detailed projections of actual eligible property to be repaired or replaced beyond FY 2020 as the risk model will determine specific areas of focus.  PWSA’s Amended LTIIP notes that its 40-Year Plan dated September 2012 estimated the resources needed for capital improvements to PWSA’s system.  PWSA’s 40-Year Plan identified upgrades to maintain and enhance the performance of the water and sewer systems.  PWSA notes that cost estimates were developed in the 40-Year Plan for distribution system improvements, pumping and storage facilities, treatment facilities, sewers, and GIS improvements based upon regional cost information available at that time.  PWSA notes that much of the information originally contained in the 40-Year Plan, including updated capital cost estimates, has been revised and updated since its release.

PWSA maintains that the increase in the volume of capital project delivery planned for the next 5 years demands an ever-increasing level of management excellence to achieve the efficiencies necessary to meet the challenge of adhering to project budgets and schedules.  Table 3-6 of Appendix B of the Amended LTIIP provides detail on actual and projected expenditures by FY from 2018-2023.  Table 4-2 of Appendix B provides detail on the hybrid actual and planned spending for PWSA’s hybrid projects.  PWSA identifies the costs associated with the projects for each year of the project schedule by the project types identified in element 2, above.  Table 2, below, details the Historical (2014-2019) and projected (2020-2023) FY capital spending for eligible property for water, sewer, and hybrid projects.

Table 2: Historical (2014-2019) and Projected (2020-2023) FY Capital Spending (in Thousands of Dollars)

| Fiscal Year | Water Projects | Sewer Projects | Hybrid Projects | Total Eligible |
| --- | --- | --- | --- | --- |
| 2014 | $3,177 | $400 | $1,983 | $5,560 |
| 2015 | $998 | $4,186 | $10,040 | $15,225 |
| 2016 | $894 | $1,305 | $5,777 | $7,976 |
| 2017 | $4,331 | $2,476 | $8,330 | $15,137 |
| 2018 | $28,002 | $2,599 | $5,547 | $36,148 |
| 2019 | $47,071 | $3,586 | $73 | $50,730 |
| 2020 | $71,887 | $33,283 | $500 | $105,670 |
| 2021 | $103,975 | $39,142 | $3,000 | $146,117 |
| 2022 | $125,908 | $30,551 | $3,000 | $159,459 |
| 2023 | $108,401 | $31,392 | $750 | $140,543 |
| Total | $494,644 | $148,920 | $39,000 | $682,565 |

PWSA states that there is a need for a comprehensive and systematic approach to the delivery of the accelerated capital improvements program.  PWSA notes it has implemented and is continuously improving several tools that will ensure the cost-effective and efficient planning, design, procurement, construction, and close-out of projects.  These tools include the e-Builder project management information system, the Program Management Plan (PMP), and contractor procurement process.  PWSA maintains that cost effectiveness will be ensured by the selection of the appropriate construction techniques such as trenchless construction during the planning stages of a project.

PWSA states that its currently planned Amended LTIIP improvements will be funded through both current rates and future rate increases, and financed through revenue bonds, a capital line of credit, pay-as-you-go (PAYGO) funding, and Pennsylvania Infrastructure Investment Authority (PENNVEST) low interest loans.  PWSA states that it is exploring the federal funded program called the Water Infrastructure Finance and Innovation Act of 2014 (WIFIA) to help finance certain planned improvements.  PWSA notes that the WIFIA program offers low, fixed interest rates and flexible financial terms.  PWSA intends to utilize a mix of all funding options to invest in the planned improvements at the lowest possible ratepayer cost.  PWSA also intends to explore the potential use of public-private partnerships in the future to lower the capital cost burden to ratepayers.

Comments

No comments were received regarding the reasonable estimates of the quantity or expenditures of property to be improved, and cost effectiveness of the plan.

Resolution

PWSA does not currently have an approved DSIC and therefore is not required to file an Annual Asset Optimization Plan (AAOP).  In order for the Commission to ensure PWSA is meeting its commitments in the LTIIP in a cost effective manner, until such time that PWSA has an approved DSIC, we shall direct PWSA to file a report in similar form and content to an AAOP that includes tables similar in form and content to tables 2-6, 3-6, and 4-2 of the Amended LTIIP’s Appendix B with updated actual eligible property amounts and expenditures, as well as an update on the progress of the Lead Service Line Replacement Program.

Upon review of PWSA’s Amended LTIIP, the Commission finds that PWSA’s Amended LTIIP fulfills the requirements of 52 Pa. Code §§ 121.3(a)(4)-(5) by providing reasonable estimates of the quantity of property to be improved and the projected annual expenditures and means to finance the expenditures and ensure cost effectiveness.

(6) ACCELERATED REPLACEMENT AND MAINTAINING ADEQUATE, EFFICIENT, SAFE, RELIABLE AND REASONABLE SERVICE TO CUSTOMERS

PWSA’s Position

PWSA maintains that for the past 30 years it has run an engineering and construction department comprised of employees and contracted professionals.  PWSA states that its staff and its outside consultants and contractors will continue to work as a unit in terms of controlling and monitoring all aspects of the capital program.  PWSA states that the increase in the volume of capital project delivery planned for the next 5 years demands an ever-increasing level of management excellence to achieve the efficiencies necessary to meet the challenge of adhering to project budgets and schedules.  To accelerate the sewer system CIP investments, PWSA notes that it has initiated sewer renewal contracts in 2018.  Sites were selected based on the asset’s physical condition, location, and/or regulatory compliance obligations.

PWSA notes that impediments to the attainment of its aggressive construction program proposed must be identified in advance, and when barriers to the efficient attainment of pre-established budget and schedule goals are identified, they must be resolved quickly and consistently.  PWSA maintains that this approach will ensure the success of the program, measured in large part by cost savings.

PWSA states there is a need for a comprehensive and systematic approach to the delivery of the accelerated capital improvements program.  PWSA notes it has implemented and is improving several tools which will ensure the cost-effective and efficient planning, design, procurement, construction, and close-out of projects, such as the e-Builder and PMP noted, above.

Table 3, below, is Figure 3-4 from the Amended LTIIP and it presents actual and projected spending on eligible sewer system projects for the period 2014-2023.  PWSA notes that the values for 2015 reflect projects that were funded through a combined capital and operations budget, which accounts for its disproportion to years prior and after.  Table 3 clearly shows a significant increase in capital spending for DSIC-eligible sewer improvements and rehabilitation.

Table 3: Historical and Projected Spending for DSIC-Eligible Sewer Projects

Comments

No comments were received regarding the manner in which the infrastructure replacement will be accelerated.

Resolution

Upon review of PWSA’s Amended LTIIP, the Commission finds that PWSA’s Amended LTIIP fulfills the requirements of 52 Pa. Code §§ 121.3(a)(6) by providing a description of the manner in which infrastructure replacement will be accelerated and how repair, improvement, or replacement will ensure and maintain adequate, efficient, safe, reliable, and reasonable service to customers.

(7) WORKFORCE MANAGEMENT AND TRAINING PROGRAM

PWSA’s Position

PWSA maintains that its existing workforce provides a solid foundation upon which to build the staff and skills it needs to become a high-performing organization.  PWSA notes that it has added more than 115 employees since 2018 to address the range of operational, capital and other Commission-mandated compliance responsibilities.  In 2020, PWSA anticipates adding an additional 33 new employees to accomplish the work associated with the 2020 CIP and other Commission-mandated compliance activities which include the eligible property infrastructure improvements.  PWSA notes that PWSA staff will be supplemented by contracted personnel as needed.

PWSA also intends to continue adding staff for stormwater related activities, as well as additional operations crews to construct water main and stormwater facilities as appropriate, in lieu of private contractors.  PWSA notes the full extent of the additional workforce will depend upon their availability in the region, and the costs for contracted work compared to PWSA staff productivity.

PWSA is not able to present an estimate of the exact number of contractors that may be needed at this time as that figure is dependent on both the progress of building an internal workforce and the final determination of actual needs and scope of the projects.  PWSA states that it utilizes subcontracted construction inspectors to provide numerous services during the installation of water mains, service lines, sewer lines, laterals and manholes in the collection system.

PWSA states that it maintains three inspectors on staff, and is seeking additional inspection staff, and utilizes qualified consultants to provide construction inspection services.  PWSA notes that these inspectors perform a wide range of services including the following tasks, as well as any other work that may be necessary to complete the construction activities:

- Monitor the installation of the water and sewer lines and appurtenances to confirm that they are properly bedded and installed in accordance with PWSA’s specifications and/or Contract Documents

- Observe, perform testing to ensure that the new utilities meet specified performance requirements

- Monitor the pipe backfill for proper compaction in accordance with PWSA’s specifications and/or local municipal, county or PennDOT requirements

- Confirm that all materials such as pipe, fittings, hydrants, valves, service connections, backfill materials, etc. being used in the project meet the PWSA’s specifications

- Record the quantities of pipe and other materials installed

- Document the quantities of pipe and other materials, labor, equipment, etc., for accurate billing and payments

- Document all locations of pipe, valves, service connections, laterals, etc., for accurate mapping and record keeping

- Interact with City residents to coordinate water service line or sewer lateral installations, lessen the impact of the project and answer or address issues that may arise during the project

- Communicate with local businesses that may be impacted by the construction activities to ensure that service disruptions can be minimized to the greatest extent possible and service outages are minimized and do not disrupt business

- Coordinate contractors with school districts, various City agencies, and emergency services so that bus routes, trash pick-up, mail delivery, and emergency response are minimally impacted

- Monitor temporary restoration activities during construction to ensure that roads are restored, to approved vehicular travel conditions, and sidewalk areas are clear for pedestrians

- Monitor the final restoration required in projects to ensure that they are done in compliance with City of Pittsburgh, Allegheny County and/or PennDOT specifications

- Observe contractor's implementation of contractor safety plans and advise contractor of any observed conditions of imminent risks to public health or safety.  Inspectors are authorized to advise supervisors of unsafe conditions and can shut down a project until an imminent danger situation is addressed.

PWSA states that it will work cooperatively with unions to find and act on opportunities to increase workforce performance and effectiveness.  PWSA notes that in early 2020, local union leadership has agreed to assist PWSA with specific training required for its laborers, equipment operators, electricians, plumbers and utility workers.

PWSA states that it will use a combination of internal and external resources to address the critical staffing needs associated with the infrastructure improvement program.  PWSA will utilize Program Management support to execute the program with design and construction management services primarily provided by consultants.  PWSA intends to cost-effectively increase staffing levels to ultimately assume the role of program management of the CIP.

PWSA notes that training for all staff has increased and includes assisting the staff to acquire certifications and licenses for their specialized capabilities (Water Treatment Operators, Distribution System Operators.)

PWSA is also working to establish and track productivity goals for work groups, where applicable.  PWSA notes that it has implemented performance metrics for every group within the organization.  More than 50 metrics are now being reported to the PUC on a quarterly basis.

PWSA maintains that four measures of success will be used to determine effectiveness of its workforce engagement program:

- Training hours per year: Goal of 20 hours per year per employee.

- Safety compliance: The goal will be to maintain a worker’s compensation experience modification rate of less than 1.0.

- Occupational Safety & Health Administration (OSHA compliance: Meet OSHA requirements

- Staff engagement survey: One every 3 years.

PWSA notes that its Program Management Team, with support of PWSA Project Controls personnel, have conducted e-Builder training for PWSA personnel and others.  PWSA states that in addition to this formal training, “e-Builder Hot Topic Meetings” are held monthly.

PWSA maintains that other training programs are conducted by in-house and contracted personnel on such topics as hydraulic modeling, low impact development (LID), sustainability, and safety.  PWSA notes that its engineering staff are certified Sustainability Professionals.  In 2014, PWSA contracted with Compliance Management International (CMI) to assist in improving their current Health & Safety Program.  PWSA states that CMI developed a Safety Improvement Plan (SIP) SIP to incorporate 12 key Health & Safety initiatives to expand and improve the overall program to include:

- Written Safety Programs

- Goals & Objectives

- Leadership/Management

- Safety Training

- Safety Inspections (Facility/Job Sites)

- Safety Committees

- Job Safety Analysis (JSA)

- Accident Prevention/Incident Investigation

- Corrective Action Tracking

- New Employee Orientation

- Emergency Procedures

- Occupational Illness/Health

PWSA notes that most of the above trainings are provided on an annual basis as part of a full day safety refresher training.  In May 2018, PWSA recertified over 80 employees as Certified Flaggers and will provide another round of training for Competent Persons for Excavations certifications.

PWSA states that is has dedicated additional resources to training and development, as well as health, safety, and risk management.  PWSA states that it provides safety training by having a full-time contractor onsite, working with the Operation and Water Production Teams on a weekly basis.  PWSA reports that they are currently interviewing individuals to hire a permanent fulltime Senior Safety Manager.

PWSA notes that it conducted Industrial Hygiene Monitoring in 2016 and 2018, including both air sampling and noise sampling.  As a result of the monitoring program, PWSA implemented an OSHA compliant respiratory program.  PWSA states that safety metrics and injury trends are continuously tracked and improvements in the provision and use of personal protective equipment (PPE) and other operational equipment to reduce employee risks and injuries have also been noted.

Comments

No comments were received regarding the workforce management and training program.

Resolution

Upon review of PWSA’s Amended LTIIP, the Commission finds that PWSA’s Amended LTIIP fulfills the requirements of 52 Pa. Code § 121.3(a)(7) by providing a workforce management and training program that is designed to ensure that PWSA will have access to a qualified workforce to perform the work in a cost effective, safe and reliable manner.

(8) DESCRIPTION OF OUTREACH AND COORDINATION ACTIVITIES WITH OTHER UTILITIES, PENNDOT AND LOCAL GOVERNMENTS ON PLANNED PROJECTS

PWSA’s Position

PWSA maintains that it has developed a coordination team with the City and its other utility members.  PWSA states that it is developing a robust GIS-based data layer to communicate its plans to other utilities.  At present, PWSA states that the critical coordination appears to be with the City, specifically the annual paving plans, and the local Gas Companies’ piping improvements.  PWSA expects significant improvement   with the coordination between the PWSA and the City as a result of the City’s hiring of a new Chief Engineer, and additional engineering staff, which has delayed coordination in the past.  PWSA has assigned specific utility coordination duties to a primary, internal utility coordination staff member within the Engineering Department.

PWSA maintains that its annual, water and sewer system capital projects including replacements, rehabilitations, and repairs are selected and vetted to PWSA’s engineering department before being prioritized for the coming budget year.  As part of this process, PWSA solicits information from PennDOT, Allegheny County, homeowner’s associations, and other utilities as to their intentions to undertake paving and other public works projects during the budget year.

PWSA states that it attends monthly utility coordination meetings with the City’s Department of Mobility and Infrastructure (DOMI) and other local utilities and coordinates construction and repair efforts when possible to avoid conflicts where overlapping work is identified.  Additionally, PWSA notes that it will utilize resources, including the Pennsylvania 811 Coordination web service application, to identify opportunities for collaboration between projects and to meet the need for increased coordination with local utilities and local, state, county and city government agencies.  PWSA notes that when it decides to undertake a pipe or manhole refurbishment project on a road pre-scheduled for paving, the project is coordinated with the State, County, City or appropriate municipality.

PWSA reports that it works closely with the applicable government agency to ensure that the design, permitting and construction of PWSA’s infrastructure project will be completed in time to allow for the road to be paved.  PWSA notes that when it undertakes a project where paving has been pre-planned by the involved government agency, in most cases PWSA and its rate payers will benefit financially through the avoidance of road surface restoration.  PWSA maintains that it will continue the proactive means to identify opportunities to coordinate pipe replacement and road paving.

PWSA states that it also employs Field Liaisons who are responsible for coordinating lead service line replacement (LSLR) work between PWSA’s contractors, property owners and often tenants.  PWSA notes that Field Liaisons contact each property owner to help them understand the replacement process and potential impacts of the work, and to encourage private property owners who have not responded to communications from PWSA’s Lead Help Desk.  PWSA notes the presence of on-site Field Liaisons also helps assure that the PWSA’s contractors meet all quality assurance and regulatory requirements, such as providing NSF approved filters and lead water test kits.  Other LSLR outreach includes presentations at community meetings within the work areas, advertisements in neighborhood publications, press releases (and resulting press coverage) of work areas, social media posts, collaboratively working with City Councilors regarding work done in their district, construction signage detailing the work and weekly updates concerning streets where work is occurring.

PWSA notes that it has created a comprehensive capital improvement outreach protocol to connect project managers and PWSA’s public affairs team in the early stages of a project to ensure that PWSA clearly communicates the benefits, impacts, and expectations of construction work.  PWSA notes its Public Affairs team members attend many of the engineering progress meetings to ensure they are in the loop as projects progress so that the public has the most pertinent, time-sensitive information on projects that will impact where they live or work.  PWSA notes that residents can check an interactive map of their neighborhood on the PWSA website to see which projects are upcoming and easily access contact information for project managers and members of the Public Affairs team.  PWSA notes it also hosts and participates in meetings and events throughout the city to share information on our programs and projects.

PWSA maintains that its industry relations are focused on enhancing the relationship with developer and contractor customers through increased outreach and technology.  PWSA reports that its Public Affairs team established a single point of contact for any development questions or commercial customer issues.  PWSA notes that the point of contact also schedules pre-development meetings that are typically the first contact with any potential applicants.  PWSA describes that at this meeting, the property owner, their consultants, and contractors meet with PWSA staff to ensure that the project complies with water and sewer regulations.

PWSA states that they have also ramped up efforts to reach industry partners including contractors, third party engineers, plumbers, and non-profits.  PWSA attended events to promote their upcoming work contracts to organizations such as the: Engineering Society of Western Pennsylvania; Society of Engineering Outreach; Society of Military Engineers; Government Agency Procurement Office; MWDBE Governmental Committee; Building Owners and Manager Association; and additional organizations.  PWSA notes that it also attended open houses, office openings, and industry award ceremonies to meet and network with new talent and potential partners.

Comments

No comments were received regarding the description of outreach and coordination activities with other utilities, PennDOT and local governments on planned projects.

Resolution

Upon review PWSA’s Amended LTIIP, the Commission finds that PWSA’s Amended LTIIP fulfills the requirements of 52 Pa. Code § 121.3(a)(8) by providing a description of PWSA’s outreach and coordination activities with other utilities, PennDOT and local governments on planned projects and roadways that may be impacted by the Amended LTIIP.

LTIIP SUMMARY

The Commission’s review of an LTIIP must determine if the LTIIP:

- Contains measures to ensure that the projected annual expenditures are cost -effective.

- Specifies the manner in which it accelerates or maintains an accelerated rate of infrastructure repair, improvement or replacement.

- Is sufficient to ensure and maintain adequate, efficient, safe, reliable and reasonable service.

- Meets the requirements of 52 Pa. Code § 121.3(a).

The utility has the burden of proof to demonstrate that its proposed LTIIP and associated expenditures are reasonable, cost effective and designed to ensure and maintain sufficient, safe, adequate, reliable and reasonable service to consumers.

The Commission has reviewed PWSA’s Amended LTIIP and any resulting comments.  The Commission finds that PWSA has meet its burden of proof by demonstrating that its Amended LTIIP contains measures to ensure that the projected annual expenditures are cost-effective, specifies the manner in which it accelerates or maintains an accelerated rate of infrastructure repair, improvement, or replacement, is sufficient to ensure and maintain adequate, safe, reliable, and reasonable service, and meets the requirements of 52 Pa. Code § 121.3(a).  Accordingly, PWSA’s Amended LTIIP is approved.

The Commission finds PWSA’s Amended Long-Term Infrastructure Improvement Plan and the manner in which it was filed conforms to the requirements of Act 11 and our Regulations.  The plan, as approved herein, is designed to maintain safe, adequate and reliable service and, as such, PWSA shall be required to comply with the infrastructure replacement schedule and elements of that plan; THEREFORE,

IT IS ORDERED:

1.	That the Petition for Approval of an Amended Long-Term Infrastructure Improvement Plan filed by the Pittsburgh Water and Sewer Authority for its Wastewater Operations is approved, consistent with this Order.

2.	That until such time as the Pittsburgh Water and Sewer Authority has an approved Distribution System Improvement Charge and is required to file an Annual Asset Optimization Plan, the Pittsburgh Water and Sewer Authority shall file a progress report 30 days after the end of each fiscal year beginning with fiscal year 2020, and each fiscal year afterwards at that same time, and the report shall be in similar form and content to an Annual Asset Optimization Plan and shall include tables similar in form and content to Tables 2-6, 3-6, and 4-2 of Appendix B of the Amended Long-Term Infrastructure Improvement Plan, along with updated actual eligible property amounts and expenditures, as well as an update on the progress of the Lead Service Line Replacement Program.

3.	That the report filed pursuant to Ordering Paragraph No. 2, above, shall be filed with the Commission’s Secretary to Docket No. P-2018-3005039 with copies served upon the Bureau of Investigation and Enforcement, the Bureau of Fixed Utility Services, the Office of Consumer Advocate, and the Office of Small Business Advocate.

4.         That the proceeding at Docket No. P-2018-3005039 be closed.

BY THE COMMISSION,

Rosemary Chiavetta

Secretary

(SEAL)

# ORDER ADOPTED: August 27, 2020

# ORDER ENTERED:  August 27, 2020

See Docket No. M-2018-2640802.

See Docket No. R-2018-3002645.

See Docket No. M-2018-2640802.

See 52 Pa. Code § 121.3.

The Commission is preparing a contemporaneous Order for the review of PWSA’s Amended LTIIP for its water operations at Docket No. P-2018-3005037.

52 Pa. Code § 121.6.

See Ordering Paragraph No. 2.

See 52 Pa. Code § 121.4(e).

See 52 Pa. Code § 121.4(d).