|  | COMMONWEALTH OF PENNSYLVANIA PENNSYLVANIA PUBLIC UTILITY COMMISSION 400 NORTH STREET 2ND FLOOR, HARRISBURG PA 17120 http://www.puc.pa.gov E-filing and E-service only per Emergency Order M-2020-3019262 |  | IN REPLY PLEASE REFER TO OUR FILE |
| --- | --- | --- | --- |

December 7, 2020

A-2020-3021094

Via Eservice and Email Only

TO PARTIES OF RECORD

Application of East Hempfield Township for approval to alter the public crossing (DOT 517 593 B) by the construction of additional thru lanes, a center left turn lane, a concrete median, a 5-foot pedestrian crossing and traffic signal pre-emption, where Centerville Road (T-607) crosses at-grade a single track of Norfolk Southern Railway Company in East Hempfield Township, Lancaster County and the allocation of costs incident thereto.

To Whom It May Concern:

This matter is before us, by reason of an application filed

July 30, 2020, by East Hempfield Township (Township) seeking Commission approval to alter the public crossing (DOT 517 593 B) by the construction of additional thru lanes, a center left turn lane, a concrete median, a 5-foot pedestrian crossing and traffic signal pre-emption, where Centerville Road (T-607) crosses at-grade a single track of Norfolk Southern Railway Company (NS) in East Hempfield Township, Lancaster County and the allocation of costs incident thereto.

Upon receipt of the application, a field investigation and conference was arranged by a Commission staff engineer and held on August 28, 2020, at the site of the crossing.  All parties were notified by electronic mail on August 18, 2020, of the date and time of the field conference.  Representatives of East Hempfield Township, the Pennsylvania Department of Transportation, NS, PPL Electric Company, were in attendance.  Lancaster City, Lancaster Sewer Authority, Verizon Pennsylvania and Lancaster County were notified of the time and place of the meeting but did not attend.

At the existing crossing, Centerville Road (T-607), is a two-lane bituminous asphalt roadway with bituminous shoulders and no sidewalks, that crosses, at grade, a single track of NS. The existing crossing consists of a timber and asphalt crossing surface.  The warning facilities at the crossing in each direction of the highway consist of post-mounted flashing-light warning signals with gates and a bell. The approach roadways to the crossing have W10-1 advance warning signs, do not stop on tracks signs, pavement markings and stop lines.

There are signalized intersections on each side of the crossing. The Centerville Road and Hempland Road intersection is approximately 350 feet north of the crossing and the intersection of Centerville Road and Old Tree Drive is approximately 370 feet south of the crossing.  The traffic signals at both intersections currently do not utilize railroad preemption.

At the field conference, the Township described the proposed work. The project will be done at the Township’s sole cost and expense, Centerville Road will be widened to 5 lanes consisting of a 12-foot center turning lane with two 11-foot thru lanes, 2-foot shoulders, curbs, and 5-foot wide sidewalks in each direction. The existing crossing surface will be replaced with a new asphalt and rubber flangeway crossing surface that will extend across the full width of the roadway and across both sidewalks. The existing traffic signals at the intersections of Old Tree Drive and Hempland Road with Centerville Road will be upgraded with railroad preemption.

NS, at the Township’s sole cost and expense, will (1) remove the existing crossing surface and post-mounted flashing light warning signals; (2) install a new asphalt and rubber flangeway crossing surface across the full width of five-lanes of Centerville Road and both sidewalks; (3) install two new active traffic control systems on each crossing approach consisting of post-mounted flashing lights with bells and gates with one system mounted behind the sidewalk along the right side of the two-lane approach roadway and one system mounted in the raised concrete median on the left side of the two-lane approach roadway; (4) provide railroad preemption interconnect to 2 junction boxes, with one junction box on each side of the crossing.

The Township, at its sole costs and expense, will (1) upgrade the highway traffic signals at the intersections of Old Tree Drive and Hempland Road with Centerville Road with railroad preemption; (2) install a new junction boxes on each side of the crossing for the preemption interconnect; (3) provide the cable form the junction boxes to the traffic signal control boxes; (4) widen Centerville Road to include two thru lanes and a center turning lane on each highway approach to the crossing (5) install a raised concrete median in the center lane on each side of the crossing; (6) install pavement markings and stop lines.

All work is to be performed in accordance with the attached preliminary plans entitled “EXHIBIT B,” consisting of twenty-four (24) sheets, filed with this Commission on July 29, 2020.  The Township, at its sole cost and expense, will submit detailed roadway construction plans including traffic signal plans with railroad preemption to all parties of record. NS, at the sole cost and expense of the Township, will submit a situation plan to all parties of record for review and the Commission for approval, and a circuitry plan to the Pennsylvania Department of Transportation for review and to the Commission for approval.

NS agreed to maintain its warning facilities at the Centerville Road crossing including the automatically operated flashing-light warning signals and all appurtenant equipment, and to maintain at all times in a smooth and satisfactory condition the asphalt and rubber flangeway crossing surface.

The Township, at its sole cost and expense, will maintain the advanced warning signs, the highway traffic signals and railroad pre-emption timing at the subject intersections.

The Commission hereby establishes its jurisdiction limits at the subject crossing as the area within the confines of the railroad right-of-way and the highway right-of-way along Centerville Road and extending along the highway right-of-way from Station 35+50 to 43+50.

The Commission has exclusive jurisdiction in crossing alterations and is the final arbiter of any fees associated with a crossing application. Any conditions, including fees associated with a crossing application must be approved by the Commission.

The project will be funded by 80 percent federal funds and 20 percent local funds.

Upon full consideration of the matters involved and inasmuch as no objection has been filed with the Commission, we find that a Secretarial Letter can be issued approving the application without a formal hearing.

The Commission issues this Secretarial Letter in accordance with Section 2702 of the Public Utility Code and finds that the alteration of the subject crossing is necessary and proper for the service, accommodation, convenience or safety of the public.

The application of East Hempfield Township is approved as herein directed:

1.	The caption of the subject proceeding is hereby revised as shown herein.

2.	The public at-grade crossing (public crossing (DOT 517 593 B) where Centerville Road (T-607) crosses at-grade a single track of Norfolk Southern Railway Company (NS) in East Hempfield Township, Lancaster County, be altered in accordance with East Hempfield Township’s application and attached preliminary plans entitled “EXHIBIT B,” consisting of twenty four (24) sheets, filed with this Commission on July 29, 2020.

3	East Hempfield Township, at its sole cost and expense and prior to the start of construction, shall submit detailed construction plans, including traffic signal plans with railroad preemption at the intersections of Old Tree Drive and Hempland Road with Centerville Road to all parties of record for review and to the Commission for approval.

4.	Norfolk Southern Railway Company, at the sole cost and expense of East Hempfield Township, prior to the start of construction, submit a situation plan to all parties of record for review and the Commission for approval, and submit a circuitry plan to the Pennsylvania Department of Transportation for review and to the Commission for approval.

5.	Norfolk Southern Railway Company, at the sole cost and expense of East Hempfield Township, furnish all material and do all work necessary to alter the subject crossing by will (1) remove the existing crossing surface and post-mounted flashing light warning signals; (2) install a new asphalt and rubber flangeway crossing surface across the full width of all five-lanes of Centerville Road and both sidewalks; (3) install two new active traffic control systems on each crossing approach consisting of post-mounted flashing lights with bells and gates with one system mounted behind the sidewalk along the right side of the two-lane approach roadway and one system mounted in the raised concrete median on the left side of the two-lane approach roadway; (4) provide railroad preemption interconnect to 2 junction boxes, with one junction box on each side of the crossing; all in accordance with the approved plans, Part 8 of the Manual on Uniform Traffic Control Devices and this Secretarial Letter.

6.    	East Hempfield Township, at its sole costs and expense, will

(1) upgrade the highway traffic signals at the intersections of Old Tree Drive and Hempland Road with Centerville Road with railroad preemption; (2) install a new junction box on each side of the crossing for the preemption interconnect; (3) install a cable from each junction box to each traffic signal control box at Old Tree Drive and at Hempland Road; (4) widen Centerville Road to include two thru lanes and a center turning lane on each highway approach to the crossing (5) install a raised concrete median in the center lane on each side of the crossing; (6) install pavement markings and stop lines, all in accordance with the approved plans, Part 8 of the Manual on Uniform Traffic Control Devices and this Secretarial Letter.

7.	East Hempfield Township, at its sole cost and expense, furnish all material and do all work necessary to establish and maintain any detours or traffic controls at the subject crossing that may be required to properly and safely accommodate highway and pedestrian traffic during the time the crossing is being altered.

8. 	Norfolk Southern Railway Company, at the sole cost and expense of East Hempfield Township, furnish all material and perform all work necessary to furnish watchmen, flagmen, inspectors, and/or engineering services that may be deemed necessary to protect the railroad’s operations or facilities during the time the facilities are being installed.

9.	Any relocation of, changes in and/or removal of any adjacent structures, equipment or other facilities of any non-carrier public utility company or municipal authority located within the limits of the Commission’s jurisdiction, which may be required as incidental to the execution of the proposed project, be made by said public utility, at its initial cost and expense and in such manner as will not interfere with construction of the project.

10.	Any relocation of, changes in and/or removal of any adjacent structures, equipment or other facilities of any non-carrier public utility company or municipal authority located in private right-of-way within the limits of the Commission’s jurisdiction, which may be required as incidental to the execution of the crossing project, be made by said public utility or municipal authority and in such manner as will not interfere with the project.

11.	All parties involved herein cooperate fully with each other so that during the time the work is being performed, vehicular, pedestrian and railroad traffic will not be endangered or unnecessarily inconvenienced and so that the requirements of each of the parties will be provided for and accommodated insofar as possible.

12.	East Hempfield Township notify all parties of record at least fourteen (14) days prior to performing any work in accordance with this Secretarial Letter.

13.	Pennsylvania Department of Transportation, at least twenty-one (21) days prior to the start of work, notify all parties in interest and local emergency management services of the actual date on which work will begin.

14.	East Hempfield Township pay all compensation for damages due to the owners of any property taken, injured or destroyed by reason of the alteration of the subject crossing in accordance with this Secretarial Letter.

15.	Upon completion of construction of the project, Norfolk Southern Railway Company, at its sole cost and expense, furnish all material and perform all work necessary thereafter to maintain its railroad facilities at the crossing, including the automatically operated flashing-light warning signals with gates and bells and all appurtenant equipment, and to maintain at all times in a smooth and satisfactory condition the railroad crossing surfaces located between the rails and for a distance of twenty-four (24) inches beyond the rails; and provide 10-days of advance notice to East Hempfield Township prior to doing any work at the crossing, all in accordance with this Secretarial Letter .

16.	Upon completion of construction of the project, East Hempfield Township, at its sole cost and expense, furnish all material and do all work necessary to maintain the highway approaches to the subject crossings to points twenty-four (24) inches beyond each outside rail and, in addition, maintain the grade crossing advance warning signs and stop lines on the approaches thereto, in accordance with Part 8 of the Manual on Uniform Traffic Control Devices and this Secretarial Letters, and provide 10-days of advance notice to Norfolk Southern Railway Company prior to doing any work at the crossing, all in accordance with Part 8 of the Manual on Uniform Traffic Control Devices and this Secretarial Letter.

17.	Upon completion of construction of the project, East Hempfield Township, at its sole cost and expense, furnish all material and do all work necessary thereafter to maintain the highway traffic signals and traffic signal control box at the intersections of Old Tree Drive and Hempland Road with Centerville Road, and to maintain the cables from the junction boxes to both the traffic signal control boxes, in a safe and satisfactory condition.

18. 	Upon completion of the work herein directed, East Hempfield Township, at its sole cost and expense, shall maintain and shall annually inspect the traffic signals, the traffic signal control boxes and the cables form the junction boxes to the traffic signal control box to ensure that the timing and preemption operation of the signal systems are functioning as designed.  East Hempfield Township shall contact Norfolk Southern Railway Company and arrange for railroad personnel to activate the railroad crossing warning system to accommodate the required inspection.  East Hempfield Township shall report any operational problems that cannot be corrected during the annual inspection to both the Pennsylvania Department of Transportation and the Pennsylvania Public Utility Commission.

19.	Upon completion of the work herein directed, and upon written request from any party of record, this proceeding be scheduled for a hearing at a time and place to be determined by the Commission, for the purpose of taking testimony upon the final allocation of any costs incurred by the non-carrier utility companies and other matters relevant to this proceeding.

The Parties are reminded that failure to comply with this or any Order or Secretarial Letter in this proceeding may result in an enforcement action seeking civil penalties and/or other sanctions pursuant to 66 Pa. C.S. § 3301.

All parties are being served via email due to the COVID-19 Emergency Closure.  Please note that during this period of Disaster Emergency, the Commission shall only accept E-filings in lieu of paper filings, for all documents.  Thus, all parties are to open and use E-filing accounts to file documents and accept service during the pandemic emergency in accordance with the Commission’s Emergency Order at M-2020-3019262.

If you are dissatisfied with the resolution of this matter, you may, as set forth in 52 Pa. Code §§ 1.31 and 5.44, file a Petition for Reconsideration from Staff Action (Petition) with the Commission within twenty (20) days of the date of this letter.  The Petition shall be submitted by E-filing said petition within twenty (20) days, or if no timely request is made, the action will be deemed to be a final action of the Commission.

The Petition MUST include: (1) a written statement (divided into numbered paragraphs) outlining the reasons for the request; (2) the case docket number (it is provided for you at the top right hand corner of this letter); (3) the party on whose behalf the petition is made; (4) a Certificate of Service on the other parties of record; and (5) a Verification with original signature in accordance with 52 Pa. Code § 1.36.

Very truly yours,

Rosemary Chiavetta

Secretary