|  | COMMONWEALTH OF PENNSYLVANIA PENNSYLVANIA PUBLIC UTILITY COMMISSION 400 NORTH STREET 2ND FLOOR, HARRISBURG PA 17120 http://www.puc.pa.gov E-filing and E-service only per Emergency Order M-2020-3019262 |  | IN REPLY PLEASE REFER TO OUR FILE |
| --- | --- | --- | --- |

June 23, 2021

A-2021-3024998

(Amended)

Via Eservice and Email Only

TO PARTIES OF RECORD

Re:  Application of the Department of Transportation of the Commonwealth of Pennsylvania for approval to alter the public at-grade crossing (DOT 506 378 J)

by the installation of new active traffic control devices on Struble Road (T-380) and upgrading the highway traffic signals at the intersection of Struble Road and College Avenue (State Route 0026) with railroad preemption where Struble Road, crosses a track of the SEDA-COG Joint Rail Authority, operated thereon by Nittany and Bald Eagle Railroad, in College Township, Centre County all in accordance with the Federal Grade Crossing Program and the allocation of costs incident thereof.

To Whom It May Concern:

This matter is before us, by reason of an application filed

April 5, 2021, by Pennsylvania Department of Transportation (Department) seeking Commission approval to alter the public crossing (DOT 506 378 J) by the installation of new active traffic control devices on Struble Road (T-380) and upgrading the highway traffic signals at the intersection of Struble Rod and College Avenue (SR 0026) with railroad preemption where Struble Road, crosses a track of the SEDA-COG Joint Rail Authority, operated thereon by Nittany and Bald Eagle Railroad, in College Township, Centre County all in accordance with the Federal Grade Crossing Program and the allocation of costs incident thereof.

Upon receipt of the application, a field investigation and conference was arranged by a Commission staff engineer and held on May 13, 2021, at the site of the crossing.  All parties were notified by electronic mail on May 7, 2021, of the date and time of the field conference.  Representatives of College Township, College Township Water Authority, the Pennsylvania Department of Transportation, SEDA-COG Joint Rail Authority, Nittany and Bald Eagle Railroad, Columbia Gas of PA and West Penn Power were in attendance.  State College Borough Water Authority, Ruetgers-Nease Corporation, Comcast Cable, Verizon, and Centre County, were notified of the time and place of the meeting but did not attend.

At the existing crossing, Struble Road (T-380), is a two-lane bituminous asphalt roadway with bituminous shoulders and no sidewalks, that crosses, at grade, a single track of SEDA-COG Joint Rail Authority, operated thereon by Nittany and Bald Eagle Railroad. The existing crossing consists of an asphalt and rubber rail seal crossing surface.  The warning facilities at the crossing in each direction of the highway consist of crossbucks. The approach roadways to the crossing have W10-1 advance warning signs.

The intersection of College Avenue (SR 0026) and Struble Road is on the north side of the crossing and has existing highway traffic signals.

At the field conference, the Department described the proposed work. The project will be done at the Department’s sole cost and expense. SEDA-COG Joint Rail Authority, at the Department’s sole cost and expense, will (1) install a new gate ready active traffic control systems on each approach to the crossing consisting of post-mounted flashing light warning signals with bell on the south-bound approach and a cantilevered flashing light warning signal with bell on the north-bound approach; (2) provide railroad preemption and an interconnect to a junction box.

The Department, at its sole costs and expense, will (1) upgrade the highway traffic signals at the intersection of College Avenue (SR 0026) and Struble Road with railroad preemption; (2) install a new junction for the preemption interconnect; (3) install a cable from the junction box to the traffic signal control box; (4) install blank-out no turn signs on both approaches of College Avenue to the intersection with Struble Road.  The Department, at its sole cost and expense, will submit detailed roadway construction plans, including traffic signal plans with railroad preemption, to all parties of record for review.

College Township, at its sole costs and expense, will install stop lines on each approach roadway to the crossing.

SEDA-COG Joint Rail Authority, prior to the start of construction, shall submit a situation plan to all parties of record for review and to the Commission for approval and submit a detailed circuit plan to the Pennsylvania Department of Transportation for review and to the Commission for approval.

SEDA-COG Joint Rail Authority agreed to maintain its warning facilities at the Struble Road crossing including the automatically operated flashing-light warning signals and all appurtenant equipment, and to maintain at all times in a smooth and satisfactory condition the asphalt and rubber flangeway crossing surface.

College Township, at its sole cost and expense, will maintain the advanced warning signs, the highway traffic signals and railroad pre-emption timing at the subject intersection.

The Commission hereby establishes its jurisdiction limits at the subject crossing as the area within the confines of the railroad right-of-way and the highway right-of-way along Struble Road and extending along the highway right-of-way to include the intersection of Struble Road and College Avenue (SR 0026).

The Commission has exclusive jurisdiction in crossing alterations and is the final arbiter of any fees associated with a crossing application. Any conditions, including fees associated with a crossing application must be approved by the Commission.

Pennsylvania Department of Transportation will provide funding through the Federal Highway Grade Crossing Safety Program.

Upon full consideration of the matters involved and inasmuch as no objection has been filed with the Commission, we find that a Secretarial Letter can be issued approving the application without a formal hearing.

The Commission issues this Secretarial Letter in accordance with Section 2702 of the Public Utility Code and finds that the alteration of the subject crossing is necessary and proper for the service, accommodation, convenience or safety of the public.

The application of Pennsylvania Department of Transportation is approved as herein directed:

1.	The caption of the subject proceeding is hereby revised as shown herein.

2.	The public at-grade crossing (DOT 506 378 J) where Struble Road, crosses a track of the SEDA-COG Joint Rail Authority, operated thereon by Nittany and Bald Eagle Railroad, in College Township, Centre County be altered as herein directed.

3. 	SEDA-COG Joint Rail Authority, at sole cost and expense of Pennsylvania Department of Transportation, prior to the start of construction, submit a situation plan to all parties of record for review and to the Commission for approval.

4. 	SEDA-COG Joint Rail Authority, at sole cost and expense of Pennsylvania Department of Transportation, prior to the start of construction and submit a detailed circuit plan for the subject crossing alteration to the Pennsylvania Department of Transportation for review and to the Commission for approval.

5.	Pennsylvania Department of Transportation, at its sole cost and expense and prior to the start of construction, shall submit detailed construction plans, including traffic signal plans with railroad preemption at the intersection of Struble Road and College Avenue (SR 0026) to all parties of record for review and to the Commission for approval.

6.	SEDA-COG Joint Rail Authority, at the sole cost and expense of Pennsylvania Department of Transportation, furnish all material and do all work necessary to alter the subject crossing by (1) installing new gate ready active traffic control systems on each approach to the crossing consisting of post-mounted flashing light warning signals with bell on the south-bound approach and a cantilevered flashing light warning signal with bell on the north-bound approach; (2) providing railroad preemption and an interconnect to a junction box; all in accordance with the approved plans, Part 8 of the Manual on Uniform Traffic Control Devices and this Secretarial Letter.

7.    	Pennsylvania Department of Transportation, at its sole costs and expense, will (1) upgrade the highway traffic signals at the intersection of College Avenue (SR 0026) and Struble Road with railroad preemption; (2) install a cable from the junction box to the traffic signal control box; (3) install blank-out no turn signs on both approaches of College Avenue (SR 0026) to the intersection with Struble Road, all in accordance with the approved plans, Part 8 of the Manual on Uniform Traffic Control Devices and this Secretarial Letter.

8. 	College Township, at its sole cost and expense, furnish all material and do all work necessary to install stop lines on the approaches to the crossing, all in accordance with the approved plans, Part 8 of the Manual on Uniform Traffic Control Devices and this Secretarial Letter.

9.	Pennsylvania Department of Transportation, at its sole cost and expense, furnish all material and do all work necessary to establish and maintain any detours or traffic controls at the subject crossing that may be required to properly and safely accommodate highway and pedestrian traffic during the time the crossing is being altered.

10. 	Nittany and Bald Eagle Railroad, at the sole cost and expense of Pennsylvania Department of Transportation, furnish all material and perform all work necessary to furnish any watchmen, flagmen, inspectors, and/or engineering services that may be deemed necessary to protect the railroad’s operations or facilities during the time the facilities are being installed.

11.	Any relocation of, changes in and/or removal of any adjacent structures, equipment or other facilities of any non-carrier public utility company or municipal authority located within the limits of the Commission’s jurisdiction, which may be required as incidental to the execution of the proposed project, be made by said public utility, at its initial cost and expense and in such manner as will not interfere with construction of the project.

12.	Any relocation of, changes in and/or removal of any adjacent structures, equipment or other facilities of any non-carrier public utility company or municipal authority located in private right-of-way within the limits of the Commission’s jurisdiction, which may be required as incidental to the execution of the crossing project, be made by said public utility or municipal authority and in such manner as will not interfere with the project.

13.	All parties involved herein cooperate fully with each other so that during the time the work is being performed, vehicular, pedestrian and railroad traffic will not be endangered or unnecessarily inconvenienced and so that the requirements of each of the parties will be provided for and accommodated insofar as possible.

14.	Pennsylvania Department of Transportation notify all parties of record at least ten (10) days prior to performing any work in accordance with this Secretarial Letter.

15.	Pennsylvania Department of Transportation, at least ten (10) days prior to the start of work, notify all parties in interest and local emergency management services of the actual date on which work will begin.

16.	All work necessary to complete the alteration of the subject crossing be done in a manner satisfactory to this Commission on or before December 31, 2022 and that on or before said date, Pennsylvania Department of Transportation report the date of actual completion of the work.

17.	All costs, which are to be reimbursed by the Department of Transportation consistent with this Secretarial Letter, shall be reimbursed as set forth in the provisions of 23 C.F.R. Parts 140 and 646. The aforesaid Federal reimbursement shall not supersede, delay or, in any manner, postpone the effect of any paragraph contained in this or any related Secretarial Letter or Order.

18.	Pennsylvania Department of Transportation pay all compensation for damages due to the owners of any property taken, injured or destroyed by reason of the alteration of the subject crossing in accordance with this Secretarial Letter.

19.	Upon completion of construction of the project, SEDA-COG Joint Rail Authority, at its sole cost and expense, furnish all material and perform all work necessary thereafter to maintain its railroad facilities at the crossing, including the automatically operated flashing-light warning signals and all appurtenant equipment, and to maintain at all times in a smooth and satisfactory condition the railroad crossing surfaces located between the rails and for a distance of twenty-four (24) inches beyond the rails; and provide 10-days of advance notice to College Township prior to doing any work at the crossing, all in accordance with this Secretarial Letter.

20.	Upon completion of construction of the project, College Township, at its sole cost and expense, furnish all material and do all work necessary to maintain the highway approaches to the subject crossing to points twenty-four (24) inches beyond each outside rail and, in addition, maintain the grade crossing advance warning signs and stop lines on the approaches thereto, in accordance with Part 8 of the Manual on Uniform Traffic Control Devices and this Secretarial Letters, and provide 10-days of advance notice to SEDA-COG Joint Rail Authority prior to doing any work at the crossing, all in accordance with Part 8 of the Manual on Uniform Traffic Control Devices and this Secretarial Letter.

21.	Upon completion of construction of the project, College Township, at its sole cost and expense, furnish all material and do all work necessary thereafter to maintain the highway traffic signals, blank out signs and traffic signal control box at the intersection of intersection of College Avenue (SR 0026) and Struble Road, and to maintain the cables from the junction boxes to both the traffic signal control boxes, in a safe and satisfactory condition.

22. 	Upon completion of the work herein directed, College Township, at its sole cost and expense, shall maintain and shall annually inspect the traffic signals, the traffic signal control boxes and the cables form the junction boxes to the traffic signal control box to ensure that the timing and preemption operation of the signal systems are functioning as designed.  College Township shall contact SEDA-COG Joint Rail Authority and arrange for railroad personnel to activate the railroad crossing warning system to accommodate the required inspection.  College Township shall report any operational problems that cannot be corrected during the annual inspection to both the Pennsylvania Department of Transportation and the Pennsylvania Public Utility Commission.

23.	Upon completion of the work herein directed, and upon written request from any party of record, this proceeding be scheduled for a hearing at a time and place to be determined by the Commission, for the purpose of taking testimony upon the final allocation of any costs incurred by the non-carrier utility companies and other matters relevant to this proceeding.

The Parties are reminded that failure to comply with this or any Order or Secretarial Letter in this proceeding may result in an enforcement action seeking civil penalties and/or other sanctions pursuant to 66 Pa. C.S. § 3301.

All parties are being served via email due to the COVID-19 Emergency Closure.  Please note that during this period of Disaster Emergency, the Commission shall only accept E-filings in lieu of paper filings, for all documents.  Thus, all parties are to open and use E-filing accounts to file documents and accept service during the pandemic emergency in accordance with the Commission’s Emergency Order at M-2020-3019262.

If you are dissatisfied with the resolution of this matter, you may, as set forth in 52 Pa. Code §§ 1.31 and 5.44, file a Petition for Reconsideration from Staff Action (Petition) with the Commission within twenty (20) days of the date of this letter.  The Petition shall be submitted by E-filing said petition within twenty (20) days, or if no timely request is made, the action will be deemed to be a final action of the Commission.

The Petition MUST include: (1) a written statement (divided into numbered paragraphs) outlining the reasons for the request; (2) the case docket number (it is provided for you at the top right hand corner of this letter); (3) the party on whose behalf the petition is made; (4) a Certificate of Service on the other parties of record; and (5) a Verification with original signature in accordance with 52 Pa. Code § 1.36.

Very truly yours,

Rosemary Chiavetta

Secretary