## Projects Under Consideration
Plan # | Project Name | Type | Description | Owner & Applicant | Lot Size (Acres) | Tax Parcel | Zoning | Status/Action | Time Expires | Escrow Balance as of MAY 15, 2019
496 N | Fieldstone at Lower Makefield Edgewood Road | Major Subdivision | 30 single-family residential building lots | Quaker Group Bucks, L. P. / Same | 39.2 | 20-16-73 | R-2 Residential Medium Density | Preliminary Plan | 2019-12-31 | 0
562 | Dogwood Drive (aka Harmony Lane) Dogwood Drive | Major Subdivision | 5 single-family residential building lots | Dogwood Drive, L.P. / Same | 14.727 | 20-8-25 | R-2 Residential Medium Density | Recommended for Final Plan Approval by PC 1/22/2018 | 2019-11-01 | 20.7
574 | Capstone Terrace Stony Hill Road at Township Line Road | Land Development | 3-story 180,000 sq. ft. office building | Shady Brook Investors, L.P. / Same | 14.855 | 20-16-39 20-12-1 20-12-2 | O/R Office Research | Final Plan Preliminary Approval by BOS 11/5/2008 | 2019-11-01 | 0
590 | Aria Health (fka Frankford Health System) Route 332 & Stony Hill Road | Land Development | 3-story 375,000 sq. ft. hospital, two (2)-40,000 sq. ft. medical buildings with 976 parking spaces & a heliport | Aria Health / Same | 41.178 | 20-12-1-1 | O/R Office Research | Preliminary Plan | 2019-12-31 | 39236.28
643 | Erin Development 1685 Dobry Road Dobry Road | Major Subdivision | 76 single-family attached dwelling Age-Qualified Community | Dobry Road, LLC. / ERIN Development | 16.57 | 20-12-28 | C-3 General Business Industrial | Preliminary Plan Variances approved at the 12/4/2018 ZHB meeting. Revised plans submitted in July 2019. | 2019-10-01 | -157.39
655 | Marrazzo Garden Center Property Yardley- Morrisville Road & Sutphin Road | Major Subdivision | 16 single-family attached townhouse dwellings w/ 10 parking spaces (non-conforming use) | Dan & Carmela Marrazzo / Same | 2.6 | 20-50-1-1 | R-2 Residential Medium Density | Sketch Plan Discussed by PC on 3/26/2018. | N/A | 502.04
658 | Snipes Tract Athletic Fields Dolington Road & Quarry Road | Land Development | 3 large & 1 small multi-purpose athletic fields, concession/restroom building, skate park, 157 parking spaces | Lower Makefield Township / Same | 36.26 | 20-16-2 20-16-1-1 | R-2 Residential Medium Density | Preliminary/Final Approval by BOS 5/30/2017. Remanded by Court back to Board of Supervisors. | N/A | N/A Township Project
664 | Fieldstone (Harris Tract) Edgewood Rd | Major Subdivision | 32 lot or 36 lot single-family residential building lots | Quaker Group Bucks, L.P. / J P O Fieldstone | 39.2 | 20-16-73 | R-2 Residential Medium Density | Informal Sketch Plan Discussed by PC on 1/22/2018. Discussed by BOS on 2/7/2018. | N/A | 0
665 | Weldon Homes LLC 1273 Lindenhurst Road | Major Subdivision | Subdivide a 3.03-acre lot containing an existing stone dwelling and stone barn into 3 single-family residential lots (creating 2 new building lots) | Weldon Homes LLC / Same | 3.03 | 20-3-20 | R-1 Residential Low Density | Informal Sketch Plan Discussed at PC meeting on 11/26/2018. | N/A | N/A
666 | Eric Renfors & George Schott TLY 670 LLC 670 Stony Hill Road | Special Exception | Proposed use of 2,040 sq. ft. of existing space within the Lower Makefield Shopping Center for a Learning Center for computer coding and game building | Eric Renfors & George Schott TLY 670 LLC / IRPF YARDLEY LOWER MAKEFIELD, LLC | 11.476 | 20-016-062 | C-1 Commercial Neighborhood Shopping | Special Exception Approved by ZHB 4/2/2019 | N/A | 0
667 | Shady Brook Investors (fka Capstone Terrace) Stony Hill Road at Township Line Road | Land Development | Proposed use for a 125,775 square foot single story warehouse building with 252 parking spaces | Shady Brook Investors, L.P. / Same | 14.855 | 20-16-39 20-12-1-3 20-12-2-2 | O/R Office Research | Special Exception ZHB Meeting held 4/16/2019. Continued to the 8/20/2019 ZHB meeting. | N/A | 0
668 | Lower Makefield Corporate Center North Campus Stony Hill Road at Route 332 | Land Development | Proposed reconfiguation of central parking area to create a courtyard that increases green space, outdoor gathering spaces, reduces parking spaces, traffic calming elements, and improved pedestrian circulation. | LMCC NORTH ACQUISITIONS LLC / SAME | 21.2139 | 20-016-041 | O/R Office Research | Preliminary/Final Plans submitted | 2019-09-22
669 | Lower Makefield Corporate Center South Campus Township Line Road at Stony Hill Road | Land Development | Proposed reconfiguation of front parking area to create a courtyard near the pond that increases green space, outdoor gathering spaces, reduces parking spaces, traffic calming elements, and improved pedestrian circulation. | LMCC SOUTH ACQUISITIONS LLC / SAME | 31.532 | 20-12-6-3 | O/R Office Research | Preliminary/Final Plans submitted | 2019-09-22

## Projects Recently Approved
Plan # | Project Name | Type | Description | Owner & Applicant | Lot Size (Acres) | Tax Parcel | Zoning | Approval Status | Status of Documents | Next Step | Escrow Balances , May 15,2019
642 | Kaplan Tract Dolington Road | Minor Subdivision | Subdivide 5 acres into 2 lots (1 nw building lot) | Ann Ryan Trust Lawrence Kaplan | 4.82 | 20-3-26-1 | R-1 Residential Low Density | Final Approval by BOS 6/21/2017 | Court denied and dismissed the appeal of the approval on 8/23/2018. Revised plans ready for recording. | Waiting on signed copies of documents and mylars, payment of fees, schedule pre- construction meeting | -1698
660 | Octagon Center – Office Condo Phase II Big Oak Road | Land Development | 4,500 sq. ft. office building (formerly a Dunkin' Donuts w/ a drive-thru) & a 11,909 sq. ft. Day Care Center located adjacent to Lower Bucks Pediatrics, with 114 total parking spaces | Aurliz LLC / Same | 3.88 | 20-32-3-1 | C-3 General Business Industrial | Final Amended Plan by BOS on February 6, 2019. | Revised plans submited to comply with the conditions of approval. Applicant will phase the project to construct only the Day Care improvements at this time. | Need to approve Development Agreement | -90

## Projects Under Construction
Plan # | Project Name | Type | Projects Under Consideration in the Review Process | Builder & Applicant | Lot Size (Acres) | Tax Parcel | Zone | Original Escrow/Bond | Escrow/Bond Balance Remaining | Project Status / Outstanding Items | Total # Building Lots | Building Permits Issued | Building C.O.'s Issued | Inspection Escrow Balance as of May 15, 2019
335 T | Regency at Yardley (fka Octagon Center) Big Oak Road & Oxford Valley Road | Major Subdivision | 191 single family dwellings and 186 townhouse (carriage homes) units with a clubhouse, pool, tennis courts, plus 5 acres along Old Oxford Valley Road to be donated to LMT (including a 2,500 SF pavilion) | Toll Brothers | 133.5 | 20-32-4-1 20-32-1-2 | C-3 | $783,860.83 $161,923.85 $2,860,142.73 $1,548,171.08 $619,016.72 $500,000.00 $6,473,115.21 North Total $826,000.00 $595,000.00 $668,350.00 $1,223,035.25 $3,312,385.25 South Total | $121,152.33 North Ph. 1 $27,400.60 North Ph. 2 $383,733.48 North Ph. 3 $345,439.24 North Ph. 4 $118,577.12 North Ph. 5 $49,710.98 North 6/7 $1,046,013.75 Remaining for North (Singles) $209,085.50 South Ph. I $205,742.25 South Ph. II $418,981.60 South Ph. III $776,075.00 South IV/V $2,306,213.00 Remaining for South (Carriages) | Regency North (Singles): Houses are all complete, except for 6 units adjacent to model homes. Toll Brothers is working on punchlists in anticipation of paving next Spring. Videos of sanitary sewer & storm sewer lines showed deficiencies that will need to be addressed prior to paving. Regency South (Carriages). Houses are 27% complete. Site improvements and roads are 80% complete (remaining area is the part of Phase 3 where sanitary sewer flows into Matrix Residential (62 unit) project across Big Oak Road). | North 197 South 180 | North 191 South 85 | North 191 South 49 | 9,169.04 Regency @ Yardley #D335T $7,219.48 Regency Carriage Homes #D338T
412 | Towering Oaks at Yardley Dolington Road & Susan Circle | Major Subdivision | 7 lot single family residential subdivision | Triumph Building Group / Towering Oaks LLC | 12.087 | 20-3-48 | R-1 | 447077.04 | 241650.23 | 6 of 7 houses are being constructed by Triumph Building Group. Outstanding items include final paving, landscaping, basin conversion, etc. | 7 | 6 | 5 | ($ 41,641.12) Billed for Shortage - w/Attorney for collections
538 | Boxwood Farm Oxford Valley Road & Collins Grant Court | Major Subdivision | Subdivide 8.0 acres into 5 single family residential lots | Boxwood Farm LLC | 5.84 | 20-32-21 | R-2 | 767757.34 | $302,577.43 (Release 4) | Township passed a resolution to make a claim against the bond on 11/26/2018. Developer performed final paving of Collins Grant Court on 12/4/2017, and there are still a few open items to resolve prior to dedication. If these items are completed we may be in position to rescind the Resolution to take action against his performance bond. | 8 | 8 | 8 | ($14,241.57) Billed for Shortage and requested $2,500 add’l deposit w/attorney for collections
543 | J.C. McGinn Construction (Minehart Tract) Woodside Road & Lindenhurst Road | Major Subdivision | Subdivide property into 7 single-family residential building lots and 1 lot to be added to adjoining property | Thomas & Catherine Minehart/ John C. McGinn | 30.86 | 20-3-28 20-3-28-2 | R-1 | 32525 | 32525 | Developer has requested release of Letter of Credit. Only outstanding items are on- lot stormwater management work for 2 unsold lots (Lot 2 & 7), payment of fee-in- lieu, and setting monuments. | 7 | 5 | 5 | 690.98
560 | Reserve at Yardley (aka Freeman's Farm or Ferri Tract) Big Oak Road | Major Subdivision | 14 single-family residential building lots and 1 existing lot | Toll Brothers/Erin Development Co. | 18.228 | 20-34-129 | R-2 | 851070.97 | $158,314.49 (Release 2) | RVE met with developer on 9/19/2018 to review last few items remain outstanding. Developer is compiling information in preparation for dedication. | 14 | 14 | 14 | ($829.27) Erin Dev #D560A
569 | Scammel’s Corner University Drive, Yardley-Newtown Road, West Afton Avenue | Major Subdivision | 15 single family residential lots, 1 existing lot with historic house reconstructed and 1 open space lot | J P O Scammels Corner L.P. | 17.73 | 20-16-32 | R-2 | 1020402.58 | $113,593.75 (Release 4) | Rain gardens & detention basins need additional work to drain properly. JP Orleans final paved on 12/14/2018. Developer is working with the Township Engineer to complete all items prior to dedication. | 16 | 16 | 16 | ($19,761.61) Billed, but not paying nor replying to requests. #D569S
596 | Zubaida Foundation Big Oak Road | Land Development | Convert existing church into a 6,365 SF mosque with 73 parking spaces | Zubaida Foundation | 5.09 | 20-41-2 | R-2 | 322282.68 | $45,018.43 (Release 6) | Building renovations are complete and an updated Certificate of Occupancy was issued. Remaining work includes parking lot striping, landscaping, etc. | n/a |  |  | 0
597 | Flowers Field @ Edgewood (Troilo) Stony Hill Road & Yardley- Langhorne Road | Major Subdivision/ Land Development | 48 single-family residential attached units, 12 apartments, and 273,238 S.F. of commercial space | DeLuca & Cameron Troilo Properties | 15.622 | 20-12-4-1 20-12-5 20-13-4 20-14-7 | TND | 3373000 | $222,738.14 (Release 11) | Outstanding improvements include final paving, sidewalk, landscaping, etc. DeLuca has 26 residential units built or under construction. No commercial units have been started. 22 vacant residential lots are owned by Cam Troilo. | 48 | 26 | 14 | $0.00 Troilo/#D597 ($267.25) Deluca/#D597B
612 | Estates at Sandy Run (St. Ignatius Subdivision) Sandy Run Road | Major Subdivision | Subdivide 34.55 acres into 8 single family residential lots and an open space lot | St. Ignatius RC Parish / Erin Development Company | 34.55 | 20-34-20-5 20-35-6 20-35-1-1 20-35-2-1 | R-2 | 723400 | $117,349.81 (Release 7) | Houses are under construction. Outstanding improvements include final paving, sidewalk, landscaping, etc. | 8 | 7 | 6 | ($345.02)
629 | Oakmont (Moon Nurseries) Quarry Road | Major Subdivision | 15 lot single-family residential subdivision | Toll PA XIII L.P. | 29.21 | 20-3-36-1 | R-1 | 1553783.34 | $304,788.11 (Release 3) | Developer final paved the roads on 11/30/2018. Developer is working on addressing topsoil/grass issues. Developer will need to work with the Township Engineer to complete all items prior to dedication. | 15 | 15 | 15 | $4,694.24
648 | Pennsbury School District Pennwood Middle School Makefield, Roelofs, & Big Oak Roads | Land Development | Building Renovations & reconfiguration of parking and traffic circulation | Pennsbury School District | 67.5 | 20-34-86 20-34-87 20-34-88 20-34-90 | R-2 | 4752000 |  | Building renovations and site improvements are nearing completion. RVE was PSD project engineer. | n/a |  |  | $156,394.27 Development $ 21,646.87 Planning
651 | Matrix Lower Makefield Residential Big Oak Road | Amended Major Subdivision | 62 single-family attached Age-Qualified dwellings (originally approved for 165 multi-family condominium units) | Big Oak Partners, L.P. / Ryan Homes | 19.439 | 20-32-6 | C-3 | 1927338.82 | $1,851,416.82 (Release 1) | Pre-construction meeting held 12/19/2018. Construction commenced on 1/7/2019, tree clearing has been completed and erosion measures have been installed. | 62 |  |  | $24,172.23 Development $ 91.90 Planning
652 | Artis Senior Living LLC Stony Hill Road | Land Development | 72 bed memory care facility (33,552 SF) with 43 parking spaces | Artis Senior Living LLC / Same | 5.34 | 20-12-3 20-12-3-1 20-13-2 20-13-2-1 | R-1 | 992600 | 992600 | Pre-construction meeting held on 10/10/2018. Parking area is uner construction and work on the building is progressing. | n/a |  |  | $32,930.83 Development $ 0.00 Planning
663 | Caddis Healthcare Real Estate Senior Living Facility (aka Heartis Village at Yardley) Dobry Road & Oxford Valley Road | Land Development / Lot Line Change | 2-story, 98-bed Assisted Living and Memory Care facility (95,587 square foot gross floor area), 71 parking spaces | Caddis Healthcare Real Estate | 8.62 | 20-32-8-2 20-32-9 | C-3 |  |  | Pre-construction meeting held on | n/a |  |  | $2,690.00 Construction $3,385.25 Planning

## Projects Recently Completed
Plan # | Project Name | Type | Projects Under Consideration in the Review Process | Builder & Applicant | Lot Size (Acres) | Tax Parcel | Zone | Original Escrow/Bond | Escrow/Bond Balance Remaining | Project Status / Outstanding Items | Total # Building Lots | Building Permits Issued | Building C.O.'s Issued | Inspection Escrow Balance as of May 15, 2019
532 | Brookshire Estates (Flowers Madany) Graystone Lane/ Washington Crossing Road | Major Subdivision | Subdivide 64.6 acre into 29 lots (including 1 lot in Newtown Twp.) and 3 open space lots (including 1 in Newtown Twp.) | Orleans Homes/ Brookshire Estates L.P. | 64.6 | 20-3-4 20-3-11-2 29-16-8 | R-1 | Phase 1 $2,296,558.68 Phase 2 $791,664.04 | 0 | Dedication approved at 12/5/2018 BOS meeting. Maintenance Bond expires on May 26, 2020. | Phase 1 21 Phase 2 7 | Phase 1 21 Phase 2 7 | Phase 1 21 Phase 2 7 | ($4,913.13) billed for shortages
565 | Brookshire III (Troilo Tract) Washington Crossing Road | Major Subdivision | Subdivide 8.0 acres into 5 single-family residential lots | Orleans Homes/ Brookshire Estates L.P. | 8.02 | 20-3-10 | R-1 | 632074.98 | 0 | Dedication approved at 12/5/2018 BOS meeting. Maintenance Bond expires on May 18, 2020. | 5 | 5 | 5 | 1346.05
662 | Widenmeyer Lot Line Change 1085 Reading Avenue | Lot Line Change / Minor Subdivision | Change Lot Line between parcels to have a 1.10 acre lot and a 10.06 acre lot. No new lots are created. | Maryanne Widenmeyer / Same | 11.16 | 20-35-2-3 20-35-4 | R-2 | n/a | n/a | Plans recorded with Bucks County Recorder of Deeds. | n/a | n/a | n/a | 868.64