|  | COMMONWEALTH OF PENNSYLVANIA PENNSYLVANIA PUBLIC UTILITY COMMISSION COMMONWEALTH KEYSTONE BUILDING 400 NORTH STREET HARRISBURG, PENNSYLVANIA 17120 |  | IN REPLY PLEASE REFER TO OUR FILE |
| --- | --- | --- | --- |

IN REPLY PLEASE

REFER TO OUR FILE

November 23, 2021

A-2020-3019481

Via Eservice and Email Only

TO ALL PARTIES OF RECORD

Application of PPL Electric Utilities Corporation for approval to alter the public crossing (DOT 592 369 S) where E. Derry Road (T-504) crosses at grade the tracks of Norfolk Southern Railway Company, in Derry Township, Dauphin County, by reason of the installation of communication facilities.

To Whom It May Concern:

By Secretarial Letter dated May 15, 2020, we directed the alteration of the crossing, (DOT 592 369 S), where E. Derry Road (T-504) crosses, at grade, tracks of Norfolk Southern Railway Company, in Derry Township, Dauphin County.  All work at the subject crossing was to be completed on or before May 31, 2021.

By electronic mail received on November 18, 2021, PPL Electric Utilities Corporation (PPL) requested the Commission revise the completion date to accommodate unexpected delays.

We have carefully reviewed the record in this proceeding and will grant PPL an extension of time to December 31, 2022.

1.	Paragraph 8 of our Secretarial Letter Served May 15, 2020, which reads as follows, to wit:

“8.	The alteration of the crossing be completed on or before May 31, 2021, and that on or before said date, PPL Electric Utilities Corporation, report in writing the date of actual completion of the work to this Commission and certify to the parties of record and this Commission that the work has been satisfactorily completed in accordance with the approved plans and this Secretarial Letter.”

be and is hereby modified to read:

8.	The alteration of the crossing be completed on or before December 31, 2022, and that on or before said date, PPL Electric Utilities Corporation, report in writing the date of actual completion of the work to this Commission and certify to the parties of record and this Commission that the work has been satisfactorily completed in accordance with the approved plans and this Secretarial Letter.

2.	In all other respects, our Secretarial Letter dated May 15, 2020, remains in full force and effect.

The Parties are reminded that failure to comply with this or any Order or Secretarial Letter in this proceeding may result in an enforcement action seeking civil penalties and/or other sanctions pursuant to 66 Pa. C.S. § 3301.

The Commission has waived certain regulatory service provisions as directed by the Commission’s Order at M-2021-3028321.  Currently, while the Commission’s physical facilities are open for business, some of the operational restraints occasioned by the pandemic remain.  It is evident that the pandemic and its changing nature require certain procedural flexibility for the public, the regulated community, and the Commission.  Toward this end, the Commission will continue to permit electronic service by the Commission on all parties, regardless of whether a particular party has agreed to electronic service.  An exception to this general waiver is where the Public Utility Code requires service by specified means, e.g., Section 702.  Additionally, service on Commission staff in proceedings pending before it, whether staff is a party or otherwise, shall be exclusively electronic unless the parties agree otherwise.  Filings must be submitted by efiling with the Secretary of the Commission by opening an efiling account through the Commission’s website and accepting eservice at https://www.puc.pa.gov/filing-resources/efiling/.  If your filing contains confidential material, you are required to file by overnight delivery to ensure the timely filing of your submission.

If you are dissatisfied with the resolution of this matter, you may, as set forth in 52 Pa. Code §§ 1.31 and 5.44, file a Petition for Reconsideration from Staff Action (Petition) with the Commission within twenty (20) days of the date of this letter.  The Petition shall be submitted by e-filing said petition within twenty (20) days, or if no timely request is made, the action will be deemed to be a final action of the Commission.

The Petition MUST include: (1) a written statement (divided into numbered paragraphs) outlining the reasons for the request; (2) the case docket number (it is provided for you at the top right hand corner of this letter); (3) the party on whose behalf the petition is made; (4) a Certificate of Service on the other parties of record; and (5) a Verification with original signature in accordance with 52 Pa. Code § 1.36.

Very truly yours,

# Rosemary Chiavetta

Secretary