| COMMONWEALTH OF PENNSYLVANIA PENNSYLVANIA PUBLIC UTILITY COMMISSION 400 NORTH STREET, HARRISBURG, PA 17120; IN REPLY, PLEASE REFER TO OUR FILE. | COMMONWEALTH OF PENNSYLVANIA PENNSYLVANIA PUBLIC UTILITY COMMISSION 400 NORTH STREET, HARRISBURG, PA 17120 | IN REPLY PLEASE REFER TO OUR FILE |
| --- | --- | --- |

December 1, 2021

Docket No. M-2021-3029293

Utility Code: 125042

CRAIG BERRY, SENIOR ATTORNEY

LEGAL DEPARTMENT

PHILADELPHIA GAS WORKS

800 W. MONTGOMERY AVENUE

PHILADELPHIA, PA 19122

craig.berry@pgworks.com

Re:	Annual Asset Optimization Plan (AAOP) for the Philadelphia Gas Works (PGW) – Docket No. M-2021-3029293

Dear Mr. Berry:

On October 27, 2021, Philadelphia Gas Works (PGW) filed its Annual Asset Optimization Plan (AAOP), pursuant to 52 Pa. Code § 121.6.

The Commission’s regulations require NGDCs with an approved Distribution System Improvement Charge (DSIC) to file annually an AAOP with the Commission. The AAOP shall be filed 60 days after the prior 12 months of the company’s Long Term Infrastructure Improvement Plan (LTIIP) has expired, and pursuant to this timeframe for each successive AAOP (52 Pa. Code § 121.6(a)).

The AAOP must include:

- A description that specifies all of the eligible property repaired, improved, and replaced in the prior 12-month period under its LTIIP and prior year’s AAOP.

- A description of the eligible property to be repaired, improved, and replaced in the upcoming 12-month period.

The Commission is charged with reviewing each AAOP only to determine whether the utility is in substantial compliance with the repairs, improvements, or replacements of the specific eligible property in its approved LTIIP, for the corresponding 12 month timeframes.  52 Pa. Code § 121.6(d).  The Commission has delegated the review of AAOPs to the Bureau of Technical Utility Services.

Timely Filing

52 Pa. Code § 121.6(a)

A utility with an approved DSIC shall file with the Commission, for informational purposes, an AAO plan. The AAO plan shall be filed annually with the Commission 60 days after the 12 months of its LTIIP has expired and under this time frame for each successive year of the term of the LTIIP.

PGW’s LTIIP is delineated by PGW’s fiscal year, rather than by calendar year.  PGW’s fiscal year spans September 1 of each year to August 31 of the following year, and is due by October 30.  PGW filed their AAOP on October 27, 2021 and is in compliance.

Content

52 Pa. Code § 121.6(b)

An AAO plan must include:

- A description that specifies all the eligible property repaired, improved and replaced in the prior 12-month period under its LTIIP and prior year’s AAO plan.

- A description of the eligible property to be repaired, improved and replaced in the upcoming 12-month period.

PGW’s AAOP substantially complies with this requirement.

Substantial Adherence to LTIIP

52 Pa. Code § 121.6(d)

An AAO plan will be reviewed by the Commission only to determine whether the utility is in substantial compliance with the repairs, improvements or replacements of the specific eligible property in its approved LTIIP for the corresponding 12-month time frames.

52 Pa. Code § 121.6(e)

Absent any major modifications to the LTIIP or Commission action to reject an AAO plan within 60 days of its submission to the Commission, the AAO plan will be deemed approved. The Commission may extend its consideration period if necessary.

52 Pa. Code § 121.6(f)

If an AAO plan is rejected by the Commission, the utility will be notified of the plan’s deficiencies and actions needed to repair, improve or replace eligible property to bring the utility into compliance with the work schedule in its approved LTIIP. If the utility concludes that it needs to revise its LTIIP to comply with the Commission’s determinations, it shall file a petition for modification under § 121.5.

PGW exceeded its FY 2021 LTIIP goal for accelerated pipeline replacement by 5.84 miles, with 19.43 miles of accelerated replacement.  This 43% increase in accelerated replacement was accompanied by a corresponding increase in spending of $5.5 million, an increase of only 15.5% from PGW’s LTIIP projections.  PGW’s increase in main replacement more than made up for the previous year’s (FY 2020) shortfall of 4.44 miles, putting PGW back on track with its LTIIP projections.

Compliance with the LTIIP is evaluated on a multiyear basis over the life of the LTIIP.  Construction and budget variations in individual years can be expected and it is reasonable to expect that over a multi-year timeframe, much of this variation will be mitigated.

The AAOP does not propose a Major Modification to the company’s LTIIP.

Accordingly, PGW’s AAOP appears to substantially conform to the schedule set forth in the company’s LTIIP.

Conclusion

Upon review of PGW’s Annual Asset Optimization Plan filed on October 27, 2021, it appears that the filing substantially complies with the requirements of 52 Pa. Code § 121.6 and is approved.  This approval is contingent upon the possibility that subsequent audits, reviews and inquiries, in any Commission proceeding, may be conducted pursuant to 52 Pa. Code § 121.

If you are dissatisfied with the resolution of this matter, you may, as set forth in 52 Pa. Code § 5.44, file a petition with the Commission within twenty (20) days after the date of this letter.  Please direct any questions regarding this filing to Matthew Stewart, Gas Reliability Engineer, Bureau of Technical Utility Services at mattstewar@pa.gov.

Sincerely,

Rosemary Chiavetta

Secretary

cc:	Kriss Brown, LAW

Richard Kanaskie, BIE

Dan Searfoorce, TUS

John Van Zant, TUS

Raymond Welte, PGW, raymond.welte@pgworks.com